Space engineering

ECSS Secretariat

ESA-ESTEC

Requirements & Standards Division

Noordwijk, The Netherlands

Technology readiness level (TRL) guidelines

This draft is distributed to the ECSS Community for Public Review.

Start of Public Review: 23 February 2016

End of Public Review: 20 May 2016

DISCLAIMER (for drafts)

This document is an ECSS Draft Standard. It is subject to change without any notice and may not be referred to as an ECSS Standard until published as such.

Foreword

This Handbook is one document of the series of ECSS Documents intended to be used as supporting material for ECSS Standards in space projects and applications. ECSS is a cooperative effort of the European Space Agency, national space agencies and European industry associations for the purpose of developing and maintaining common standards.

The material in this Handbook is defined in terms of description and recommendation how to organize and perform the work of Technology Readiness Level (TRL) assignment through the Technology Readiness Assessment (TRA) and reporting through the Technology Readiness Status List (TRSL)

This handbook has been prepared by the TRL Task Force, reviewed by the ECSS Executive Secretariat and approved by the ECSS Technical Authority.

Disclaimer

ECSS does not provide any warranty whatsoever, whether expressed, implied, or statutory, including, but not limited to, any warranty of merchantability or fitness for a particular purpose or any warranty that the contents of the item are error-free. In no respect shall ECSS incur any liability for any damages, including, but not limited to, direct, indirect, special, or consequential damages arising out of, resulting from, or in any way connected to the use of this document, whether or not based upon warranty, business agreement, tort, or otherwise; whether or not injury was sustained by persons or property or otherwise; and whether or not loss was sustained from, or arose out of, the results of, the item, or any services that may be provided by ECSS.

Published by: 	ESA Requirements and Standards Division

ESTEC, P.O. Box 299,

2200 AG Noordwijk

The Netherlands

Copyright: 	2016 © by the European Space Agency for the members of ECSS

Change log

| Previous Step: |  |
| --- | --- |
| ECSS-E-HB-11A DFR1 18 December 2015 | Draft for Review (DFR) Draft from the WG submitted for Parallel Assessment. |
| ECSS-E-HB-11A DFR2 16 February 2016 | Updated DFR1 agreed between ES and F. Durand-Carrier released for Public Review. |
| Current Step: |  |
| ECSS-E-HB-11A DIR1 16 February 2016 | Draft in Review (DIR1) Public Review from 23 February until 20 May 2016 |
| Next Steps: |  |
| DRR implementation |  |
| DRR Feedback |  |
| TA Vote for publication |  |

Table of contents

Change log	3

Introduction	7

1 Scope	8

2 References	9

3 Terms, definitions and abbreviated terms	10

3.1	Terms defined in other documents	10

3.2	Terms specific to the present document	11

3.3	Abbreviated terms and symbols	12

4 TRL history and evolution	13

4.1	History and evolution	13

4.2	Differences between M95r and ISO 16290 standard as seen by ECSS	13

4.3	TRL implementation in ECSS system	14

4.4	TRL basic principle	14

5 Technology readiness assessment guidelines	17

5.1	Introduction	17

5.2	General principles for technology readiness assessment	17

5.2.1	TRL standard	17

5.2.2	TRA pre-requisites	18

5.2.3	Independent verification of the TRL	19

5.2.4	Discipline specific TRA process	19

5.2.5	Typical technology readiness assessment process	22

5.2.6	TRA criteria	22

5.2.7	Viability of TRL progression	23

5.3	TRL evaluation by level	23

5.3.1	TRL 1: Basic principles observed and reported	23

5.3.2	TRL 2 : Technology concept and/or application formulated	23

5.3.3	TRL 3 : Analytical and experimental critical function and/or characteristic proof-of-concept	24

5.3.4	TRL 4 : Component and/or breadboard functional verification in laboratory environment	24

5.3.5	TRL 5 : Component and/or breadboard critical function verification in a relevant environment	25

5.3.6	TRL 6: Model demonstrating the critical functions of the element in a relevant environment	26

5.3.7	TRL 7 : Model demonstrating the element performance for the operational environment	27

5.3.8	TRL 8 : Actual system completed and accepted for flight (“flight qualified”)	27

5.3.9	TRL 9: Actual system “flight proven” through successful mission operations	28

5.4	Guidelines for other uses of TRLs in R&T&D activities	28

6 Implementation in projects	31

6.1	General	31

6.2	Critical functions and technologies in projects	32

6.2.1	Overview	32

6.2.2	Technology Readiness Status List and transference to Critical Item List	33

6.3	Technology Readiness Assessment in projects	33

6.4	Typical levels linked to project phases and milestones	34

7 Links with model philosophy and techno-demonstration, and, reassessment	38

7.1	Links with model types and techno-demonstration	38

7.1.1	Link between TRL and model types	38

7.1.2	Link between TRL and Technology Demonstrators	41

7.2	Re-assessment of TRL for re-use of element with existing TRA	43

7.2.1	Technical guidelines	43

7.2.2	Technology re-use in a new environment	45

Annex A TRL considerations for specific disciplines	46

A.1	TRL considerations for Software	46

A.1.1	SW-specific guidelines for TRA	46

A.1.2	Use of TRL with Software	48

A.1.3	Relationship between TRL and Criticality Categories	53

Annex B TRL considerations for specific disciplines	54

B.1	TRL considerations for EEE Components	54

B.1.1	EEE components	54

Annex C TRL considerations for specific disciplines	58

C.1	TRL considerations for materials and manufacturing process	58

Figures

Figure 4-1: Illustration of differences between M95r (European interpretation) and ECSS-E-AS-11	14

Figure 4-2: Evolution technology maturity	15

Figure 5-1: Illustration of an RF amplifier progressing through TRL	19

Figure 5-2: Example of ESA Technology Activity TEMPLATE	29

Figure 5-3: Illustration of a Technology Roadmap	30

Figure 6-1: Risk versus TRL and complexity	32

Figure 6-2: Evolution of technology options during preliminary project phases	34

Figure 6-3: Project phases and generalised institutional expectation of TRA outcome	36

Figure 6-4: Project phases and generalised commercial expectation of TRA outcome	37

Tables

Table 5-1: Example of increasing level of integration of the TRA subject with TRL growth	18

Table 5-2: TRL summary: Milestones and work achievement (reproduced from ISO 16290:2013)	20

Table 6-1: Benefits of use of TRA	35

Table 7-1: Models types associated to TRLs	39

Table 7-2: Use of commonly-used models for TRL progression	41

Table 7-3: Links between TRL and Heritage Category	44

Table 7-4: Technology maturity transfer for re-use	45

Table A-1 : Use of TRL with Software development	48

Table B-1 : Use of TRL for with EEE component development	56

Table C-1 : Use of TRL for with materials and manufacturing process development	59

Introduction

This Handbook a supports the application of the TRL, and provides guidelines to its use in projects and its independent verification within each specific project context.

This Handbook provides guidelines for best practice for interpretation of the requirements contained in ECSS-E-AS-11 and for the implementation of the process of TRL assessment for technologies applied to critical functions for which the maturity is to be assessed.

The ECSS-E-AS-11 - “Adoption Notice of ISO 16290 Definition of the Technology Readiness Levels (TRLs) and their criteria of assessment” adopts ISO 16290 with a minimum set of modifications, to allow for reference and for a consistent integration in ECSS system of standards.

TRL is a tool for technology maturity assessment and not a method of technology engineering nor development. TRL is used in R/T&D activities and also in project activities.

For project activities, a TRL assessment informs the project manager (until the end of B phase) of the risk when adopting a new technology for a critical function of the system. In the C&D phases TRL is no longer used by the project and the maturity of technology is managed in the critical item list.

For other projects the information of the declared technology maturity can be reused and an assessment of the new project use conditions are considered in the assessment.

In this handbook the three main actors and the respective role of each actor are clearly identified. The three discrete actors are: technology developers (R/T&D), projects team (using the technology) and the TRL assessors (who perform the technology maturity assessment).

# Scope

The present handbook is provided to support the implementation of the requirements of ECSS-E-AS-11C to space projects.

With this purpose, this handbook provides guidelines on the way to assess the technology of a product in a given environment, to use the TRL analysis outcome in the product development framework, and, to introduce some refinements for specific disciplines and/or products for which the TRL assessment methodology can be extended to.

The concept of Manufacturing Readiness Level (MRL) is not addressed in this document, whilst the concept of TRL can be applied to the technology-related aspects of manufacturing.

# References

The following documents are referenced in this text or provide additional information useful for the reader.

| ECSS-E-AS-11 | Adoption notice of ISO 16290 |
| --- | --- |
| ISO 16290:2013 | Space systems -- Definition of the Technology Readiness Levels (TRLs) and their criteria of assessment |
|  | TECHNOLOGY READINESS LEVELS ¬ A White Paper ¬ April 6, 1995 ¬ John C. Mankins Advanced Concepts Office ¬ Office of Space Access and Technology NASA 1 |

# Terms, definitions and abbreviated terms

## Terms defined in other documents

          - For the purpose of this document, the terms and definitions from ECSS-E-AS-11 apply, in particular for the following terms:

            - critical function of an element

            - element

            - breadboard

            - laboratory environment

            - mature technology

            - relevant environment

            - reproducible process

            - validation

          - For the purpose of this document the terms from ECSS-S-ST-00-01, except the terms listed in 3.11.1.1a. apply, in particular for the following term:

            - commissioning result review

            - environment

- The definition of environment in ECSS-S-ST-00-01 "ECSS Glossary" include both the natural and the induced conditions. The induced conditions include not only induced interference, heat, vibration, pollution and contamination (as stated in the EXAMPLE given in the definition in the ECSS Glossary), but also any kind of working condition created by the product in which the element is integrated. Where the element is integrated in a different product, the environment experienced by the element is also different (i.e. the environment is changing as the level of integration of the element is increasing). For additional clarification, see 5.2.2.

            - ground segment

            - technology readiness level

          - For the purpose of this document the terms from ECSS-E-ST-70, except the terms listed in 3.11.1.1a. and 3.1.b apply, in particular for the following term:

            - Ground Segment QR (GSQR)

            - Operations QR (OQR)

            - Software Requirement Specification (SRS)

## Terms specific to the present document

- ALPHA version

<software> preliminary version of software that implements the main functionality of the software product.

- Only preliminary V&V activities are achieved with this version.

- BETA version

<software> first software version that implements the complete function of the software product.

- The first software version is that for the in the software release life-cycle software version. V&V activities are only partially achieved with this version.

- component

part or all of an element

- The element can be a component, a piece of equipment, a subsystem or a system.

- customization

<software> adaptation to a dedicated environment including code modification

- software building blocks

<software> software element that has an identifiable function within a software product, and that can potentially be reused for a range of applications

- software element

<software> technology provided by software under consideration of TRL assessment

- Examples are Software Building Blocks, COTS, Open Source Software.

- software product

<software> software that is developed for an application, and which is composed of several software elements, with its associated procedures, documentation and data

- software tool

<software> software element that is used for supporting specific activities of the software life-cycle

- tailoring

<software> adaptation to a dedicated environment, without code modification

- Example would be the modification of the Generic Product configuration.

## Abbreviated terms and symbols

For the purpose of this document, the abbreviated terms from ECSS-S-ST-00-01 and the following apply:

| Abbreviation | Meaning |
| --- | --- |
| TRL | Technology Readiness Level |
| R&T&D | Research and Technology and Development |
| TRA | TRL Assessment |

# TRL history and evolution

## History and evolution

The TRL methodology was originated at NASA in the seventies in order to establish a method by which they  selected new technology amongst numerous candidates for their complex spaceflight programmes. The scale progressed until 1995 with the definition of nine levels that became the Mankins 95 reference (M95r) [ref 1]. From that moment, the principle of a maturity scale was adopted by many companies and government agencies around the world. However, although they were somewhat similar, different definitions or interpretation of the M95r were used. ECSS decided in 2008, to make a harmonization at European level then proposed to ISO a global harmonization in 2009 with the New Work Item Proposal (NWIP) “Definition of the Technology Readiness Levels (TRLs) and their criteria of assessment”.

The ISO standard 16290 was published in 2013 and as a result, TRL are now globally harmonized.  ECSS actively contributed to this standard by providing members to the ISO WG. The ISO standard concerns the definition and the criteria of assessment, however the procedure for the TRL assessment or the way to use them within projects framework is not the object of the standard. The standard is applicable primarily to space system hardware, although the definitions are used in a wider domain in many cases.

It is important to recognise that the ISO standard introduces some modifications with regards to the M95r previous interpretation in ECSS documents.

## Differences between M95r and ISO 16290 standard as seen by ECSS

M95r and ISO 16290 definitions are equivalent for levels 1, 2, 3 and 4.

ISO level 5 is a new intermediate level used when models at sub-scales are used, and ISO level 6 is equivalent to M95r level 5.

M95r level 6 has been shifted to ISO level 7.

M95r level 7 which was “System prototype demonstration in space environment” has been removed in ISO.

M95r and ISO 16290 definitions are equivalent for levels 8 and 9 respectively defining “flight qualified” and “flight proven” for the actual systems.

Differences between M95r and ISO are summed up in Figure 4-1.

Figure 4-1: Illustration of differences between M95r (European interpretation) and ECSS-E-AS-11

For the remainder of this handbook, the term TRL is referring to ECSS-E-AS-11 definition.

## TRL implementation in ECSS system

TRL are implemented in ECSS system following four ways:

1.	adoption of the ISO 16290 with an Adoption Notice (AN ref ECSS-E-AS-11),

2.	in the ECSS standards the reference to the AN when TRL are used,

3.	in the ECSS standards the requirements to manage the use of TRL,

4.	the provision of guidelines in this handbook.

The adoption notice ECSS-E-AS-11 was necessary to provide a concise method of introducing the ISO standard in ECSS system.  The AN was needed to make normative the TRL following ECSS editorial rules, to align the terms definition and to make reference when necessary to ECSS type of reviews.

This handbook provides guidelines on the way to assess the product, to use the TRL analysis outcome in the product development framework, and, to introduce some refinements for specific disciplines and/or products.

## TRL basic principle

TRL analysis allows for the assignment of a measure of the maturity of a technology. It needs to be made clear that undertaking a TRL analysis is not a method to develop technologies. The way to develop, to test, to qualify or to verify the development cycle of products, or the model philosophy defined by projects, are not the object of TRL but the purpose of others discipline-specific ECSS standards and handbooks.

The measure provided by TRL assessment is valid for a given element, at a given point in time, and a given defined environment.  It changes if the conditions that prevailed at the time of the assessment are no longer valid. Such a situation leads to TRL reassessment and re-grading, which can occur in particular when the re-build or re-use of an element is envisioned with variation in the design, development process, targeted environment or operations.

During Research and Development, or Research and Technology (R&T&D) activities, TRL can be used by the specialists developing the technologies to present their development plans (e.g. technology roadmaps) and to communicate with non-specialists or project managers, the costs or risks involved in taking particular technology choices with different TRLs.

In the framework of projects, TRL are used during preliminary phases (0,A,B) as a tool supporting the decision whether or not to use or integrate specific technology in a space mission, and allowing such decision to be taken with sufficient knowledge of any risk relating to the degree of maturity.

Generally R&T&D programs push (“research push”) the technologies maturity as far as the intermediate TRLs. Projects pull some technologies and develop these to the higher levels of maturity.

The intermediate levels of maturity (typically TRL 4, 5 & 6) are sometimes called “valley of death” since some technologies are developed until TRL 4 or below, however they never go through them (i.e. in the absence of a project “pull”) as projects are normally interested in TRL 6 or above (see Figure 4-2).

The costs associated with a specific technology achieving each level are generally increasing with each level attained.

Figure 4-2: Evolution technology maturity

It is important to highlight the following aspects in the application of TRL:

- TRL assessment is not intrinsic to a technology: if a new target environment has different constraints or performance requirements, a TRL needs to be reduced (e.g. a TRL 9 in one application falls even as far as TRL 4 in another).

- TRL 5 and higher are assessed to a specific mission environment: when a high TRL element is intended to be used in a different environment, the implications of the new environment being the potential for a TRL downgrade.

- TRL does not take into account industrial capacities of production or technology access constraints (e.g. : International Traffic in Arms Regulations).

- TRL does not take into account technology obsolescence, however conversely obsolescence can drive the need for a TRL re-assessment.

- If the production of a component of a high TRL element is discontinued, the TRL of the element can be affected.

- TRL does not replace development cycle or quality rules.

- TRL is not mandatorily incremental: It is not mandatory to achieve level 5 (sub-scale) before proceeding to level 6. More generally, it is not mandatory to go systematically through all levels.

- A TRL can only be reached by a component if all of the sub-components are at least at the same level.

- An R&T&D action does not necessarily lead to an increment in TRL.

- The time or effort to move from one TRL to another are technology dependent and cannot be linearly projected along the TRL scale.

- the proof necessary for the assessment of TRL:

  - For TRL 7 and 8, when the derivation of the evidence for the assessment of TRL is based on testing, the test is performed using the requirements of ECSS-E-ST-10-03 which addresses the requirements for performing hardware verification by testing of space segment elements and space segment equipment on ground prior to launch.

  - However, for TRL 1 to 6 where the derivation of the evidence for the assessment of TRL is selected to be based on testing, the test is performed using the state-of-the-art rules relevant to the TRL being assessed. For further details see clause 4.

# Technology readiness assessment guidelines

## Introduction

Clause 4 provides a set of guidelines for the use of the TRLs in conducting Technology Readiness Assessments (TRAs), starting with some general description of a typical process for conducting TRAs, followed by a series of detailed guidelines for TRAs, one for each Technology Readiness Level is proposed.

The value of a TRA exercise is to inform new programmes about the work already achieved on new technologies and optimise synergies between programmes. Technologies often have been developed in the frame of institutional programmes, or through R/T&D activities to prepare commercial programmes. For teams working in technology development, TRL is a way to promote (i.e. push) technologies into programmes. TRL helps to build roadmaps and helps to optimise funding opportunities in providing a framework for the assessment of risk associated with the related technology.

There are potentially three entities involved with the TRA: the entity requesting the TRA, the supplier of the technology, and the technology readiness assessment team (including the independent assessor).

- The entity requesting the TRA, e.g. a project or an R/T&D programme, can be internal or external to the technology developer organisation.

## General principles for technology readiness assessment

### TRL standard

A TRA implements the requirements of TRL Adoption Notice ECSS-E-AS-11 (which adopts the definitions and criteria of assessment of ISO 16290) which is provided at a high-level of detail in Table5-2: “TRL summary: Milestones and work achievement”.

### TRA pre-requisites

A pre-requisite of any TRA activity is the clear identification of the element that is subject to assessment.

In general, the reason for this clear identification is that

- the level of integration of the element under assessment increases when moving up in the TRL scale (particularly for TRL 5 and over).

- when moving up, critical functions and performance need to be demonstrated

  - in the laboratory environment (TRL 4)

  - in the relevant environment (TRL 5 and 6),

  - for the operational environment (TRL 7), or

  - in the complete system in flight configuration (TRL 8/9)

- other products interfacing with or integrated in the element may have an impact on its performance in providing the critical function(s). The number of products will increase with the level of integration and therefore with the progression of the TRL.

- Many of these interactions are easily predictable, but some others can be not so evident until verified by test. For example, EMC is an issue considered when increasing the level of integration.

Table 5-1 represents how the level of integration can grow when TRL is increasing, through the example of a transistor using new technology, integrated into an amplifier and subsequently into a piece of communication equipment.

Until and including TRL 4, the TRA is performed on the element a transistor in this example.

For TRL 5 and TRL 6, the critical functions are demonstrated in the relevant environment. Therefore this example the transistor is then integrated in to an amplifier, and the amplifier is then the object of the assessment.

For TRL 7 (equivalent to qualification in Space projects) the assessment needs to be performed for the operational environment. In this example, the object of qualification is the equipment in which the amplifier is integrated.

For TRL 8, the system is accepted for flight, and therefore the equipment needs to be tested for acceptance integrated into the flight system.

For TRL 9 the equipment is flown in an operational mission.

- In accordance with clause 3.7 the transistor, the amplifier and equipment have reached TRL 9 for the relevant operational environment.

Table 5-1: Example of increasing level of integration of the TRA subject with TRL growth

| Element/technology which TRL is wanted to be measured | TRA subject TRL 1, 2, 3 & 4 | TRA subject TRL 5 & 6 | TRA subject TRL 7 | TRA subject TRL 8 & 9 |
| --- | --- | --- | --- | --- |
| Transistor | Transistor | Amplifier | Communication equipment | Flight system |

Figure 5-3: Illustration of an RF amplifier progressing through TRL

### Independent verification of the TRL

- In order to ensure that a TRA of an element is objective, it is  completed by independent expertise in the discipline as detailed in ECSS-E-ST-10, i.e. not part of the technology developer engineering team.

- TRA process is similar to any review process where the review board is independent from the project team as detailed in ECSS-M-ST-10-01.

- The TRA includes details of the technology developer engineering team and provides those for the independent assessors.

### Discipline specific TRA process

EEE components, Materials and Process and Software have their own dedicated development and qualification processes consistent with the generic TRA approach given. For these disciplines the TRA is undertaken as covered in Annex A, Annex B and Annex C.

Table 5-2: TRL summary: Milestones and work achievement (reproduced from ISO 16290:2013)

| Technology Readiness Level | Milestone achieved for the element | Work achievement (documented) |
| --- | --- | --- |
| TRL 1: Basic principles observed and reported | Potential applications are identified following basic observations but element concept not yet formulated. | Expression of the basic principles intended for use. Identification of potential applications. |
| TRL 2: Technology concept and/or application formulated | Formulation of potential applications and preliminary element concept. No proof of concept yet. | Formulation of potential applications. Preliminary conceptual design of the element, providing understanding of how the basic principles would be used. |
| TRL 3: Analytical and experimental critical function and/or characteristic proof-of-concept | Element concept is elaborated and expected performance is demonstrated through analytical models supported by experimental data/characteristics. | Preliminary performance requirements (can target several missions) including definition of functional performance requirements. Conceptual design of the element. Experimental data inputs, laboratory-based experiment definition and results. Element analytical models for the proof-of-concept. |
| TRL 4: Component and/or breadboard functional verification in laboratory environment | Element functional performance is demonstrated by breadboard testing in laboratory environment. | Preliminary performance requirements (can target several missions) with definition of functional performance requirements. Conceptual design of the element. Functional performance test plan. Breadboard definition for the functional performance verification. Breadboard test reports. |
| TRL 5: Component and/or breadboard critical function verification in a relevant environment | Critical functions of the element are identified and the associated relevant environment is defined. Breadboards not full-scale are built for verifying the performance through testing in the relevant environment, subject to scaling effects. | Preliminary definition of performance requirements and of the relevant environment. Identification and analysis of the element critical functions. Preliminary design of the element, supported by appropriate models for the critical functions verification. Critical function test plan. Analysis of scaling effects. Breadboard definition for the critical function verification. Breadboard test reports. |
| TRL 6: Model demonstrating the critical functions of the element in a relevant environment | Critical functions of the element are verified, performance is demonstrated in the relevant environment and representative model(s) in form, fit and function. | Definition of performance requirements and of the relevant environment. Identification and analysis of the element critical functions. Design of the element, supported by appropriate models for the critical functions verification. Critical function test plan. Model definition for the critical function verifications. Model test reports. |
| TRL 7: Model demonstrating the element performance for the operational environment | Performance is demonstrated for the operational environment, on the ground or if necessary in space. A representative model, fully reflecting all aspects of the flight model design, is build and tested with adequate margins for demonstrating the performance in the operational environment. | Definition of performance requirements, including definition of the operational environment. Model definition and realisation. Model test plan. Model test results. |
| TRL 8: Actual system completed and accepted for flight (“flight qualified”) | Flight model is qualified and integrated in the final system ready for flight. | Flight model is built and integrated into the final system. Flight acceptance of the final system. |
| TRL 9: Actual system “flight proven” through successful mission operations | Technology is mature. The element is successfully in service for the assigned mission in the actual operational environment. | Commissioning in early operation phase. In-orbit operation report. |

- The Table (Table 5-1) taken from ISO 16290:2013, is reproduced with the permission of the International Organization for Standardization, ISO. This standard can be obtained from any ISO member and from the Web site of the ISO Central Secretariat at the following address: www.iso.org. Copyright remains with ISO. The standard can be obtained from ISO or its members, see www.iso.org.

### Typical technology readiness assessment process

For the main milestones in the technology roadmaps a typical TRA is realised following some basic principles, to be included in a specific Terms of Reference (ToR):

- TRA inputs:

  - Formal definition of the ToR for the assessment generally including:

    - identification of the element to be assessed

    - mission profile/mission requirements

    - target TRL

    - timing

    - technology data to be provided

    - how or what form the technology data will be provided

    - the detailed criteria for the TRA, by instantiating the general terms in clause 4.3 for the relevant target TRL and the technology domain under consideration

  - Identification of key supporting data including:

    - operating environment,

    - expected system applications

    - programmatic environment

  - Development and delivery of technology data to the TRA (often including preparatory meetings and/or studies by members of the technology community involved).

  - Existing element TRA (e.g. previous assessments or from lower level)

- TRA organisation:

  - Identification of TRA leader and participants  (including appropriate involvement of technologists and/or systems program participants).

  - Implementation of the TRA itself (often involving meetings of a formal review committee)

- TRA outputs:

  - Development of a TRA Report (including viability evaluation), endorsed by the independent assessor (in line with the ToR).

    - TRA Report details whether the targeted TRL is reached or identifies the lacking aspects and associated evidence necessary to reach the targeted TRL.

### TRA criteria

Generally speaking, a set of specific criteria are applied in conducting a TRA. The principal areas for TRA criteria are:

- Element definition status:

A description of the element, the associated critical function and technology being assessed including also other technologies that are involved and, if appropriate, the interactions between the various technologies

- In case of multiple technologies being assessed within a single element, the TRA assess each technology.

- Performance requirements status:

  - Identified applications

  - Functional performance, operational performance (for example)

- Verification/validation status:

  - Test environment (i.e. “laboratory”, “relevant”, or “operational” environments)

  - Test support used (e.g. “breadboard”, “representative models”, “qualification models” (for example)

### Viability of TRL progression

It is good practice to include as part of  the TRA an optional evaluation of viability for further progression of the element through the Technology Readiness Levels. This option, although primarily in the R/T&D programmes, is considered on the basis that the additional effort to perform this analysis is limited and provides considerable risk-related data to the potential future users of the element being evaluated. This evaluation is made on the basis of:

- Predicted time for maturity progression

- Cost

- Complexity

- Consideration of programmatic constraints

## TRL evaluation by level

### TRL 1: Basic principles observed and reported

- Element definition status:

Expression of basic principles for intended use

- Space Agencies and Industries are generally not involved in this scientific research activity.

- Performance requirements status:

  - Potential applications identified

  - Performance requirements are not yet specified

- Verification/validation status:

Not Applicable for Space Agencies and Industries

- TRA not performed on this level

### TRL 2 : Technology concept and/or application formulated

- Element definition Status:

Preliminary conceptual design of the element, providing understanding of how the basic principles are used.

- Performance requirements status:

  - Formulation of potential application

  - Performance requirements are general and broadly defined

- Verification/validation status:

No proof of concept yet

- TRA not performed on this level.

### TRL 3 : Analytical and experimental critical function and/or characteristic proof-of-concept

#### General evaluation aspects

- Element definition status:

Proof of the critical function of the element or characteristic by analysis possibly supported by laboratory experiments (such as technological samples supporting “proof-of-concept”) based on a conceptual design.

- Performance requirements status:

Preliminary functional performance requirements are established (targeting several missions/applications)

- Verification/validation status:

Analytical model, study and/or simulation and/or laboratory experiment

#### Documentation for TRA

Study report with verification results (laboratory experiments and/or analysis and/or simulation) and including:

- “Preliminary performance requirements (can target several missions) including definition of functional performance requirements”.

- Conceptual design of the element.

- Experimental data inputs, laboratory-based experiment definition and results.

- Element analytical models for the proof-of-concept.

### TRL 4 : Component and/or breadboard functional verification in laboratory environment

#### General evaluation aspects

- Element definition status:

The same as TRL 3 updated with breadboard test results

- Performance requirements status:

The same as TRL 3 updated with breadboard test results

- Verification/validation status:

A laboratory breadboard model of the element is integrated to establish that the “pieces” will work together to demonstrate the basic functional performance of the element. The verification is “low fidelity” compared to the eventual system and is limited to laboratory environment.

#### Documentation for TRA

Report with breadboard definition, test plan and test results demonstrating functional performance verification and including:

- “Preliminary performance requirements (can target several missions) including definition of functional performance requirements”. Requirements are updated from TRL3, as available.

- Conceptual design of the element. (updated from TRL3, as available)

- Functional performance test plan.

- Breadboard definition for the functional performance verification.

- Breadboard test reports.

### TRL 5 : Component and/or breadboard critical function verification in a relevant environment

#### General evaluation aspects

- Element definition status:

Critical functions of the element are identified and verified in a relevant environment on (not necessarily full-scale) breadboard(s). Preliminary functional and technical design of the element is achieved.

- Performance requirements status:

In particular for critical functions:

  - Preliminary definition of performance requirements

  - Definition of the relevant environment.

- Verification/validation status:

  - “Breadboards not full-scale are built for verifying the performance through testing in the relevant environment, subject to scaling effects”.

  - “At this stage the element feasibility can be considered as demonstrated, subject to scaling effects”.

#### Documentation for TRA

- Preliminary definition of performance requirements and of the relevant environment:

  - Preliminary Technical Requirements Specification (see ECSS-E-ST-10-06 Annex A)

- Identification and analysis of the element critical functions:

  - Analysis Report  (see ECSS-E-ST-10 Annex Q) for technology associated with critical functions

- Preliminary design of the element, supported by appropriate models for the critical functions verification:

  - Preliminary Design Definition File (see ECSS-E-ST-10 Annex G)

  - Preliminary Design Justification File (see ECSS-E-ST-10 Annex K), including:

    - Identification of computational design methods and tools

    - Analysis of scaling effects.

    - Breadboard definition for the critical function verification.

    - Critical function test plan (see Test Plan – template of which using the DRD as an example in ECSS-E-ST-10-03 Annex A).

    - Breadboard test reports (see Test Report  – template of which using the DRD as an example in ECSS-E-ST-10-02 Annex C).

### TRL 6: Model demonstrating the critical functions of the element in a relevant environment

#### General evaluation aspects

- Element definition status:

Critical functions of the element are verified and design of the element is achieved (supported by appropriate models for critical function verification).

- Performance requirements status:

Mission objectives, operational environment and the operational performance requirements are established and agreed upon by the stakeholders, taking into account the element integration in the final system.

- Verification/validation status:

The critical functions of the element are verified in the relevant environment (relevant for critical functions). For that purpose, a representative model(s) in terms of form, fit and function is used for demonstrating the critical functions and unambiguously demonstrating the element performance. It is confirmed that the test performance is in agreement with analytical predictions. The model types used, see ECSS-E-HB-10-02 clause 5.2.5.2, for this verification include one or more of the following (depending on model philosophy and critical functions):

  - engineering model,

  - engineering qualification model,

  - structural model,

  - structural thermal model,

  - thermal model.

#### Documentation for TRA

- Definition of performance requirements and of the relevant environment:

  - Technical Requirements Specification (see ECSS-E-ST-10-06 Annex A),

  - Interface Requirement Document (see ECSS-E-ST-10-24 Annex A)

- Identification and analysis of the element critical functions:

  - Analysis Report  (see ECSS-E-ST-10 Annex Q) for critical functions

- Design of the element, supported by appropriate models for the critical functions verification:

  - Design Definition File (see ECSS-E-ST-10 Annex G),

  - Design Justification File (see ECSS-E-ST-10 Annex K) including:

    - Model definition for the critical function verification

    - Identification of computational design methods and tools

    - Critical functions test plan.

      - Assembly, integration and test plan (see E-ST-10-03C Annex  A) for critical functions,

      - Test specification (see E-ST-10-03C Annex  B) for critical functions

    - Model test reports (see Test Report example in ECSS-E-ST-10-02 Annex C).

### TRL 7 : Model demonstrating the element performance for the operational environment

#### General evaluation aspects

- Element definition status:

Final definition of the element established in its operational environment.

- Performance requirements status:

The mission objectives, operational environment and the operational performance requirements are established and agreed upon by the stakeholders, taking into account the element integration in the relevant system.

- Verification/validation status:

The validation of the element performance is established through testing to demonstrate performance in the operational environment and validation of Qualification Margins. The element is successfully tested following qualification test requirements as described in E-ST-10-03. Those tests are conducted on a QM (or, depending on the models philosophy, on EQM or PFM, see ECSS-E-HB-10-02 clause 5.2.5.2).

#### Documentation for TRA

- Definition of performance requirements, including definition of the operational environment:

  - Technical Requirement Specification (see ECSS-E-ST-10-06 Annex A),

  - Interface Requirement Document (see ECSS-E-ST-10-24 Annex A)

- Model definition and realisation:

  - Design Definition File (see ECSS-E-ST-10 Annex G),

  - Design Justification File (see ECSS-E-ST-10 Annex K) including:

    - Assembly, integration and test plan (see ECSS-E-ST-10-03 Annex  A) for the element,

    - Test specification (see ECSS-E-ST-10-03 Annex  B),

    - Test procedure (see ECSS-E-ST-10-03 Annex C) for the element

    - Test Report (see ECSS-E-ST-10-02 Annex C),

Qualification Review report of the Review Team (see ECSS-M-ST-10-01 Annex C) and/or the Review Authority (see ECSS-M-ST-10-01 Annex D) assessing successful qualification.

### TRL 8 : Actual system completed and accepted for flight (“flight qualified”)

#### General evaluation aspects

By definition, all technologies being applied in actual systems go through TRL 8.

- Element definition status:

The same as TRL 7.

- Performance requirements status:

The same as TRL 7.

- Verification/validation status:

The qualified element (FM or PFM) is integrated into the final system which has been accepted for flight (successful Acceptance Review).

#### Documentation for TRA

“Flight acceptance of the final system”:

- AR report of the Review Team (see ECSS-M-ST-10-01 Annex C) and/or the Review Authority (see ECSS-M-ST-10-01 Annex D), assessing successful flight acceptance with documentation for the element as required by the project (see ECSS-E-ST-10 Annex A, and ECSS-Q-ST-20 Annex I).

### TRL 9: Actual system “flight proven” through successful mission operations

#### General evaluation aspects

- Element definition status:

The same as TRL 8.

- Performance requirements status:

The same as TRL 8 with the inclusion of mission operations duration.

- Verification/validation status:

The element is successfully in service for the assigned mission in the intended operational environment. A system, integrating the element, has passed through a successful CRR.

- In the case of anomaly post CRR, and a redesign is necessary,  a TRL is only assigned after a TRA is performed (see also clause 6.2 “Re-assessment of TRL for re-use of element with existing TRA”).

#### Documentation for TRA

“Commissioning in early operation phase. In-orbit operation report”:

- CRR report of the Review Team (see ECSS-M-ST-10-01 Annex C) and the Review Authority (see ECSS-M-ST-10-01 Annex D), assessing successful commissioning results, with documentation for the element as required by the project (see ECSS-E-ST-10 Annex A, and ECSS-Q-ST-20 Annex I).

- The TRA can consider, as additional information, the duration of operations achieved at the time of assessment.

## Guidelines for other uses of TRLs in R&T&D activities

TRLs are also used in planning and managing the implementation of R&T&D  programs. TRLs can be used in:

- establishing and applying the criteria for acceptance of a technology into an R&T&D  program:  for example some programs can be dedicated to activities from TRL 2 to TRL 3, some others from TRL 4 to TRL 6;

- establishing objectives for individual technology proposals to a R&T&D  program: for example the proposal forms include fields such as “Estimated current TRL” and “Target TRL” (see example Figure 5-4);

- completing an R&T&D individual technology activity with a TRA (see clause 5.2 to 5.3).

Figure 5-4: Example of ESA Technology Activity TEMPLATE

The use of TRL in R&T&D  programs is highly beneficial to clarify technical policy and objectives, to assess the results and to ease the transition from research activities to projects.

In addition TRLs are also used in framing and articulating technology roadmaps. The application of the scale in technology roadmaps allows to project the evolution of a technology maturity against programmatic goals and future missions needs and synergies (see example Figure 5-5.)

Figure 5-5: Illustration of a Technology Roadmap

# Implementation in projects

## General

In any project where new technologies are intended to be used, or existing technologies are used in new ways, it is important to understand the risks associated with technology maturity. Technology Readiness Levels provide a structure for the evaluation of such risks by setting out criteria to be met to reach each level.

In order to apply the TRL method to the benefit of a project it is essential that it becomes embedded as a standard management tool within daily project management. TRLs add value when projects use them routinely.

In this way, TRA outcomes are able to:

- Support go/no-go decisions, during Phase 0, A and B, about the inclusion of new technologies in a system

- Mitigate risk to projects by identifying exactly what development has been performed to date

- Assist project planning by identifying the remaining tasks necessary to increase technical maturity

- Provide a consistent ranking system to reliably compare the maturity of different technologies

- Projects exist within an organisation and the following clauses only consider the project aspects. The use of TRL and associated TRA (along with TRSL) can also provide organisational insight in to the technology-related risk profile of a number of projects and therefore contribute to the decision-making process at the key project go-no-go decision points.

It is important to note that for the project use of TRL for technologies providing critical functions the following topics are not addressed, but are known to be necessary project considerations such as:

- Architectural sensitivity

- AI&T sensitivity

- Immature technologies not providing critical functions

- Complexity

- TRL is one factor for the evaluation of risks due to technologies. Amongst the other factors, complexity is also an important one and Figure 6-6 gives a qualitative evaluation of risks versus TRL and complexity.

Figure 6-6: Risk versus TRL and complexity

## Critical functions and technologies in projects

### Overview

ECSS-E-AS-ST-11 provides the definitions such as Critical function of an element, Critical part of an element, Element function. In particular, the Critical function of an element, is defined as a “mandatory function which requires specific technology verification”, providing for a differentiation between a technology and a function. On this basis, the project conducts an analysis to determine the critical functions performing the mission requirements, and in turn the related technologies are selected for a TRA.

In order to identify which elements of a system are “critical” for the mission the project uses the following criteria:

- their function is “mandatory” for the mission accomplishment  - i.e. for cost, schedule or performance, and,

- their technology needs “specific technology verification” - “when either the element or components of the element are new and cannot be assessed by relying on previous realizations, or when the element is used in a new domain, such as new environmental conditions or a new specific use not previously demonstrated”.

It is through this approach that the TRA provides a project tool for the tracking of potential impacts of immature technology on cost estimation (Ref ECSS-M-ST-60), project schedule (Ref ECSS-M-ST-60) and risk identification and management (Ref ECSS-M-ST-80) at the early phases of a project, i.e. Phase 0 to Phase B. At Phase B the TRA provides the necessary rationale for transferring specific identified technologies / elements on to the Critical Item List, for which ECSS-Q-ST-10-04 applies.

In summary, the key questions for identifying the technologies candidates for assessment for a project/programme, are:

            - is the function (associated with the technology) mandatory to meet the mission requirements?

            - is further “specific technology verification”  (performing the critical function) necessary?

If the answer to both questions is yes, the technology maturity is assessed through a TRA.

### Technology Readiness Status List and transference to Critical Item List

The critical functions are established within the TRSL in the preliminary phases (Phase 0, A and B), then the identified elements are transferred to the Critical Item List (as defined in ECSS-Q-ST-10-04).

In accordance with ECSS-E-ST-10, the system engineering organization evaluates the identified technologies in terms of TRL, and identifies and collects the critical functions in the TRSL (as per ECSS-E-ST-10 Annex E). Such a list provides, for each critical function:

            - the element and/or the technology providing the critical function,

            - the element TRL,

            - the reference to the TRA report and its date,

            - a concise rationale of the TRA,

            - the planned way forward in terms of TRL evolution (specifying ongoing and future activities and the planned date at which the target TRL is expected), and

            - the indication whether or not the element is a candidate for inclusion in the Critical Item List.

At the end of the phase B (PDR) the elements whose functions are critical from the technology point of view, are candidates for being transferred in to the Critical Item List (see ECSS-Q-ST-10-04). The risk due to technology maturity is managed as a critical item of the project and generally a TRA is no longer performed by the project.

## Technology Readiness Assessment in projects

TRAs are performed at many stages of a technology or product development, for instance at the time of R&T&D  reviews. TRAs are certainly also performed in early feasibility studies.

It is expected that formal TRAs are performed in both institutional and commercial projects.

A TRA is applied at the following project stages:

- In institutional projects during Phase 0, A and B,

- In commercial projects prior to commencement (see clause 5.4).

The TRAs are managed in the TRSL which is reviewed at the end of Phase 0 (MDR), Phase A (PRR) and Phase B (SRR and PDR). The TRA is carried out by one or more independent technical experts (see clause 4.2.3), depending on the complexity of the item. ECSS-E-ST-10 clause 5.6.7 refers to the TRA as a deliverable, as defined in ECSS-E-ST-10 Annex E, 2.1<5>.

As a result of this activity technologies of interest to a project in the very early stages are refined to support the project needs for the product development, as presented in Figure 6-2.

Figure 6-7: Evolution of technology options during preliminary project phases

TRA are typically run under the accountability of the project, and the execution of TRAs is typically performed under the responsibility of the (project) system engineering supported by the PA organization. ECSS-Q-ST-10 clause 5.2.1 defines the PA manager role in the Technology Readiness Status List (TRSL) and the Technology Plan (TP).

The leader of the TRA is responsible for assigning tasks / roles to personnel and to secure their availability and participation. The different assessment steps are planned by the TRA leader in cooperation with the project management. To reduce any necessary extra effort for the project, the Assessment is performed in line with the project schedule, i.e. utilise nominal project milestones and is provided through the delivery of TRSL (as part of the Technology Plan) to customer, as defined in ECSS-E-ST-10 Annex A, Table A-1.

The leader of the TRA is responsible for reporting the TRA outcomes, and also for alerting the project management of TRL related risks in need of mitigation. Any corrective measures established are then injected into the project under the responsibility of the project management.

The PA manager checks, for each critical item and for each project, that the TRA has been correctly carried out in accordance with the organization procedures. The PA manager also checks that the TRSL has been correctly produced in accordance with ECSS-Q-ST-10 clause 5.2.1.

Some organizations have an overall TRL process owner, in charge of generating/updating TRL procedure documentation and tools and liaise with the TRL managers.

## Typical levels linked to project phases and milestones

When considering the relationship between projects phases and the technology maturity of the critical functions, it is considered normal practice to achieve TRL 6 prior to entering the detailed definition phase (Phase C). It is highlighted that there is a specific project decision to proceed from Phase B to C  (i.e. at system-level PDR) to accept greater risk through the adoption of technologies below TRL 6 at this milestone.

- In cooperative space programmes within U.S. national institutions, for the US projects  to enter the detailed definition phase (phase C), flight hardware providing a critical function meets or exceeds TRL 6.

For ground segment project developments, which differ in approach to that given in Clause 6.3 above, the specificities of managing readiness levels are given in Annex A.

In the early project phases (0, A, B), the development of the technology plan and of the TRSL, is essential to properly support the assessment of the mission achievable performance, the overall project schedule and the related costs and risk. An outline of benefits of engaging the TRA at these early stages in provided in Table 6-1.

Table 6-3: Benefits of use of TRA

| Project Phase | Benefits of use of TRA |
| --- | --- |
| Phase 0 (MDR) | - Establish the TRSL – listing candidate technologies for the same critical functions - Re-orient the system concept for optimising technology readiness and technology selection decision schedule - TRSL also provides a connection from the project to the technology developers (R/T&D programmes). |
| Phase A (PRR) | - Contribution to the technology plan (TP) - Consolidate TRSL within the TP. - Refine list of candidate technologies for the same critical function |
| Phase B (up to SRR) | - Consolidate TRSL within the TP. - Preliminary identification of items for transfer to CIL |
| Phase B (from SRR to PDR) | - Inputs from TRSL to the Critical Item List (CIL) - TRSL provides risk data supporting the decision to move to detailed design phase (C) - Final selection of (suppliers for) candidate technologies for the critical functions |

Passing through preliminary phases, the number of technology options for a critical function of the project is  decreasing until the end of phase B were generally only one option is kept with a TRL at least 6.

It is worth noting that in the Technology Plan the project defines a model philosophy for the technology development (and TRL progression) followed over the project phases. The model philosophy selected for the technology critical elements drives their TRL upgrades during the early project phases.

Once the project is within the detailed design phase (i.e. Phase C), the evolution of the critical items related to technology maturity (now included in the Critical Item List) follows the project development process as specified in ECSS standards.

In order for an organization to apply TRL to the benefit of projects, it is important that TRAs become embedded as a standard project management practice. TRLs add value when projects use them routinely. Figure 6-8 gives a generalized example of when formal TRAs are typically performed during institutional projects. Institutional projects generally develop critical functions (provided by technologies) and models from lower TRL through to TRL6 during the early phases of the project (prior to Phase C).

Figure 6-8: Project phases and generalised institutional expectation of TRA outcome

- For Commercial or recurring product development (product development without Phase A/B) – refer to ECSS-E-ST-60-13 and ECSS-Q-ST-20-10.

Figure 6-9 illustrates the link between project phases and expectation of TRA outcomes for commercial projects where the TRL of a technology is below TRL7. In this case the phases are shown in grey font, to illustrate that for commercial projects, TRL is more linked to key project milestones. This is because the TRL of technologies selected for use on commercial projects are targeted at high maturity (i.e. TRL7, 8 or 9) whenever possible. Commercial projects therefore tend not to include phases 0, A and B prior to project start. Hence commercial customers expect all or most of the products used to be already TRL 7, 8 & 9 prior to their ITT release. This is not always possible. Commercial customers often expect more functionality and capacity from one project to the next, whilst not directly funding any pre-development activities. It is rare for a technology below TRL 5 to be allowed into a commercial project, as the schedule for the overall mission is put at too much risk. Accordingly prime contractors request TRL information from their suppliers in order to support their bid/no bid assessment. If the prime enters into final negotiation with the customer, a TRA is normally performed prior to project start. This is to verify TRL claims made by selected suppliers are valid. It also enables the credibility of development plans to be examined in the case where it is essential to develop technology during the project from TRL5 or 6 to 7 prior to spacecraft flight. Normally the project performs a system QR (S-QR) after the system CDR. The outcome of which is to ensure all technologies employed are at TRL7 or higher.

Figure 6-9: Project phases and generalised commercial expectation of TRA outcome

The main difference between the two types of projects being that commercial projects generally use already flight qualified, or high TRL, models from the outset whenever possible (i.e. models that have achieved TRL6 or above). In both cases conducting TRAs for the project at the time of proposal vetting (i.e. for phase C of an institutional programme) is key to risk mitigation.

# Links with model philosophy and techno-demonstration, and, reassessment

## Links with model types and techno-demonstration

### Link between TRL and model types

For lower TRL (i.e. up to TRL5), verification / validation of critical function is supported by breadboard or components. For TRL 6 to TRL 9 the verification / validation is supported by models (e.g. EM, QM, PFM, FM).

Table 7-4provides model types typically associated to TRLs.

Table 7-4: Models types associated to TRLs

| TRL # | TRL definition | Associated model | Performance requirements | Test environment | Comments and practical use |
| --- | --- | --- | --- | --- | --- |
| 1 | Basic principles observed and reported | Not applicable | Normally not defined at this TRL | Not applicable | Survey of emerging technology to establish candidate technologies. |
| 2 | Technology concept and/or application formulated | Synoptic, block diagram | Generally and broadly defined | Not applicable | Potential maturity level for starting technology R&T&D activity |
| 3 | Analytical and experimental critical function and/or characteristic proof-of-concept | Proof of concept model, such as mathematical models, simulations, supported by experimental data / characteristics | Generally and broadly defined (and could be formalised in a preliminary definition file) Note: At this level of maturity, some Ph0 requirements can be taken in to consideration | Laboratory | Typical starting maturity level for technology R&T&D activity. Also minimum maturity level for a project Ph0 TRSL. Characterising technology potential before breadboard integration. |
| 4 | Component and/or breadboard functional verification in laboratory environment | Breadboard of the element (integration of functionally representative breadboard). | Generally and broadly defined | Laboratory | Evaluate pure performances of the technology applied to the element. |
| 5 | Component and/or breadboard critical function verification in a relevant environment | Breadboard, also referred to as sub-scaled EM for the critical functions | Preliminarily defined, possibly incomplete due to model scaling effects | Relevant environment. Test results can be subject to model scaling effects | In a few cases, where scaling effects were assessed as negligible, the level of risk presented by technology being at TRL 5 has been considered equivalent to that of TRL 6 for a project to enter the detailed definition (phase C). |
| 6 | Model demonstrating the critical functions of the element in a relevant environment | Full scale EM(s), representative in form fit and function for critical functions | Established and agreed upon between the customer and supplier | Relevant environment | Normal threshold for enabling the start of detailed definition and production phase (C / D) |
| 7 | Model demonstrating the element performance for the operational environment | QM | Established and agreed upon between the customer and supplier | Operational (capable of being tested on-ground with qualification margins) | QM validated Note: project can consider to allow use of EQM and/or PFM instead of QM |
| 8 | Actual system completed and accepted for flight (“flight qualified”) | FM acceptance tested, integrated in the final system | Established and agreed upon between the customer and supplier | Operational (as conducted for an Acceptance Review) | A system integrating the element has passed through a successful AR. FM model integrated in a system whose acceptance has been achieved through test and demonstration. Threshold for Operations phase (E). |
| 9 | Actual system “flight proven” through successful mission operations | FM, flight proven | Established and agreed upon between the customer and supplier | Actual operational | Corresponds to technology reaching a “mature” status. |
| * Phases referred to herein are stated from a project perspective (and not the Phases relative to the technology development). |  |  |  |  |  |

Table 7-5 provides the range of applicability for the work achievement (in support of the TRA) that is obtained from the various models developed during a project (as defined in ECSS-E-HB-10-02).

Table 7-5: Use of commonly-used models for TRL progression

| Model | Potential use with respect to TRL scale |
| --- | --- |
| Structural Model | Used to progress to TRL 6 |
| Thermal Model | Used to progress to TRL 6 |
| StructuralThermal Model | Used to progress to TRL 6 |
| Engineering Model (scaled) | Used to progress from TRL 4 to TRL 5 |
| Engineering Model (full scale) | Used to achieve TRL 6 |
| Engineering Qualification Model | Used to progress to or achieve TRL 7 |
| Qualification Model | Used to achieve TRL 7 |
| Human related models | Used to achieve TRL 7 |
| Life Test Model | Used to progress to TRL 7 in conjunction with model(s) used for qualification |
| Proto-Flight Model | Used to achieve TRL 7, TRL 8 and TRL 9. |
| Flight Model | Flight model achieves TRL 8 and 9. |
| Software and ground segment specific models | Refer to Annex A for specific details of software and ground segment models used in TRL progression |

Some other model types described in ECSS-E-HB-10-02 are also used to TRL progression for dedicated purpose, examples of which being; function-oriented models, electrical or functional models.

### Link between TRL and Technology Demonstrators

#### Introduction

To realise a desired maturity of the Technology Readiness Level there are various classes of demonstrator used to provide the necessary data or evidence in support of the TRA. The following demonstrator types are developed:

- Ground Demonstrators

- Space Demonstrators for Technology

- Mission precursor Demonstrators

- Space Environment demonstrators is not considered in this handbook as its objective is not the maturity demonstration of a technology but to measure the space environment linked to the mission environment constraints.

#### Ground demonstrators for technologies

The objective of this type of demonstrator is to ease the transition from the R&T activities to the R&T&D for the project (i.e. to take the technology through the “valley of death”), by undertaking ground-based data collection supporting the TRA.

The elements under consideration for this type of activity are equipment, instruments and or components. This activity is undertaken to reassure the final customer in terms of reduced risk, and to reduce future potential costs for the project. As such this activity is undertaken during the R&T&D activities up to space qualification (generic, i.e. not dedicated to a specific mission, or project). Sometimes specific missions, or projects take this activity within the scope of their project development plan (but not necessarily directly funded by the project). As this activity is associated with product development, the beneficiary is the product developers. As such in industrial competition, this activity helps companies to develop a product to be well placed on a dedicated market.

The TRL transition achieved is generally from TRL 4 or 5 to TRL 6 or 7. Examples include data handling receivers for micro or nanosats, batteries lifetime testing.

#### Space demonstrators for technologies

The objective of this type of demonstrator is to demonstrate the adequacy of the technology performance in the relevant space environment (for example: radiation, microgravity, life duration).

In any case the space demonstrators for technologies are managed as regular programmes with mission definition and development of a ground segment. The technologies being demonstrated on-orbit are qualified as far as possible on ground.

The elements under consideration for this type of activity are equipment, instruments and / or components. The technology demonstration is performed as part of a project main mission, or be hosted or piggy-backed technologies not part of the project main mission.

Space demonstration is undertaken in a way to provide heritage to ensure the achievement of TRL 8 and TRL 9

- to reassure the final customer in terms of reduced risk, and/or

- to reduce future potential costs for the project (e.g. Proba, Stentor ), and/or

- in cases where the validation of the critical function in the space environment is the only viable solution (e.g. operation of heatpipe fluidic loop in microgravity).

The activity purpose ranges from mission-dedicated to technologies demonstration.

The TRL transition achieved by space demonstrator development projects is generally from TRL 4 (or TRL 5) to TRL 8. In some cases where the technology forms part of the main mission, it follows that TRL 9 will be achieved

In the case of technology demonstration satellites the mission objective is currently one of education and  technology demonstration only. This provides valuable information to assist in the transition between TRL 4 and 5/6 (the “valley of death”). In all likelihood any critical functions, technology, or models developed specifically for use on such missions will not be able to demonstrate having reached TRL 6 or 7 in accordance with the ECSS requirements prior embarking on a flight. Similarly the project is unlikely to have the relevant TRA evidence needed for subsequent use on either institutional or commercial main missions. The implication of this is that the technology is not used as flight qualified (for either an institutional or commercial main mission) until sufficient additional verification has taken place. The model needs to achieve TRL 6 commensurate with the mission environment prior to consideration; or a careful risk mitigation plan embarked upon by the project.

#### Mission precursor demonstrator

The objective of this type of demonstrator is to prepare the technologies for a future operational mission.

The elements under consideration for this type of activity are instruments or system concepts. These generally have a dedicated project (commonly for science), or be hosted or piggy-backed by another project (e.g. Q/V frequency band hosted experimental payload on Alphasat)

This activity is to refine technology or mission / system definition needs for future applications or use.

The TRL transition achieved by this demonstration is generally from TRL 4 or 5 to TRL 6 through to 9. Examples include EDRS Optical link, LISA Pathfinder, and Galileo In-Orbit Validation satellites.

## Re-assessment of TRL for re-use of element with existing TRA

### Technical guidelines

When re-using an item the qualification or the design of the item is assessed for the impact to TRL. ECSS-E-ST-10-02C (Clause. 5.2.4.2) provides the conditions under which the qualification of a heritage item is still valid in a new project.

The following table provides the assessment guidelines for the re-use cases for each of the heritage categories, A, B, C and D.

Table 7-6: Links between TRL and Heritage Category

| Heritage Category | A | B | C | D |
| --- | --- | --- | --- | --- |
| Description | Off the shelf product without modifications and | Off the shelf product without modifications. However: | Off the shelf product with design modifications. | Newly designed and developed product. |
|  | - subjected to a qualification test programme at least as severe as that imposed by the actual project specifications including environment and | - It has been subjected to a qualification test programme less severe or different to that imposed by the actual project specifications (including environment). | Modification includes changes to design, parts, materials, tools, processes, procedures, supplier, or manufacturer |  |
|  | - produced by the same manufacturer or supplier and using the same tools and manufacturing processes and procedures |  |  |  |
| Qualification programme | None | Delta qualification programme, decided on a case by case basis. | Delta or full qualification programme (including testing), decided on a case by case basis depending on the impact of the modification. | Full qualification programme. |
| TRL considerations for re-use cases | The existing TRA is still valid | The product is re-assigned as TRL6 for the re-use project. | The original TRA is no longer valid, and therefore a TRL cannot be assigned until a new TRA is performed. The outcome of the TRA can range between TRL 4 and 6 on a case by case basis. If the design changes impact the technology providing the critical function, then TRA gives TRL<6. | A TRA is needed |

### Technology re-use in a new environment

When re-using a mature technology within a new operational environment, there is an assessment of the impact to TRL. The potential outcomes of the TRA is given in Table 7-7.

Table 7-7: Technology maturity transfer for re-use

| Initial TRL | Characteristics of the item w.r.t. the new environment | TRA guideline outcome |
| --- | --- | --- |
| 7 - 9 | Same or less severe operational environment | TRA is still valid - TRL declared is same as initial TRL |
|  | Same or less severe relevant environment, and operational environment is changed outside of that given in the TRA | TRL 5 or TRL 6 |
|  | Relevant environment and operational environment is changed outside of that given in the TRA | TRL 4 (as a maximum) |

For clarification the following definitions are applied from ECSS-E-AS-11 to Table 7-7:

operational environment

“set of natural and induced conditions that constrain the element from its design definition to its operation”

relevant environment

“minimum subset of the operational environment (2.11) that is required to demonstrate critical functions of the element performance in its operational environment”

- TRL considerations for specific disciplines

  - TRL considerations for Software

    - SW-specific guidelines for TRA

      - ISO TRL scale and software developments

ISO TRL definition does not address the use of TRLs for software and there is no international or even European uniform approach for using TRLs for software developments. For convenience and for avoiding the introduction of a specific scale for software, it is proposed to use the same ISO scale for software developments by providing a clear definition of the expected development state at each TRL.

For that purpose, software specific definitions are provided in clause 3.2, and basic principles underlying software developments are exposed in clause A.1.1.2.

      - Basic principles

Software TRL (SW TRL) is applied to assess the maturity of technologies implemented in software which may be part of the flight segment (flight software), ground segment (ground software) or engineering tools (software tools).

Due to their very different development and application characteristics, the type(s) of software needs to be identified for the purpose of TRL definition:

            - Software tool.

            - Software Element. SW that necessarily interacts with other software and possibly also with HW. Two categories exist as follows:

              - Building block: SW conceived to be reused in a range of missions, either flight or ground software. This software is executed as part of a larger software application.

              - Specific Software: SW that is targeting a specific application and that is not conceived to be reused in another domain of application (e.g. equipment embedded software).

            - Generic Software Product

              - Tailored Generic Software Product

              - Customized Generic Software Product

This clause clarifies the notion of SW TRL for the SW types 1, 2.a and 3.a, for the SW types 2.b and 3.b, the TRL ISO classification is applicable as is (the TRL assessment is done at product/equipment level and applies consistently for HW & SW).

As for HW TRL, the SW TRL are not meant to be applied to the management of a software development project, for which typically the software engineering standard (e.g. ECSS-E-ST-40 and ECSS-Q-ST-80) is applied. The SW TRL is then simply a tool for the evaluation of the maturity of a given software technology (building blocks, tools) within the context of its intended application.

The underlying principles are summarized for the following TRL :

- TRL 1 to 4 covers the beginning of the development as the level of implemented functionality increases.

- TRL 5 and 6 cover the transformation of the prototype into a product with frozen requirements. A pre-qualification data package is produced by making use of the ECSS-E-ST-40 and ECSS-Q-ST-80 standards, giving confidence that the product performs as expected in the final environment.

At least TRL 6 is established for a Generic Software Product and for a Building Block during Phase C of the instantiating project.

- TRL 7 corresponds to the SW qualification for the foreseen application verifying the SW performance in its intended environment.

  - For a SW tool, this corresponds to full validation on a representative pilot case.

  - For a building block, it is fully integrated in the qualified software as part of the foreseen application.

TRL 7 is established for a Tailored Generic Software Product or a Building Block integrated in a Complete Software which has been successfully qualified (successful Sw-QR)

- TRL 8 corresponds to the final product acceptance for operation.

  - For a SW tool, it corresponds to the readiness for the full deployment in operation.

  - For a building block, this corresponds to the end of the system qualification.

TRL 8 is established for a Tailored Generic Software Product or a Building Block which has been integrated and completed, qualified in the Ground Segment/System (successful Ground Segment QR (GSQR) / Operations QR (OQR) / System QR). It is ready to support LEOP and Commissioning Phases

- TRL 9 corresponds to successful operations and performance achievement in the foreseen application. Ground Segment is periodically evaluated (e.g. on a yearly basis) during IOOR (In Orbit Operations Review): TRL 9 for a Tailored Generic Software Product or a Building Block is established during one of these reviews (may be several years after FQR)

- The terms “alpha” and “beta” versions are used by analogy with names used outside of the space domain, but do not intend to carry any of these non-space meanings.

    - Use of TRL with Software

The following table provides an overview of the generalized alignment of the software development cycle and that of the associated Technology Readiness Levels. Similar to the development of hardware, TRL is not to be seen as a development tool, but as a method for risk assessment associated with critical functionality provided by an identified software element through its various stages of development.

- For TRL 5 to 9, requirements of ECSS‐E‐ST‐40C and ECSS‐Q‐ST‐80C are fully applied.

                - : Use of TRL with Software development

| TRL | Engineering terms relevant to SW | Additional explanation to cover software | Description | Requirements | Verification | Viability |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | FIRST FORMULATION | Scientific knowledge | Preliminary algorithmic stage. Publication of research results. | Expression of a problem and of a concept of solution. | Clear algorithmic formulation. | Feasibility to be implemented in software with available computing facilities demonstrated. |
| 2 | ALGORITHM | Individual algorithms or functions are prototyped | Algorithm implementation documented. Results documented. | Practical application identified. A concrete specification of a part of the problem. | Single algorithms are prototyped and tested with synthetic data resulting in their characterization and feasibility demonstration. Execution target may not be representative of the final target. | Feasibility to build important functions in a system architecture demonstrated. |
| 3 | PROTOTYPE | Prototype of the main functionalities of the integrated system | Specification & architectural design of important functions is documented. | Preliminary solution to specific needs. Main use cases implemented. | Some functionalities are implemented and tested to allow the demonstration of global operation and performance. Execution target is representative of the final target. Preliminary V&V activities executed in a simulated laboratory environment. | Feasibility to build an operational system taking into account preliminary performance and usability aspects demonstrated. |
| 4 | ALPHA version | Initial design of the complete product is achieved and most of the functionalities are implemented. | Documentation as for TRL 3 plus: - User Manual - Design File | Clear identification of the domain of applicability. Requirements for solutions to a range of problems specified. All use cases implemented. | Verification & Validation process is partially completed, or completed for only a subset of the functionality or problem domain. Execution target is representative of the final target, including hardware aspects. V&V activities executed in a representative simulated laboratory environment. | Feasibility to complete missing functionality and reach a product level quality demonstrated. |
| 5 | BETA version | Implementation of the complete software functionality, and integration of critical functionalities demonstrated | Full documentation according to the applicable SW engineering & quality standards, including test reports and application examples. | Formal definition of the domain of (re)use and associated variability features of the implementation. All use cases and error handling specified. | Validated against the requirements of the complete domain of applicability including robustness. Quality assurance aspects taken into account. V&V activities executed in an End-to-end representative laboratory environment including real target (hardware execution target). | Feasibility to fix reported problems within available resources evaluated. User support organization in place. |
| 6 | Product RELEASE | Ready for use in an operational/ production context, including user support, as a building block or a tool. | Documentation according to the applicable SW engineering and Quality standards for a software product. | Building block & Generic Software Product: Process for reuse, for instantiation in the domain of the implementation and its test environment. Documentation is compliant with critically level of the target application. Tools: All use cases and error handling implemented. User friendliness validated. | Building block & Generic Software Product: Validated against the requirements of the complete domain, validation environment also reusable, reuse file (SRF) available. Tools: Verification and Validation process is complete for the intended scope, including robustness. Configuration control and Quality assurance processes fully deployed. V&V activities executed in an End-to-end fully representative laboratory environment including real target. | Feasibility to be applied in an operational project demonstrated. Availability of a data package suitable to support future qualification. |
| 7 | Early adopter version | Building block & Tailored Generic Software Product: qualified for a particular purpose Tool: ready for market deployment | In addition to TRL 6 Documentation, updates to documentation and qualification files SPR database Lessons learnt report Documentation & tooling, if any, related to the tailoring of the Generic Software Product | Requirements traced to mission requirements. Validity of solution confirmed within intended application. Requirements specification validated by the users. | Building block & Tailored Generic Software Product: Integrated in the spacecraft/ground segment following the applicable software standards Tools: The tool has been successfully validated in a pilot case, representative of the intended project application | Engineering support and maintenance organization in place, including helpdesk |
| 8 | General product | System qualified and ready to be applied in the execution of a real space mission | Full documentation including specifications, design definition, design justification, verification & validation (qualification file), users and installation manuals and software problem reports and non- compliances. Including also qualification files, SPR database. Lessons learnt report. | Requirements traced to mission requirements. Validity of solution confirmed within intended application. Requirements specification validated by the users. | Building block & Tailored Generic Software Product: Integrated in the spacecraft/ground segment and completed successfully system qualification campaign. Tool: the tool has been successfully applied in an operational project but has not yet been validated against the in- flight experience | Engineering support and maintenance organization in place, including helpdesk. Capability for in-orbit data exploitation and post flight analysis. |
| 9 | Live product | Has been applied in the execution of a real space mission | In addition to TRL 8 Updates to documentation and qualification file SPR database updated. Lessons learnt report Track record of application in space projects | Building block & Generic Software Product: Maintained Tools: Full process implemented, Maintenance, updates, etc. | Building block & Tailored Generic Software Product is operational for the mission and performance is in line with operation procedures. This state is reached after IOOR. Tool: the tool has been successfully validated in one or several space missions, including exploitation of in-orbit data. All anomalies encountered have been analysed and resolved. | Sustaining engineering, including maintenance and upgrades in place |

    - Relationship between TRL and Criticality Categories

Critical SW is defined to be at Category A, B or C. The Software criticality category, as defined for dependability and safety (ref. ECSS-Q-ST-30C and ECSS-Q-ST-40C) is according to the consequences of failures and is not linked with the maturity of the software described by the TRL. As such, the SW criticality level of a function or product is independent from the TRL and is based on System and SW RAMS analysis. However, from the perspective of reusing a building block in a Software Product, it is clear that there is a direct relationship with the needed maturity of the building block and its level of criticality.

The 2 main use cases to consider for TRL and Critical SW apply to "Developing a Building Block" and "Using a Building Block".

Developing a Building Block:

The TRL does not apply to a Specific Software Product (see clause A.1.1.2, SW types 2.b & 3.b), but only to a building block such as an RTOS, that are later used in product Software Product. As such, SW criticality and TRL are linked at the level of pre-qualification, e.g. the Building Block is pre-Qualified for category A, B or C at TRL 6. At TRL 6 and higher, ECSS is by construction fully applied.

In addition, it is important to note that the criticality is given by a system dependability analysis that does not apply specifically to the Building Block. However, the Building Block will be expected to be used into a system where it will receive criticality A, B or C. Therefore, the Building Block is pre-qualified to the identified level of criticality. Since the criticality determines the level of engineering and PA, this is adjusted in TRL5 or 6, by applying appropriately the ECSS standards.

Using a Building Block:

Given that a Building Block of TRL6 pre-qualified for Cat X is available to be used in a Software Product of category Y, then:

- if X is the same or of a higher critical category than Y, the Building Block can be used as is

- on the contrary, if X has a lower criticality category than Y, the Building Block needs to be re-engineered to raise its criticality category (see ECSS-Q-ST-80C, clause 6.2.7.8). The gap in the functionality and the delta qualification needed is documented in the SW Reuse File (SRF).

In the case of the integration of a Building Block of TRL 6 or above (and a declared level of criticality) in a Software product of a higher level of criticality, the TRL of the Building Block is downgraded to at least TRL 6 depending on the level of Building Block re-engineering.

For a Building Block developed iteratively, with the aim of progressively increasing its functionality and maturity, the tailoring of the SW Engineering and SW Quality standards (ECSS‐E‐ST‐40C and ECSS‐Q‐ST‐80C) in each iteration depends on both the criticality of the function in its final environment and on its TRL. As such, an early beta version with TRL 5, for example, is developed with Category D tailoring. This tailoring is then be progressively aligned with the criticality level of the software in its final environments, as the TRL is increased.

I is expected that for TRL 1, 2, 3 and 4 the ECSS tailoring, if any, will be below Category D.

- ECSS-Q-ST-80C covers the Analysis of Software Maturity and its reporting for Critical SW (see clause 7.1.8).

- TRL considerations for specific disciplines

  - TRL considerations for EEE Components

    - EEE components

This covers EEE components in the meaning of ECSS-Q-ST-60.  For practical purposes it is sufficient to distinguish between Active (semiconductor technologies), Passive and Hybrid Microcircuits* where necessary.

This does not apply to Commercial EEE Components in the meaning of ECSS-Q-ST-60-13 due to the lack of assured lot homogeneity and typically insufficient product traceability as well as the inherent limitations of the up-screening concept.

With few exceptions EEE Components are recurrent products intended for use in a wide variety of system applications , specified and designed with sufficient margins to suit a wide variety of mission profiles.  Demonstrated robustness against stresses induced by the application and operating environment are key criteria for TRL determination.  Full maturity (space qualification) is typically achieved with TRL 7 / 8 due to the nearly complete test coverage for operational conditions in the relevant environment achievable on ground and with coverage of synergy effects by use of margin policies.

- Although Hybrid Microcircuits are electric circuits assembled from individual components in a common dedicated protective package the requirements for components apply.

| TRL 1 | Milestones: possible constituent materials, processes, manufacturing tools, design rules and tools exist and are identified documented. A principal adequacy for the intended application has a high probability. Work achievement: basic function(s) defined and constituent prerequisites initially documented. |
| --- | --- |
| TRL 2 | Milestones: Basic test structures (initial prototypes for Passives) exist and have been used to demonstrate basic technology / component capabilities and parametric limits and major potential failure modes are known. This includes an initial characterization of robustness toward ionising radiation (TID), if applicable. Work achievement: initial hardware based test data obtained, initial quantification of possible performance parameters. |
| TRL 3 | Milestones and work achievements: Design library and special functions for the intended application and environment and eventually hardened against TID, if applicable, exist. Relevant Failure Modes (wear out and overstress driven) are known, characterized and compatible with the intended application. First simulation models and tools are available to allow functional verification of a component design, if applicable. Representative test structures are produced and suitable to demonstrate functionality, operating temperature range and a level of radiation tolerance as intended for the final product. |
| TRL 4 | Milestones: A comprehensive Component Detail Specification exists, test programs have been developed, evaluation boards designed and fabricated, if needed, and prototypes have been produced and successfully tested to demonstrate compliance with functional and performance requirements at least including temperature range, TID, DD and SEL (if applicable) testing to validate the component design. The manufacturer evaluation has been successfully completed. Work achievements: design maturity and manufacturability confirmed. |
| TRL 5 | Milestones: The component is available in its intended space qualified package (if applicable), has passed thermal/mechanical tests (e.g. shock, vibration, thermal cycling and the substrate/PCB mounting process has been qualified. The required SEE testing has been successfully completed. |
| TRL 6 | Milestones: The component has successfully completed the applicable evaluation test programme (ESCC or other) and reliability test data exists to confirm the required mission life time. Derating requirements have been defined. The supply chain has been consolidated and operates under an independently certified QMS. The component design is fully approved, its functional and performance characteristics are fully specified and it is recurrently producible in a stabilized manufacturing process with a known yield. Work achievements: the functional and performance validation in the intended application environment has been completed / a manufacturer’s in house qualification is achieved, if applicable. |
| TRL 7 | Milestones: The component has successfully completed the applicable evaluation test programme (ESCC, ECSS-Q-ST-60 class 1 or equivalent requirements from other standardization systems) and reliability test data exists to confirm the required mission life time. Derating requirements have been defined. The supply chain has been consolidated and operates under an independently certified QMS. All Radiation Hardness Assurance tests have been successfully completed and complementary mitigation options identified. Component has been qualified against ESCC or equivalent EEE space component qualification systems or for custom mission specific components achieved the full demonstration of meeting the mission requirements. |
| TRL 8 | Milestones / Work achievements: Component has been qualified against ESCC or equivalent EEE space component qualification systems or for custom mission specific components achieved the full demonstration of meeting the mission requirements. A space qualified component has been demonstrated to meet mission requirements which exceed the envelope of space qualification requirements, if necessary, including the effectiveness demonstration of system level mitigation measures (e.g. with external error detection and correction). |
| TRL 9 | Milestones / Work achievements: The component has achieved flight heritage as per qualification envelope or under specific mission approval constraints after two years of nominal performance under nominal mission conditions. |

                - : Use of TRL for with EEE component development

- TRL considerations for specific disciplines

  - TRL considerations for materials and manufacturing process

A challenge for materials technology readiness level is the inherent link to the maturity status of the manufacturing process as well as associated supply chain risks in maintaining the manufacturing capability. Table C-1 provides an overview that relates the TRL to the manufacturing capability and provisions for product assurance.

                - : Use of TRL for with materials and manufacturing process development

| TRL | Testing requirements | M&P requirements | Legal/regulatory requirements |
| --- | --- | --- | --- |
| 1 | - | - | - |
| 2 | - | - | - |
| 3 | Feasibility test Analytical test | Materials and processes assessed for manufacturability and availability. Definition of supply chain requirements. | General assessment of obsolescence risks (supply chain, regulatory) for materials and processes. Full assessment of exposure to environmental regulations (e.g. REACH, RoHS) other obsolescence risks for materials and processes in line with product life-cycle. Lessons learned |
| 4 | Test configuration, relevant environment, and results recorded in traceable manner. Implementation of Test Readiness Review (TRR). | Function of critical materials and processes recorded and followed up. Materials performance and process parameters characterised at elementary level. |  |
| 5 | Implementation of Test Review Board (TRB). | Representative materials performance and process parameters characterised in relation to their end-use. | ECSS-Q-ST-70 and ECSS-Q-ST-70-71 and relevant level 3 standards are applicable. |
| 6 | Test plan with relevant technical and PA expertise. Test reports Analytical report | Processes are in place to ensure manufacturability and quality for production of demonstrator. Materials performance and process parameters characterised in relation to their end-use. |  |
| 7 | QM Test plan with relevant technical and PA expertise. QM Test reports | Full capability is in place for manufacturing QM model in relevant (controlled) environment. |  |
| 8 | FM Test plan with relevant technical and PA expertise. FM Test reports | Flight model is built | Flight acceptance |
| 9 | In orbit operation report | In orbit operation | Flight proven |