

Space engineering

System engineering general requirements

**ECSS Secretariat**

**ESA-ESTEC**

**Requirements & Standards Division**

**Noordwijk, The Netherlands**

**Foreword**

This Standard is one of the series of ECSS Standards intended to be applied together for the management, engineering and product assurance in space projects and applications. ECSS is a cooperative effort of the European Space Agency, national space agencies and European industry associations for the purpose of developing and maintaining common standards. Requirements in this Standard are defined in terms of what shall be accomplished, rather than in terms of how to organize and perform the necessary work. This allows existing organizational structures and methods to be applied where they are effective, and for the structures and methods to evolve as necessary without rewriting the standards.

This Standard has been prepared by the ECSS-E-ST-10C Rev.1 Working Group, reviewed by the ECSS Executive Secretariat and approved by the ECSS Technical Authority.

**Disclaimer**

ECSS does not provide any warranty whatsoever, whether expressed, implied, or statutory, including, but not limited to, any warranty of merchantability or fitness for a particular purpose or any warranty that the contents of the item are error-free. In no respect shall ECSS incur any liability for any damages, including, but not limited to, direct, indirect, special, or consequential damages arising out of, resulting from, or in any way connected to the use of this Standard, whether or not based upon warranty, business agreement, tort, or otherwise; whether or not injury was sustained by persons or property or otherwise; and whether or not loss was sustained from, or arose out of, the results of, the item, or any services that may be provided by ECSS.

Published by: ESA Requirements and Standards Division

 ESTEC, P.O. Box 299,

 2200 AG Noordwijk

 The Netherlands

Copyright: 2017 © by the European Space Agency for the members of ECSS

Change log

|  |  |
| --- | --- |
| ECSS-E-10A19 April 1996 | First issue |
| ECSS-E-10 Part 1B18 November 2004 | Second issue |
| ECSS-E-ST-10C6 March 2009 | Third issue |
| ECSS-E-ST-10C Rev.115 February 2017 | Third issue Revision 1Major changes of this version with regard to the previous version are:* Implementation of Change Requests
* Update of Scope of document
* Inclusion of ECSS-E-AS-11 " Adoption Notice of ISO 16290, Space systems - Definition of the Technology Readiness Levels (TRLs) and their criteria of assessment" as Normative Reference
* Update of clause 3 "Terms, definitions and abbreviated terms"
* Term "system engineering organisation" replaced in the whole document by "system engineering function"
* Updated of clause 4 "Overview of system engineering" including Figure 4-1
* Former clause 6 "Overview of system engineering tasks per project phase" deleted and added with modifications as new clause 4.3 "Overview of system engineering tasks per project phase" as informative material.
* Clause 7 "Pre-tailoring matrix per space product types" added
* Annex A including Table A-1 updated
* Annex M "Interface Requirement document (IRD) - DRD" deleted as this DRD is now part of ECSS-E-ST-10-24 "Interface management"
* Annex Q "Analysis report – DRD" deleted and added with modifications as informative Annex S "Guideline content of Analysis Report" as last Annex.
* All references to ECSS-E-HB-10 "System engineering guidelines" removed as this document was never published and is not planned anymore.

**Added requirements*** 5.1d; 5.2.3.3c; 5.6.3c; 5.6.7d-g; E.2.1<5>b.

**Modified requirement*** 5.1a; 5.1c; 5.2.1a-e; 5.2.2a-c; 5.2.3.1a-c; 5.2.3.2a-b; 5.2.3.3b; 5.2.3.4a-b; 5.2.3.5a; 5.2.3.7a; 5.2.3.8a; 5.2.3.9a; 5.3.1a-j; 5.3.2a-e; 5.3.3a-c; 5.3.4a-h; 5.4.1.1a-f; 5.4.1.2a-c; 5.4.1.3a-f; 5.4.1.4a-c; 5.4.2.1a-c; 5.2.2.2a; 5.4.2.3a; 5.5.1a; 5.5.2b-d and f; 5.6.1a and f-g; 5.6.2a; 5.6.3a-b; 5.6.4a; 5.6.5a-b; 5.6.7a-c; 5.6.8a and c; 5.6.9a-c; B.2.1<4>a ; D.2.1<3.1>a.4 and 5; D.2.1<4.1>b; D.2.1<4.4>a; D.2.1<5.1.1>a and b NOTE deleted; D.2.1<5.1.2>f; D.2.1<5.2>b (all interleaved NOTES moved to end of requirement); F.2.1<4>b.1 and 2; G.2.1<5.5>a; G.2.1<8>a; I.2.1<3>a (interleaved Note moved to end of requirement); P.2.1<5.3>a.4; all requirements of Annex Q deleted as this Annex was converted into the new informative Annex S**.**

**Deleted requirements*** 5.1b; 5.2.3.1d; 5.2.3.3a; 5.2.3.6a-b; 5.2.3.8b; 5.4.2.3b; 5.5.2a and e; 5.6.1b-e; 5.6.4b-c; 5.6.6a-b; 5.6.8b; 6.2a-e; 6.3a-c; 6.4a-c; 6.5a-c; 6.6a-c; 6.7a-c; 6.8a-d; 6.9a-b; B.2.1<4>b (moved into requirement B.2.1<4>a); all requirements of Annex M and Annex Q.

**Editorial modifications and corrections:*** E.1.2 Reference to Annex referred to corrected to read "Annex D"
* Title of header of E.2.1<5> changed from "Critical issues" to "Technology issues"
* ECSS references in Annex R completed
* Bibliography updated and corrected.
* All embedded Notes moved to the end of the respective requirement.
 |

Table of contents

[Change log 3](#_Toc474402265)

[1 Scope 8](#_Toc474402266)

[2 Normative references 10](#_Toc474402267)

[3 Terms, definitions and abbreviated terms 11](#_Toc474402268)

[3.1 Terms from other standards 11](#_Toc474402269)

[3.2 Terms specific to the present standard 11](#_Toc474402270)

[3.3 Abbreviated terms 12](#_Toc474402271)

[4 Overview of system engineering 15](#_Toc474402272)

[4.1 The system engineering discipline 15](#_Toc474402273)

[4.2 The system engineering process 19](#_Toc474402274)

[4.3 Overview of system engineering tasks per project phase 20](#_Toc474402275)

[4.3.1 Overview 20](#_Toc474402276)

[4.3.2 General 20](#_Toc474402277)

[4.3.3 Phase 0 Overview: Mission analysis-need identification 21](#_Toc474402278)

[4.3.4 Phase A Overview: Feasibility 21](#_Toc474402279)

[4.3.5 Phase B Overview: Preliminary definition 21](#_Toc474402280)

[4.3.6 Phase C Overview: Detailed definition 22](#_Toc474402281)

[4.3.7 Phase D Overview : Qualification and production 22](#_Toc474402282)

[4.3.8 Phase E Overview: Operations / utilization 22](#_Toc474402283)

[4.3.9 Phase F Overview: Disposal 22](#_Toc474402284)

[5 General requirements 24](#_Toc474402285)

[5.1 System engineering plan 24](#_Toc474402286)

[5.2 Requirement engineering 25](#_Toc474402287)

[5.2.1 General 25](#_Toc474402288)

[5.2.2 Requirement traceability 25](#_Toc474402289)

[5.2.3 Requirement engineering process 26](#_Toc474402290)

[5.3 Analysis 28](#_Toc474402291)

[5.3.1 System analysis 28](#_Toc474402292)

[5.3.2 System environments and design and test factors 29](#_Toc474402293)

[5.3.3 Trade-off analyses 29](#_Toc474402294)

[5.3.4 Analysis methods, tools and models 30](#_Toc474402295)

[5.4 Design and configuration 31](#_Toc474402296)

[5.4.1 Design 31](#_Toc474402297)

[5.4.2 Configuration 32](#_Toc474402298)

[5.5 Verification 33](#_Toc474402299)

[5.5.1 General 33](#_Toc474402300)

[5.5.2 Product verification 33](#_Toc474402301)

[5.6 System engineering integration and control 34](#_Toc474402302)

[5.6.1 Management of system engineering activities 34](#_Toc474402303)

[5.6.2 Planning 34](#_Toc474402304)

[5.6.3 Engineering data 34](#_Toc474402305)

[5.6.4 Interface control 35](#_Toc474402306)

[5.6.5 Coordinate systems and units 35](#_Toc474402307)

[5.6.6 Technical budgets and margin policy 35](#_Toc474402308)

[5.6.7 Technology 35](#_Toc474402309)

[5.6.8 Risk management 36](#_Toc474402310)

[5.6.9 Changes and nonconformances control 36](#_Toc474402311)

[6 <<deleted and added with modifications as new clause 4.3>> 37](#_Toc474402312)

[6.1 <<deleted>> 37](#_Toc474402313)

[6.2 <<deleted, modified and moved to clause 4.3>> 37](#_Toc474402314)

[6.3 <<deleted, modified and moved to clause 4.3>> 37](#_Toc474402315)

[6.4 <<deleted, modified and moved to clause 4.3>> 37](#_Toc474402316)

[6.5 <<deleted, modified and moved to clause 4.3>> 37](#_Toc474402317)

[6.6 <<deleted, modified and moved to clause 4.3>> 38](#_Toc474402318)

[6.7 <<deleted, modified and moved to clause 4.3>> 38](#_Toc474402319)

[6.8 <<deleted, modified and moved to clause 4.3>> 38](#_Toc474402320)

[6.9 <<deleted, modified and moved to clause 4.3>> 38](#_Toc474402321)

[7 Pre-tailoring matrix per space product types 39](#_Toc474402322)

[Annex A (informative) System engineering documents delivery per review 53](#_Toc474402323)

[Annex B (normative) Mission description document (MDD) - DRD 57](#_Toc474402324)

[Annex C (normative) System concept report - DRD 61](#_Toc474402325)

[Annex D (normative) System engineering plan (SEP) - DRD 62](#_Toc474402326)

[Annex E (normative) Technology plan (TP) - DRD 71](#_Toc474402327)

[Annex F (normative) Technology matrix - DRD 75](#_Toc474402328)

[Annex G (normative) Design definition file (DDF) - DRD 77](#_Toc474402329)

[Annex H (normative) Function tree - DRD 82](#_Toc474402330)

[Annex I (normative) Technical budget - DRD 84](#_Toc474402331)

[Annex J (normative) Specification tree - DRD 86](#_Toc474402332)

[Annex K (normative) Design justification file (DJF) - DRD 88](#_Toc474402333)

[Annex L (normative) Trade-off report - DRD 95](#_Toc474402334)

[Annex M (normative) <<deleted>> 98](#_Toc474402335)

[Annex N (normative) Requirements traceability matrix (RTM) - DRD 99](#_Toc474402336)

[Annex O (normative) Requirements justification file (RJF) - DRD 101](#_Toc474402337)

[Annex P (normative) Product user manual (PUM or UM) - DRD 104](#_Toc474402338)

[Annex Q <<deleted and replaced by informative Annex S>> 112](#_Toc474402339)

[Annex R (informative) Mapping of typical DDP to ECSS documents 114](#_Toc474402340)

[Annex S (informative) Guideline content of Analysis Report 116](#_Toc474402341)

[Bibliography 118](#_Toc474402342)

**Figures**

[Figure 4‑1: System engineering, sub-functions and boundaries 17](#_Toc474402343)

[Figure 4‑2: System engineering sub-functions inter-relationships 18](#_Toc474402344)

[Figure B-1 : Relationship between documents 58](#_Toc474402345)

[Figure E-1 : TRSL template 74](#_Toc474402346)

**Tables**

[Table A-1 : System engineering deliverable documents 54](#_Toc474402347)

# Scope

This standard specifies the system engineering implementation requirements for space systems and space products development.

Specific objectives of this standard are:

* to implement the system engineering requirements to establish a firm technical basis and to minimize technical risk and cost for space systems and space products development;
* to specify the essential system engineering tasks, their objectives and outputs;
* to implement integration and control of engineering disciplines and lower level system engineering work;
* to implement the “customer-system-supplier model” through the development of systems and products for space applications.

Depending of the product category, the application of this standard needs to be checked and if needed tailored. The pre-tailoring table in clause 7 contains the applicability of the requirements of this document and its annexes according to product type. Specific requirements related to system engineering, like technical specification, verification, and testing are specified in dedicated documents and standards within the set of ECSS system engineering standards ECSS-E-ST-10-XX.

Discipline or element specific engineering implementation requirements are covered in dedicated ECSS standards. These standards are based on the same principles, process and documentation model. The applicability of each these standards can therefore not be considered in isolation from the others.

* 1. 1 The term “Discipline” is defined in ECSS-M-ST-10, as “a specific area of expertise within a general subject”. The name of the discipline normally indicates the type of expertise, e.g. in the ECSS system mechanical engineering, software and communications are disciplines within the engineering domain.
	2. 2 The requirements on the system engineering process are gathered in this standard; specific aspects of the SE process are further elaborated in dedicated standards.

For engineering process both for SW and for Ground Segment and Operations the following standards are considered fully sufficient for development of these items:

* ECSS-E-ST-70 Space engineering - Ground systems and operations
* ECSS-E-ST-40 Space engineering - Software
* ECSS-Q-ST-80 Space product assurance - Software product assurance

This standard may be tailored for the specific characteristic and constrains of a space project in conformance with ECSS-S-ST-00.

# Normative references

The following normative documents contain provisions which, through reference in this text, constitute provisions of this ECSS Standard. For dated references, subsequent amendments to, or revision of any of these publications do not apply, However, parties to agreements based on this ECSS Standard are encouraged to investigate the possibility of applying the more recent editions of the normative documents indicated below. For undated references, the latest edition of the publication referred to applies.

|  |  |
| --- | --- |
| ECSS-S-ST-00-01 | ECSS system - Glossary of terms |
| ECSS-E-AS-11 | Adoption Notice of ISO 16290, Space systems - Definition of the Technology Readiness Levels (TRLs) and their criteria of assessment |
| ECSS-E-ST-10-02 | Space engineering – Verification |
| ECSS-E-ST-10-06 | Space engineering – Technical requirements specification |
| ECSS-E-ST-10-09 | Space engineering – Reference coordinate system |
| ECSS-E-ST-10-24 | Space engineering – Interface control |
| ECSS-M-ST-10 | Space project management – Project planning and implementation |
| ECSS-M-ST-40 | Space project management – Configuration and information management |
| ECSS-Q-ST-10 | Space product assurance - Product assurance management |
| ECSS-Q-ST-10-09  | Space product assurance - Nonconformance control system |
| ECSS-Q-ST-20-10 | Off-the-shelf items utilization in space systems |

# Terms, definitions and abbreviated terms

## Terms from other standards

1. For the purpose of this Standard, the terms and definitions from ECSS-S-ST-00-01 apply, in particular for the following terms:
	1. acceptance
	2. approval
	3. configuration baseline
	4. critical
	5. development
	6. equipment
	7. inspection
	8. integration
	9. mission statement
	10. product tree
	11. requirement
	12. specification
	13. subsystem
	14. system
	15. test
	16. verification
2. For the purpose of this Standard, the terms and definitions from ECSS-E-AS-11 apply, in particular for the following terms:
	1. technology readiness level

## Terms specific to the present standard

1. requirement traceability

requirement attribute that links each single requirement to its higher level requirements inside the requirement set

1. This enables the derivation of a requirement tree, which demonstrates the coherent flow-down of the requirements.
2. recurring product

product which conforms to a qualified design and is produced according to the corresponding production master file

1. system engineering

interdisciplinary approach governing the total technical effort required to transform requirements into a system solution

1. From IEEE P1220.

|  |  |
| --- | --- |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |

1. verification matrix

initial issue of the VCD which contains for each requirement to be verified the methods, levels and stages of product verification

1. See ECSS-E-ST-10-02 for a more detailed definition of the VCD.

## Abbreviated terms

For the purpose of this Standard, the abbreviated terms from ECSS-S-ST-00-01 and the following apply:

|  |  |
| --- | --- |
| Abbreviation | Meaning |
| AIT | assembly, integration and test |
| AIV plan | assembly, integration and verification plan |
| AOCS | attitude and orbit control sub-system |
| AR | acceptance review |
| CDR | critical design review |
| COTS | commercial off-the-shelf |
| CRR | commissioning results reviewNOTE For space vehicles (e.g. launcher, transfer vehicle, crew transport vehicle) the CRR can be replaced or complemented by a flight qualification review (FQR).  |
| DDF | design definition file |
| DDP | design development plan |
| DJF | design justification file |
| DRD | document requirements definition |
| ECSS | European Cooperation for Space Standardization |
| ELR | end-of-life review |
| FDIR | failure, detection, isolation, recovery |
| FM | flight model |
| FMECA | failure modes, effects, and criticality analysis |
| FOM | flight operations manual |
| FRR | flight readiness review |
| FTA | fault tree analysis |
| GSE | ground support equipment |
| HITL | human-in-the-loop |
| ICD | interface control document |
| ILS | integrated logistic support |
| IRD | interface requirement document |
| LRR | launch readiness review |
| MCR | mission closed-out review |
| MDD | mission description document |
| MDR | mission definition review |
| MOP | mission operations plan |
| MS | mission statement |
| ORR | operational readiness review |
| PDR | preliminary design review |
| PM&P  | parts materials and processes |
| PMP  | project management plan |
| PRR | preliminary requirement review |
| PUM  | product user manual |
| QR | qualification review |
| RAMS | reliability, availability, maintainability, safety |
| RAR | risk assessment report |
| RF | radio frequency |
| RJF | requirement justification file |
| ROD | review of design |
| ROM/RAM | read only memory / random access memory |
| RTM | requirement traceability matrix |
| R&D | research and development |
| SE | system engineering |
| SEP | system engineering plan |
| SFT | system functional test |
| SRR | system requirement review |
| SVT | system validation test |
| TP | technology plan |
| TRA | technology readiness assessment |
| TRL | technology readiness level |
| TRSL | technology readiness status list |
| TS | technical requirements specification |
| UM  | user manual |
| VCD | verification control document |
| VP | verification plan |
| w.r.t. | with respect to |

# Overview of system engineering

## The system engineering discipline

System engineering is an interdisciplinary approach governing the total technical effort to transform requirements into a system solution.

A system is an integrated set of elements to accomplish a defined objective. These elements include hardware, software, firmware, human resources, information, techniques, facilities services, and other support elements.

In this standard the concept of “system” is used in a wide sense. The highest level, often called “mission level” or “space system”, consists usually of one (or more) space segment(s), of a ground segment, and of a user segment. Elements of system decomposition are also considered a system. For the purpose of this standard the system can be any element at any level of decomposition as defined by the function tree (see Annex H) or the product tree (see ECSS-M-ST-10 Annex B). The scope of an element can include hardware, software, procedures, man-in-the-loop, facilities and services.

From the perspective of the considered system, requirements originate from the next upper level (the customer) and elements are procured from the next lower level (the suppliers).

* 1. 1 The customer-supplier model is described in ECSS-S-ST-00.
	2. 2 Through this standard the notion of customer refers to several actors ,in relation to the project phase. In fact a customer can be e.g. a scientific community in phase 0, a commercial user in phase A or an Agency in phase B. A supplier can on the other hand be an Agency in both phase 0 and phase A.

Figure 4‑1 shows the boundaries of system engineering (for which the indicated interactions between the identified major disciplines is not exhaustive but indicative), its relationship with production, operations, product assurance and management disciplines (and their cross-interaction is indicated as “interface areas” in the figure) and its internal partition into the following system engineering sub-functions:

* requirement engineering, which consist on requirement analysis and validation, requirement allocation, and requirement maintenance;
* analysis, which is performed for the purpose of resolving requirements conflicts, decomposing and allocating requirements during functional analysis, assessing system effectiveness (including analysing risk factors); and complementing testing evaluation and providing trade studies for assessing effectiveness, risk, cost and planning;
* design and configuration which results in a physical architecture, and its complete system functional, physical and software characteristics;
* verification, which objective is to demonstrate that the deliverables conform to the specified requirements, including qualification and acceptance;
* system engineering integration and control, coordinating the various engineering disciplines and participants throughout all the project phases.

Figure 4‑2 shows system engineering sub-functions, their inter-relationships and their main activities during the system engineering process.

System engineering sub-functions are applied in an iterative mode during implementation of the system engineering process described in clause 4.2.

Within the frame of a project, the system engineering function is generally implemented by a system engineering organisation of the supplier which is in charge of transforming the requirements of the customer into a system solution delivered by the supplier. For the purpose of this standard, the ‘*system engineering function*’ only is referred to in the normative statements, independent of whether the supplier has a formal ‘system engineering organisation’ or not.

1. With respect to the next lower level, the supplier plays the role of the customer.



Figure 4‑1: System engineering, sub-functions and boundaries



Figure 4‑2: System engineering sub-functions inter-relationships

## The system engineering process

The system engineering activities of a project are conducted by an entity or resources within the project team of a supplier. This entity or the resources that perform this function is called in this document “system engineering function”. The system engineering process is in turn applied by each system engineering function of each supplier of the elements of the product decomposition.

The system engineering process consists of activities to be performed by the system engineering function within each project phase according to the designated lifecycle model. The objective is to obtain a product which satisfies the customer technical requirements within pre-established objectives of cost time and quality. The requirements for these activities are described in clause 5.

The system engineering process is intrinsically iterative across the whole life of a project, in particular in the initial phases (i.e. 0, A, and B) of the development of a complex system (e.g. a spacecraft), procured through a multi-layered set of suppliers.

During these phases, the system engineering function derives design oriented technical solutions starting from the design-independent customer requirements contained in a technical requirements specification (TS). This is achieved through an iterative top-down process by trading off several design solutions at an increasing level of detail.

1. For definition and requirements for a technical requirements specification see ECSS-E-ST-10-06.

Through this process the system engineering function performs a multidisciplinary functional decomposition to obtain logical lower level products (both hardware and software). At the same time the system engineering function decides on balanced allocations, throughout the system, of resources allocated by the customer and respects agreed margin philosophies as a function of the relevant technology readiness levels.

The functional decomposition defines, for each level of the system, the technical requirements for the procurement of subassemblies or lower level products as well as the requirements for the verification of the final characteristics of each product.

The system engineering process uses the results of these lower level verification activities to build a bottom-up multi-layered evidence that the customer requirements have been met.

The system engineering process is applied with various degrees of depth depending on the level of maturity of the product (e.g. new development or off-the-shelf).

The system engineering process can be applied with different level of tailoring as agreed between customer and supplier in their business agreement.

The system engineering function has interfaces with those other functions in charge of management, product assurance, engineering disciplines, production, and operations and logistics.

1. The project phases are defined in ECSS-M-ST-10.

## Overview of system engineering tasks per project phase

### Overview

The allocation of specific system engineering requirements per phase depends strongly on the type of business agreement established between customer and supplier and the nature and level of complexity of the system subject of the agreement. The breakdown and the details of the tasks are defined in the business agreement specific documents.

1. Some projects define them in a Statement of work (SoW).

The actors in the customer-supplier relationship change between phases and across levels. In the following clauses each system engineering function is meant to be the supplier’s system engineering function during that phase.

### General

1. The system engineering function plans its activities in conformance with the project phases as defined in the Project Management Plan in accordance with ECSS-M-ST-10 and document it in the SEP as per Annex D.
2. The phases or combination thereof to be implemented for a project are specified in the business agreement.
3. The system engineering function monitors the execution of all system engineering activities including lower levels.
4. The system engineering function identifies the critical items in cooperation with the Product Assurance (PA) according to ECSS-Q-ST-10 (PA being tasked to manage the critical items throughout the project life).
5. The system engineering function ensures that for critical items the technical requirements specification, the design definition file and the design justification file are available at latest by end of Phase B .
6. Information regarding the expected delivery of system engineering documents for each project review is provided in 7.
	* + 1. The documents to be approved by the customer as well as the time of their approval are listed in the business agreement.
7. The system engineering function activities need to be aligned with Product Assurance (PA) activities according to ECSS-Q-ST-10 throughout the project life. This includes definition and execution of tasks in which PA activities are involved (detailed in the Product Assurance Plan).

### Phase 0 Overview: Mission analysis-need identification

1. For Phase 0, the system engineering function
	1. supports the identification of customer needs.
	2. proposes possible system concepts.
	3. supports the Mission Definition Review (MDR) and ensures implementation of the MDR actions.
	4. performs an analysis of the Mission Statement document, and integrates this analysis and any relevant contribution from lower level suppliers in to a Mission Description document(s) in conformance with Annex B, and maintains this latter document for the final selected concept.
	5. proposes the requirements against the expressed user needs for agreement with the customer.
2. Mission Statement captures the declared “user needs”.

### Phase A Overview: Feasibility

1. For Phase A, the system engineering function
	1. finalises the expression of the needs identified in Phase 0.
	2. proposes system solutions (including identification of critical items and risks) to meet the customer needs.
	3. supports the Preliminary Requirement Review (PRR) and ensure implementation of PRR actions.
	4. finalises the validation of the requirements against the expressed needs together with the customer.
2. Mission Statement captures the declared “user needs”.

### Phase B Overview: Preliminary definition

1. For Phase B, the system engineering function
	1. establishes the system preliminary definition for the system solution selected at end of Phase A.
	2. demonstrates that the solution meets the technical requirements according to the schedule, the target cost and the customer requirements.
	3. supports the System Requirements Review (SRR) and Preliminary Design Review (PDR), and ensuring implementation of the SRR and PDR actions.
	4. define development approach and plan of engineering activities.

### Phase C Overview: Detailed definition

1. For Phase C, the system engineering function
	1. establishes the system detailed definition.
	2. demonstrates the capability to meet the technical requirements of the system technical requirements specification.
	3. supports the Critical Design Review (CDR) and ensures implementation of the CDR actions.

### Phase D Overview : Qualification and production

1. For Phase D, the system engineering function
	1. finalizes the development of the system by qualification and acceptance.
	2. finalizes the preparation for operations and utilization.
	3. supports Qualification Review (QR) and Acceptance Review (AR) and ensures implementation of the QR and AR actions.

### Phase E Overview: Operations / utilization

1. For Phase E, the system engineering function
	1. supports the launch campaign.
	2. supports the entity in charge of the operations and utilization following the terms of a business agreement.
	3. supports the Flight Readiness Review (FRR), Operations Readiness Review (ORR), Launch Readiness Review (LRR), Commissioning Results Review (CRR), End-of-Life Review (ELR), and recurring products AR, and ensure implementation of the actions of those reviews.
	4. supports the execution of all system engineering activities and provision of documents in support to anomaly investigations and resolutions.
2. Phase E and its reviews as presented in Table A-1 refer only to mission level. In case of lower level product, activities to be considered by the system engineering function are only related to maintenance and anomaly investigations.

### Phase F Overview: Disposal

1. For Phase F, the system engineering function
	1. supports the entity in charge of the disposal following the terms of a business agreement.
	2. supports the Mission Close-out Review (MCR) and ensure implementation of the actions of the MCR.
2. Phase F and its review as presented in Table A-1 refer only to mission level. In case of lower level product, activities to be considered by the system engineering function are only related to disposal.

# General requirements

## System engineering plan

The system engineering function shall produce and maintain a system engineering plan (SEP) in conformance with Annex D.

1. The system engineering function establishes the SEP with the contributions and constraints of management, product assurance, engineering disciplines, production, and operations and logistics.

<<deleted and moved modified as Note to 5.1a>>

The SEP shall take consideration of the lower level plans, ensure consistency between these plans, and, be consistent with these plans.

* 1. 1 The early version of the Project Management Plan (PMP), which includes the early version of the SEP, contains all the information which was traditionally contained in the Design and Development Plan (DDP). See Annex R which illustrates the mapping between a typical DDP and ECSS DRDs.
	2. 2 The SEP content evolves with the phase of the project, with more information on risk analysis and new technologies in early phases 0, A and B, and more information on verification and validation aspects in phases C, D.
	3. 3 The SEP can be considered a collection of documents delivered over the life-cycle as illustrated in Table A-1.
	4. 4 No SEP lower than equipment/unit.

The system engineering function shall support the project manager in the project reviews as defined in the Project Management Plan in accordance with ECSS-M-ST-10.

## Requirement engineering

### General

The system engineering function shall analyse the requirements for the system issued by the customer.

* 1. 1 This analysis enables the transformation of customer requirements into the supplier’s system solution.
	2. 2 The level of the required analysis and form of any deliverable is expressed in the business agreement.

The system engineering function shall derive, generate, control and maintain the set of requirements for the lower level elements, defining their design and operational constraints and the parameters of functionality, performance, and verification necessary to meet the system requirements issued by the customer.

The system engineering function shall ensure consistency of the requirements at system level, at lower levels, as well as amongst levels.

1. Consistency of requirements of different system engineering sub-functions at the same level is the responsibility of the higher level system engineering function.

The system engineering function shall ensure requirements generated in 5.2.1b. are in conformance with characteristics specified in ECSS-E-ST-10-06 clause 8.

The system engineering function shall ensure that each requirement for the lower level elements has a justification reflected in the requirement justification file in conformance with Annex O.

1. Tailoring of a standard in a list of applicable standards, or of a requirement in an applicable standard, is possible where each tailoring measure is duly justified.

### Requirement traceability

The system engineering function shall ensure forward and backward traceability of all requirements:

to their sources;

to the lower level requirements, if existing;

to changes in the design inducing modifications of the requirements;

to their verification close-out.

1. to item 1: Examples for sources: a higher level requirement, an imposed management constraint, an applicable standard or an accepted lower level constraint.

The system engineering function shall establish and maintain the requirements traceability matrix in conformance with Annex N.

The system engineering function shall ensure that the requirement close-out traceability is documented in the VCD in conformance with ECSS-E-ST-10-02 Annex B.

### Requirement engineering process

#### Technical requirements specifications

The system engineering function shall establish technical requirements specifications of the next lower level products consistent among them and with the technical specification received from the customer.

The system engineering function shall ensure that the technical requirements specifications it establishes conform to ECSS-E-ST-10-06 and its DRD in Annex A.

The system engineering function shall establish a specification tree in conformance with Annex J.

* 1. 1 Requirements common to more than one lower level product can be gathered in “common” technical specifications called “support specifications” (e.g. GDIR “General Design and Interface Requirements”, environmental, test, EMC requirements specifications).
	2. 2 Requirements for equipment level products (or lower level products) can be issued in self-contained specifications.

<<deleted>>

#### Requirement consolidation

The system engineering function shall involve the customer in the consolidation of requirements by identifying and resolving incomplete, duplicate, ambiguous, and contradictory requirements for customer-issued requirements.

The system engineering function shall reflect the consolidated requirements in the release of the technical specifications.

#### Requirement risk analysis

<<deleted>>

The system engineering function shall perform the requirements analysis to identify impacts on system risks.

As part of the risk management process implemented on the project, the system engineering function shall report the requirement impacts on the risk.

1. ECSS‐M‐ST‐80 Annex E describes the risk reporting process.

#### Requirements verification methods

The system engineering function shall ensure that for each requirement contained in the technical requirements specification, one or a combination of verification methods are identified.

1. Technical requirements specification is defined in ECSS-E-ST-10-06 Annex A.

The system engineering function shall ensure that for each requirement contained in the technical requirements specification, the verification methods are reflected in the verification matrix.

1. Technical requirements specification is defined in ECSS-E-ST-10-06 Annex A.

#### Requirement allocation

The system engineering function shall ensure that the system requirements and their verification methods are allocated to lower levels and included in the specifications of the related products.

#### Requirements consistency

<<deleted>>.

<<deleted>>

#### Requirements agreement

In phase 0 the system engineering function shall propose requirements in response to the expressed user needs, for agreement with the customer.

1. ”User needs” are expressed in the Mission Statement document.
2. In some contexts this activity is called “requirements validation”. This terminology has not been used to avoid confusion with the term “validation” as defined in ECSS-S-ST-00-01.

#### Requirements maintenance

The system engineering function shall ensure that agreed changes to requirements are applied to and maintained in system and lower level specifications.

<<deleted>>.

#### Requirements baseline

The system engineering function shall establish the list of documents constituting the system requirements baselines in contribution to the configuration baselines.

1. Details on configuration baselines are provided in ECSS-M-ST-40.

## Analysis

### System analysis

In phase 0 the system engineering function shall perform an analysis of the Mission Statement document, produce Mission Description document(s) in conformance with Annex B, and maintain this latter document for the final selected concept.

The system engineering function shall perform a functional analysis, produce the functional architecture, and produce the function tree which satisfy the customer technical requirements specification, in conformance with Annex H.

The system engineering function shall document the functional architecture in the design definition file (DDF) in conformance with Annex G.

The system engineering function shall justify the functional architecture in the DJF in conformance with Annex K.

The system engineering function shall perform a physical analysis, produce the physical architecture and produce the product tree in conformance with ECSS-M-ST-10 Annex B.

The system engineering function shall document the physical architecture in the DDF in conformance with Annex G.

The system engineering function shall justify the physical architecture in the DJF in conformance with Annex K.

The system engineering function shall analyse the performance of the system, including end-to-end evaluation, documenting the results of the analysis in the Design Justification File in conformance with Annex K.

The system engineering function shall analyse the influence of mission, design, development, operations and constraints on cost and schedule as an input to the project cost and schedule consolidation and to the utilisation recurring cost

The system engineering function shall document analysis that it performs in an analysis report.

1. An example of an analysis report is given in Annex S.

### System environments and design and test factors

The system engineering function shall establish the influence of all types of environments applied during each life profile event on system and its elements in terms of nominal and extreme environmental conditions including all applicable operational phases.

The system engineering function shall establish the criteria for qualification and acceptance in conformance with Annex K of system and system elements for all types of environment.

The system engineering function shall ensure that analyses include design induced effects between system components or the system and its external environment and account for analysis uncertainties, in conformance with Annex K.

The system engineering function shall establish the design and test factors and margins applicable for design in conformance with Annex K.

* 1. 1 Design factors are factors applied to specified loads to ensure robustness of the design.
	2. 2 Test factors are factors applied to specified loads to demonstrate margins w.r.t. these loads (e.g. qualification / acceptance factors).

The system engineering function shall establish test environment conditions for product verification in test specifications.

### Trade-off analyses

The system engineering function shall conduct or consolidate trade-off analyses to:

assist in selecting system concepts, designs and solutions (including people, parts and materials availability);

support material selection and process decisions;

support make-or-buy and supplier selection;

examine alternative technologies to satisfy functional and design requirements;

evaluate environmental and cost impacts of materials and processes;

evaluate alternative physical architectures to select preferred products and processes;

establish the system and its configuration items;

analyze planning critical paths and propose alternatives;

select standard components, techniques, services and facilities that reduce system life-cycle cost;

establish model and product verification philosophy for achieving qualification and acceptance objectives while considering testability;

assess design capacity to evolve.

The system engineering function shall evaluate alternative concepts, designs and solutions against each other in a Trade-off report in conformance with Annex L.

The system engineering function shall document alternative system concepts considered during system trade-off studies in a System Concept Report in conformance with Annex C.

### Analysis methods, tools and models

The system engineering function shall define the analysis methods and tools to be used during the product life cycle, as well as the related models and data exchanges between the tools, and document these in the SEP in conformance with Annex D.

The system engineering function shall ensure that analysis tools are validated.

The system engineering function shall ensure that analysis tools are maintained.

The system engineering function shall ensure that analysis tools are capable of exchanging and using models and data where agreed by customer and supplier.

* 1. 1 For exchange of models and data, see ECSS-E-TM-10-20 and ECSS-E-TM-10-21.
	2. 2 Exchange can be either direct or via interfaces.

The system engineering function shall ensure that analysis tools are capable of transferring models and data for multi-disciplinary analysis where agreed by customer and supplier.

* 1. 1 Details on product data exchange and system modelling and simulation are provided in ECSS-E-TM-10-20 and ECSS-E-TM-10-21.
	2. 2 Exchange can be either direct or via interfaces.

The system engineering function shall ensure that models produced by analysis tools are validated based on documented procedures and results.

The system engineering function shall ensure that modelling and test accuracy as well as limitations are considered (as part of Annex K) when establishing the performances and specifying environmental conditions for product verification.

The system engineering function shall ensure that models are kept operational in accordance with the terms of the business agreement.

## Design and configuration

### Design

#### General

The system engineering function shall establish a design of the system from its functional architecture, requirement allocation, and technology selection.

1. This includes definition of the interfaces and corresponding ICDs.

The system engineering function shall ensure that the design addresses system aspects, covering its whole lifecycle, producing the physical architecture documented in conformance with Annex G and the product tree in conformance with ECSS-M-ST-10 Annex B.

The system engineering function shall take into account the outcome of the design and verification activities of the lower level products.

The system engineering function shall ensure that the design covers hardware, software, and human-in-the-loop (HITL).

The system engineering function shall ensure that the design is supported by analyses consistent with the level of maturity of the design.

The system engineering function shall coordinate with all entities for design data exchange..

1. This relates to coordination between the various functions given in Figure 4‑1.

#### Technical budgets and margin policy

The system engineering function shall define, control and maintain all technical budgets of the system in conformance with Annex I in terms of target, current status and their trends.

The system engineering function shall apportion and control budget requirements to all levels of system decomposition.

The system engineering function shall define and apply the margin policy agreed between customer and supplier in compliance with Annex D.2.1<4.2>b.5.

1. The system margin policy is defined in the SEP.

#### Design methods, tools and models

The system engineering function shall define the design methods, tools and related models to be used during the product life cycle and document them in the SEP.

The system engineering function shall ensure that design tools are validated and maintained.

The system engineering function shall ensure that design tools are capable of exchanging and using design models and data where agreed by the customer and supplier.

The system engineering function shall ensure that models are kept operational in accordance with the business agreements.

The system engineering function shall ensure that design models produced by design tools are validated.

The system engineering function shall ensure that all design models are defined in accordance with the Coordinate System Document with transformation methods as defined in ECSS-E-ST-10-09.

1. Coordinate system document is delivered as part of the SEP.

#### Design files

The system engineering function shall establish and maintain a design definition file in conformance with Annex G.

The system engineering function shall establish and maintain a design justification file in conformance with Annex K.

The system engineering function shall establish and maintain a product user’s manual (PUM) or user’s manual (UM) in conformance with Annex P.

1. In case the product considered is a space segment, the Space Segment User Manual defined in ECSS-E-ST-70 Annex E is generated with support of the system engineering function.

### Configuration

#### Configuration content

The system engineering function shall ensure that the configuration includes the system functional, physical and software characteristics, budgets, and, internal and external interfaces.

The system engineering function shall ensure that the configuration includes lower decomposition levels.

The system engineering function shall ensure that the configuration is documented in the DDF and in configuration definition documents.

1. Details on configuration definition documents are provided in ECSS-M-ST-40.

#### Configuration baselines

The system engineering function shall establish the system configuration baselines to be placed under control at defined project milestones.

1. Details on system configuration baselines are provided in ECSS-M-ST-40.

#### Configuration assembly constraints

The system engineering function shall define and document the hierarchy and assembly sequence of the system elements in line with the physical architecture.

<<deleted and incorporated in 5.4.2.3a.>>.

## Verification

### General

The system engineering function shall define the Verification Plan in accordance with ECSS-E-ST-10-02 Annex A and coordinate the product verification accordingly..

### Product verification

<<deleted, covered by 5.5.2c.>>.

The system engineering function shall assign the product to a verification product category, as defined in ECSS-E-ST-10-02 Table 5-1.

The system engineering function shall specify the configuration and environment conditions for product verification and the criteria for its qualification and acceptance.

The system engineering function shall confirm that all product verification objectives are achieved by analysing the results of the verification activities.

1. This includes analysis of Verification Control Document and its closeout documents, as defined in ECSS-E-ST-10-02 Annex B.

<<deleted>>

The system engineering function shall ensure that the verification covers the complete product including hardware, software, human-in-the-loop (HITL), operations and representative mission scenarios (including pre-launch, launch and early orbit, in-orbit, post-landing, or other mission scenario).

* 1. 1 The testing performed during and at the end of the integration of a system is defined as System Functional Test (SFT).
	2. 2 For system composed of different segments (e.g. space segment, ground segment), the testing performed to ensure operability and functionality of the complete system is defined as System Validation Test (SVT).
	3. 3 System validation is performed against user needs and is typically performed under customer authority, with supplier involvement as detailed in the business agreement.

## System engineering integration and control

### Management of system engineering activities

The system engineering function shall implement the SEP including quantification of this effort as input to management.

<<deleted>>

<<deleted>>

<<deleted>>

<<deleted, covered by 5.6.1a.>>.

The system engineering function shall ensure that all engineering changes, dispositions and decisions are provided to project configuration control in accordance with the Configuration Management Plan.

The system engineering function shall ensure that the experience gained in past and in parallel activities is systematically considered and support project management in the collection of experience gained for future use.

### Planning

The system engineering function shall ensure that the SEP is consistent with the project schedule.

1. Details on the project schedule content are provided in ECSS-M-ST-60, in particular the DRD Annex B.

### Engineering data

The system engineering function shall define the engineering data to be stored in a data repository.

The system engineering function shall ensure that engineering data can be exchanged in electronic form between the different organizations in charge of the elements of the product decomposition levels via agreed and validated interfaces.

The system engineering function shall ensure the availability of engineering data to meet the schedule which enable the system to be designed, produced, tested, delivered, operated, maintained, and disposed of.

### Interface control

The system engineering function shall ensure external and internal interfaces are controlled in conformance with ECSS-E-ST-10-24.

* 1. 1 The control of the external interfaces is performed in cooperation with the parties involved in the interface.
	2. 2 Interface requirements are rolled-out of the technical specification as interface requirements documents

<<deleted>>

<<deleted>>.

### Coordinate systems and units

The system engineering function shall define the coordinate systems and related coordinate units in the Coordinate System Document conforming to DRD ECSS-E-ST-10-09 Annex A.

The system engineering function shall define the units system to be used during the product life cycle and document it in the SEP.

1. For example; the unit system being selected as "metric".

### Technical budgets and margin policy

<<deleted, covered by clause 5.4.1.2>>.

<<deleted, covered by clause 5.4.1.2>>

### Technology

The system engineering function shall identify candidate technologies, and document them in the Technology Matrix in conformance with Annex F.

The technologies proposed shall be assessed and verified in terms of TRL levels, defined in ECSS-E-AS-11, and documented in the Technology Plan in conformance with Annex E.

1. For assessing and verifying technologies, the process described in ECSS-E-HB-11 “TRL Handbook” can be used.

The system engineering function shall demonstrate supportability and feasibility within the defined supplier’s cost and schedule constraints.

The Technology Readiness Status List (TRSL) shall be completed and provided to the customer for Phase 0 in conformance with Annex E.2.1<5>.

The Technology Readiness Status List (TRSL) of the programme technologies shall be maintained and provided to the customer at Phase A and B project reviews

The TRSL specified in Annex E.2.1<5> shall be developed by the system engineering team with the support of the PA manager.

The items identified in the TRSL shall be assessed at Phase B for inclusion and tracking in the Critical Items List

1. The TRSL and the processes of transferring technologies to the Critical Item List is captured in ECSS-E-HB-11.

### Risk management

The system engineering function shall contribute to the identification of risks and mitigation measures.

1. Details on risk management are provided in ECSS-M-ST-80.

<<deleted, covered in 5.4.1.1f.>>.

The system engineering function shall implement and control the content of the risk management plan which is within system engineering responsibility.

### Changes and nonconformances control

The system engineering function shall provide a technical assessment on any change proposal to the baseline of the product.

The system engineering function shall provide a technical assessment on any nonconformance to the status of the product.

1. Nonconformance treatment is described by ECSS-Q-ST-10-09.

The system engineering function shall implement and control agreed actions assigned to it, arising from change proposals and nonconformances.

* 1. 1 Change is related to a request for deviation.
	2. 2 Nonconformance is related to a request for waiver.
	3. 3 The change procedure/control is defined as part of the configuration management as defined in ECSS-M-ST-40.

# <<deleted and added with modifications as new clause 4.3>>

# Pre-tailoring matrix per space product types

The Matrix of Table 7‑2 presents the pre-tailoring of this ECSS Standard per space product type.

For the terminology and definitions of the space product types see ECSS-S-ST-00-01.

1. “Ground segment equipment” is not to be confused with “Ground support equipment”.

ECSS-E-ST-10 addresses System Engineering processes to be followed throughout the whole Space System development. This includes, along with Space Segment, also Ground Segment and Operations.

Yet, specific standards detail the Engineering process both for SW and for Ground Segment and Operations. The following standards are considered fully sufficient for development of these items:

* ECSS-E-ST-70 Space engineering - Ground systems and operations
* ECSS-E-ST-40 Space engineering - Software
* ECSS-Q-ST-80 Space product assurance - Software product assurance

Thus, in the above applicability table, the columns for SW and Ground are stated as not applicable, i.e. “-”.

Table 7‑1: Definitions of the columns of Table 7‑2

| Column title | Description |
| --- | --- |
| Applicability status | There are nine product types, one per column.For each product type the possible values for each requirement are:**X** when applicable**-** when not applicable**//** when pre-tailoring applicability not definable - to be determined during tailoring>> the requirement is applicable to a lower product type. Responsibility of tailoring (if needed) resides with the customer of this lower product type**X#** when requirement is applicable except in a specific case - the criteria for being “not applicable” are defined in the Comments column **//#** when pre-tailoring applicability not definable – however supplementary indications regarding applicability in the tailoring are given in the Comments column1. "**#**” is a number to uniquely identify every comment in the same row.

A requirement is considered applicable for a product type if it is verified on this product type. |
| Comments | The column “Comments”* provides information on the limitation of applicability – it provides clarification on the limited and specific conditions for the applicability of the requirement.
* is not used to modify a requirement.
 |

Table 7‑2: Pre-tailoring matrix per “Space product types”

| ECSS req. # | Space system | Space segment element and sub-system | Space segment equipment | Launch segment element and sub-system | Launch segment equipment | Ground segment element and sub-system | Ground segment equipment | Ground support equipment | Software | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1a | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level: for subsystem level - see 22 applicability should be defined/tailored at each level for next lower level, depending on product heritage, engineering complexity and industrialization context. |
| 5.1c | X | X1 | - | //2 | - | - | - | - | - | 1 applicable at element level: for subsystem level - see 22 applicability should be defined/tailored at each level for next lower level, depending on product heritage, engineering complexity and industrialization context. |
| 5.1d | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level: for subsystem level - see 22 applicability should be defined/tailored at each level for next lower level, depending on product heritage, engineering complexity and industrialization context. |
| 5.2.1a | X | X | X | X | - | - | - | - | - |  |
| 5.2.1b | X | X | X1 | X | - | - | - | - | - | 1 not applicable in case of no lower level elements in scope of engineering responsibility of supplier. |
| 5.2.1c | X | X | X1 | X | - | - | - | - | - | 1 not applicable in case of no lower level elements in scope of responsibility of supplier. |
| 5.2.1d | X | //1 | //1 | //1 | - | - | - | - | - | 1 depending on the applicability of ECSS-E-ST-10-06 clause 8. |
| 5.2.1e | X | X | //1 | X | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.2.2a | X | X | X1 | X | - | - | - | - | - | 1 5.2.2a.1 not applicable in the case of upper level traceability provided by the upper layer; 5.2.2a.2 not applicable in the case of no lower level requirements. |
| 5.2.2b | X | X | X1 | X | - | - | - | - | - | 1 not applicable in case of no lower level components in scope of engineering responsibility of supplier |
| 5.2.2c | X | X | X | X | - | - | - | - | - |  |
| 5.2.3.1a | X | X | X1 | X | - | - | - | - | - | 1 not applicable in case of no lower level elements in scope of engineering responsibility of supplier |
| 5.2.3.1b | X | X | X1 | // | - | - | - | - | - | 1 applicable for new specifications developed by the equipment supplier in direct response to higher level ones in the contractual chain where the ECSS-E-ST-10-06 and Annex A are applicable. Not applicable where existing specifications developed from a different heritage or modifications thereof are deemed adequate. |
| 5.2.3.1c | X | X | X1 | X | X1 | - | - | - | - | 1 not applicable in case of no lower level elements in scope of engineering responsibility of supplier. |
| 5.2.3.2a | X | X | //1 | X | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.2.3.2b | X | X | //1 | X | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.2.3.3b | X | X | //1 | X | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.2.3.3c | X | X | //1 | X | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.2.3.4a | X | X | //1 | X | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.2.3.4b | X | X | //1 | X | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.2.3.5a | X | X | X1 | // | //2 | - | - | - | - | 1 not applicable in case of no lower level elements in scope of engineering responsibility of supplier2 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.2.3.7a | X | // | - | // | - |   |   | - | - |  |
| 5.2.3.8a | X | X | //1 | X | //1 | - | - | - | - | 1 lower levels specifications implementation, not applicable in case of no lower level elements in scope of engineering responsibility of supplier. |
| 5.2.3.9a | X | X | //1 | X | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context.ECSS-M-ST-40 is sufficient |
| 5.3.1a | X | - | - | //1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - and applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1b | X | X1 | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level,: for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1c | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1d | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1e | X | //1 | //1 | //1 | //1 | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1f | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1g | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, // for sub-system level- see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1h | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1i | X | //1 | - | //1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - and applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.1j | X1 | X1 | X1 | X | - | - | - | - | - | 1 Depending on the scope of the analysis other more detailed standards are used in place of Annex Q. |
| 5.3.2a | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, // for sub-system level - see 2 2 defined by the upper level and made applicable directly, applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.2b | X | X | //1 | // | - | - | - | - | - | 1 defined by the upper level and made applicable directly, applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.2c | X1 | X1 | X1 | // | - | - | - | - | - | 1 depending on the scope of the analysis other more detailed standards are used in place of Annex K. |
| 5.3.2d | X | X | //1 | // | - | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.2e | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.3a | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.3b | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level – see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.3c | X | X | - | //1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - and applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.4a | X | //1 | //1 | //1 | - | - | - | - | - | 1 applicability should be defined/tailored at each level for next lower level, depending on product heritage, engineering complexity and industrialization context. |
| 5.3.4b | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider whether other more detailed standards already cover this point for specific domains. |
| 5.3.4c | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider the specific need for maintenance and whether other more detailed standards already cover this point for specific domains. |
| 5.3.4d | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider both the specific need for exchange and whether other more detailed standards already cover this point for specific domains. |
| 5.3.4e | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider both the specific need for exchange and whether other more detailed standards already cover this point for specific domains. |
| 5.3.4f | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider whether other more detailed standards already cover this point for specific domains. |
| 5.3.4g | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.3.4h | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.1.1a | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.1.1b | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.1.1c | X | X | X1 | X | - | - | - | - | - | 1 not applicable in case of no lower level elements in scope of engineering responsibility of supplier. |
| 5.4.1.1d | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider whether other more detailed standards already cover this point for specific domains. |
| 5.4.1.1e | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider whether other more detailed standards already cover this point for specific domains. |
| 5.4.1.1f | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.1.2a | X | X | X | X | - | - | - | - | - |  |
| 5.4.1.2b | X | X | X1 | // | - | - | - | - | - | 1 not applicable in case of no lower level elements in scope of engineering responsibility of supplier. |
| 5.4.1.2c | X | X | X | X | - | - | - | - | - |  |
| 5.4.1.3a | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for subsystem level - see 22 applicability should be defined/tailored at each level for next lower level, depending on product heritage, engineering complexity and industrialization context. |
| 5.4.1.3b | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider the specific need and whether other more detailed standards already cover this point for specific domains. |
| 5.4.1.3c | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider both the specific need for exchange and whether other more detailed standards already cover this point for specific domains. |
| 5.4.1.3d | X | X1 | //2 | // | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.1.3e | X | //1 | //1 | //1 | - | - | - | - | - | 1 during tailoring, consider the specific need and whether other more detailed standards already cover this point for specific domains. |
| 5.4.1.3f | X | X1 | //2 | // | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.1.4a | X | X | //1 | // | - | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.1.4b | X | X | //1 | // | - | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.1.4c | - | X | X1 | // | - | - | - | - | - | 1 during tailoring, Annex P contents are also tailored to fit the need. |
| 5.4.2.1a | X | X | //1 | X | - | - | - | - | - | 1 during tailoring, other configuration management standards called by the business agreement when considered fully sufficient to suppress the applicability at this level. |
| 5.4.2.1b | X | X | X1 | X | - | - | - | - | - | 1 not applicable in case of no lower level elements in scope of engineering responsibility of supplier.  |
| 5.4.2.1c | X | X | //1 | X | - | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.4.2.2a | X | X | //1 | X | - | - | - | - | - | 1 during tailoring, other configuration management standards called by the business agreement when considered fully sufficient to suppress the applicability at this level. |
| 5.4.2.3a | X | X | //1 | X | - | - | - | - | - | 1 during tailoring, other configuration management standards called by the business agreement when considered fully sufficient to suppress the applicability at this level. |
| 5.5.1a | X | X | X | // | - | - | - | - | - |  |
| 5.5.2b | X | X | X | // | - | - | - | - | - |  |
| 5.5.2c | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.5.2d | X | X | X | X | - | - | - | - | - |   |
| 5.5.2f | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for subsystem level - see 22 applicability can be suppressed where adequately covered by other requirements e.g. ECSS-E-ST-10-03 and the TS and the SOW. |
| 5.6.1a | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.1f | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.1g | X | X | //2 | X1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.2a | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.3a | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.3b | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.3c | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.4a | X | X | X1 | X | - | - | - | - | - | 1 for ECSS-E-ST-10-06 Annex A also see pre-tailoring of 5.2.3.1b |
| 5.6.5a | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.5b | X | X1 | //2 | //2 | - | - | - | - | - | 1applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.7a | X | X | X | X | X | - | - | - | - |  |
| 5.6.7b | X | X | X | X | X | - | - | - | - |  |
| 5.6.7c | X | X | X | X | X | - | - | - | - |   |
| 5.6.7d | X | X | X | X  | X | - | - | - | - |   |
| 5.6.7e | X | X | X | X | X | - | - | - | - |   |
| 5.6.7f | X | X | X | X  | X | - | - | - | - |   |
| 5.6.7g | X | X | X | X | X | - | - | - | - |   |
| 5.6.8a | X | X | //1 | X | - | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.8c | X | X1 | //2 | //2 | - | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| 5.6.9a | X | X | //1 | X | - | - | - | - | - | 1 during tailoring, consider whether this requirement is superfluous to existing measures e.g. PA plan, RFD/RFW templates |
| 5.6.9b | X | X | //1 | X | - | - | - | - | - | 1 during tailoring, consider whether this requirement is superfluous to existing measures e.g. PA plan, RFD/RFW templates |
| 5.6.9c | X | X | //1 | X | - | - | - | - | - | 1 during tailoring, consider whether this requirement is superfluous to existing measures e.g. PA plan, RFD/RFW templates |
| Annex B | X | - | - | - | - | - | - | - | - |  |
| Annex C | X | //1 | - | //1 | - | - | - | - | - | 1 applicable at element level, for sub-system level - and applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| Annex D | X | //1 | //1 | //1 | - | - | - | - | - | 1 applicability should be defined/tailored at each level for next lower level, depending on product heritage, engineering complexity and industrialization context. |
| Annex E | X | X | //1 | X | //1 | - | - | - | - | 1 depending on product heritage, engineering complexity and industrialization context. |
| Annex F | X | X | //1 | X | //1 | - | - | - | - | 1 depending on product heritage, engineering complexity and industrialization context. |
| Annex G | X | X | //2 | X1 | //1 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| Annex H | X | X1 | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| Annex I | X | X | X | X | - | - | - | - | - |  |
| Annex J | X | X | X1 | X | X1 | - | - | - | - | 1 not applicable in case of no lower level elements in scope of engineering responsibility of supplier. |
| Annex K | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| Annex L | X | X | //2 | X1 | //2 | - | - | - | - | 1 applicable at element level, for sub-system level - see 22 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| Annex N | X | X | X1 | X | - | - | - | - | - | 1 not applicable in case of no lower level components in scope of engineering responsibility of supplier. |
| Annex O | X | X | //1 | X | - | - | - | - | - | 1 applicability defined/tailored at each level for next lower level depending on product heritage, engineering complexity and industrialisation context. |
| Annex P | - | X | // | X | - | - | - | - | - |  |

1. (informative)
System engineering documents delivery
per review

Scope of the Table A-1 is to indicate the relationship of documents associated to engineering activities which support project review objectives as specified in ECSS-M-ST-10.

1. This table constitutes a first indication for the data package content at various reviews. The full content of such data package is established as part of the business agreement, which also defines the delivery of the document between reviews.

The table lists the documents generated by the engineering organization necessary for the project reviews (identified by “X”), except for verification documents, which are identified in Table G-1 of ECSS-E-ST-10-02.

The various crosses in a row indicate the expected progressive increased levels of maturity versus reviews. The last cross in a row indicates that at that review the document is expected to be completed and finalized.

For the SEP, DDF and DJF, the line entries of these documents which are not identified by a “X” in the table are not expected to be delivered for the quoted review.

1. All documents, even when not marked as deliverables in Table A-1, are expected to be available and maintained under configuration management as per ECSS-M-ST-40 (e.g. to allow for backtracking in case of changes).

: System engineering deliverable documents

| Document title | ECSS document | DRD ref. | MDR | PRR | SRR | PDR | CDR | QR | AR | ORR | FRR | LRR | CRR | ELR | MCR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mission description document | ECSS-E-ST-10 | Annex B | X | **X** |  |  |  |  |  |  |  |  |  |  |  |
|   |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specifications |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preliminary technical requirements specification  | ECSS-E-ST-10-06 | Annex A | **X** | **X** |  |  |  |  |  |  |  |  |  |  |  |
| Technical requirements specification  | ECSS-E-ST-10-06 | Annex A |  |  | **X** |  |  |  |  |  |  |  |  |  |  |
| Interface requirements document | ECSS-E-ST-10-24  | Annex A |  | **X** | **X** | **X** |  |  |  |  |  |  |  |  |  |
|   |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
| System engineering plan | ECSS-E-ST-10 | Annex D | **X** | **X** | **X** | **X** | **X** | **X** | **X** |  |  |  |  |  |  |
| Technology plan | ECSS-E-ST-10 | Annex E |  | **X** | **X** | **X** |  |  |  |  |  |  |  |  |  |
| Technology Readiness Status List | ECSS-E-ST-10 | Annex E | **X** | **X** | **X** | **X** |  |  |  |  |  |  |  |  |  |
| Technology matrix | ECSS-E-ST-10 | Annex F |  | **X** | **X** | **X** |  |  |  |  |  |  |  |  |  |
| Verification plan | ECSS-E-ST-10-02 | Annex A |  | **X** | **X** | **X** | **X** | **X** | **X** |  |  |  |  |  |  |
| AIT QM/FM plan  | ECSS-E-ST-10-03 | Annex A |  |  |  | **X** | **X** | **X** | **X** |  |  |  |  |  |  |
| Space debris mitigation plan | ECSS-U-AS-10 |  | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** |  | **X** | **X** |
| Other related plans(as called in ECSS-E-ST-10 Annex D) | ECSS-E-ST-10 | Annex D |  | **X** | **X** | **X** | **X** | **X** | **X** |  |  |  |  |  |  |
| Coordinate system document | ECSS-E-ST-10-09 | Annex A |  | **X** | **X** | **X** | **X** | **X** |  |  |  |  |  |  |  |
|   |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design definition file | ECSS-E-ST-10 | Annex G |  | **X** | **X** | **X** | **X** | **X** |  |  |  |  |  |  |  |
| Function tree | ECSS-E-ST-10 | Annex H |  | **X** | **X** | **X** |  |  |  |  |  |  |  |  |  |
| Product tree | ECSS-M-ST-10 | Annex B |  | **X** | **X** | **X** |  |  |  |  |  |  |  |  |  |
| Specification tree | ECSS-E-ST-10 | Annex J |  |  | **X** | **X** |  |  |  |  |  |  |  |  |  |
| Technical budget | ECSS-E-ST-10 | Annex I |  | **X** | **X** | **X** | **X** | **X** | **X** |  |  |  |  |  |  |
| Preliminary technical requirements specifications for next lower level  | ECSS-E-ST-10-06 |  Annex A |  | **X** | **X** |  |  |  |  |  |  |  |  |  |  |
| Technical requirements specifications for next lower level  | ECSS-E-ST-10-06 | Annex A |  |  | **X** | **X** |  |  |  |  |  |  |  |  |  |
| Design definition file for next lower level  | ECSS-E-ST-10 | Annex G |  |  |  | **X** | **X** | **X** | **X** |  |  |  |  |  |  |
| Interface control document  | ECSS-E-ST-10-24 | Annex B |  |  | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** |  |  |  |
| Product User manual / User Manual | ECSS-E-ST-10 | Annex P |  |  |  |  | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** |
|  |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design justification file | ECSS-E-ST-10 | Annex K |  | **X** | **X** | **X** | **X** | **X** |  |  |  |  |  |  |  |
| Requirements traceability matrix w.r.t. next lower level | ECSS-E-ST-10 | Annex N |  | **X** | **X** | **X** |  |  |  |  |  |  |  |  |  |
| Requirement justification file | ECSS-E-ST-10 | Annex O | **X** | **X** | **X** | **X** |  |  |  |  |  |  |  |  |  |
| System concept report | ECSS-E-ST-10 | Annex C | **X** | **X** |  |  |  |  |  |  |  |  |  |  |  |
| Trade off reports | ECSS-E-ST-10 | Annex L | **X** | **X** | **X** | **X** | **X** |  |  |  |  |  |  |  |  |
| Verification control document | ECSS-E-ST-10-02 | Annex B |  | **X(1)** | **X(1)** | **X(1)** | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** |
| Test specification | ECSS-E-ST-10-03 | Annex B |  |  |  |  | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mathematical model description  | ECSS-E-ST-32 | Annex I |  |  | **X** | **X** | **X** | **X** |  |  |  |  |  |  |  |
| Correlation report | ECSS-E-ST-31 | Annex C |  |  |  |  | **X** | **X** |  |  |  |  |  |  |  |
| Test procedure | ECSS-E-ST-10-03 | Annex C |  |  |  |  | **X** | **X** | **X** | **X** | **X** |  |  |  |  |
| Test report | ECSS-E-ST-10-02 | Annex C |  |  |  |  | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** |
| Verification report | ECSS-E-ST-10-02 | Annex F |  |  |  |  | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** | **X** |
| Design justification file for next lower level  |  ECSS-E-ST-10 |  Annex K |  |  |  |  | **X** | **X** | **X** |  |  |  |  |  |  |
| Review of design report  | ECSS-E-ST-10-02 | Annex D |  |  |  |  | **X** | **X** |  |  |  |  |  |  |  |
| Inspection report | ECSS-E-ST-10-02 | Annex E |  |  |  |  | **X** | **X** | **X** |  |  |  |  |  |  |
| GSE specifications |   |   |  |  |  | **X** | **X** | **X** | **X** |  |  |  |  |  |  |
| GSE Data packages |   |   |  |  |  |  | **X** | **X** | **X** |  |  |  |  |  |  |
|   |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other documents |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|   |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
|   |   |   |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Note (1) : Document limited to the verification matrix |

1. (normative)
Mission description document (MDD) - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.3.1a.

* + 1. Purpose and objective

The objective of the mission description document (MDD) is to provide input for the later selection of the best concept meeting the mission statement (MS) in iteration with the preparation of the preliminary technical requirements specification (TS) (as defined in ECSS-E-ST-10-06 Annex A).

It is prepared in Phase 0 and Phase A for each possible concept, as indicated in requirement 5.3.1a.

Links and chronology amongst the MS, TS, MDD, system engineering plan, project management plan and system concept report are provided on the Figure B-1.

The MDD is produced by the top-level customer (as described in ECSS-S-ST-00 clause 6.1 and figure 6-1) (typically an Agency or other institutional actors) and defines a concept that aims at satisfying the preliminary technical requirements specification, and presents how the objectives, operation profile, major system events and capabilities, contingencies and performance standards are expected to be achieved.

For each mission concept, the MDD is a complete description of that concept. And to each MDD a SEP evaluating the related system engineering effort and a report evaluating the related programmatic aspect are associated.

The system concept report assesses the different concepts from a technical, programmatic and risk point of view, includes a trade-off including weighting factors which bears some management aspects, followed by a system concept selection.



: Relationship between documents

* 1. Expected response
		1. Scope and content

Introduction

The MDD shall contain a description of the purpose, objective, content and the reason prompting its preparation (e.g. logic, organization, process or procedure).

Applicable and reference documents

The MDD shall list the applicable and reference documents in support to the generation of the document, and include, as a minimum, the current preliminary technical requirements specification.

Preliminary technical requirements specification summary

The MDD shall provide a summary of the preliminary technical requirements specification objectives and list the design driving requirements, derived from the current initial specification.

Concept description

The MDD shall provide:

Overview of the concept

Mission analysis

System description, element by element

Description of how the system works in each mission phase

Performance drivers

Constraints

Main events

Operations scenarios

* 1. 1 to item 3: For example: For a spacecraft, its ground control segment, and a user segment, e.g.
		+ 1. Space Segment
		+ Payload
		+ Platform
		+ Launch Vehicle
		+ Orbit related aspects
		+ On-Board Data Handling
		+ Reference Operation Scenarios / Observation characteristics
		+ Operability / Autonomy Requirements
			1. Ground Segment
		+ Functional Requirements and Major Elements
		+ Monitoring and Control Segment
		+ Data Processing Segment
			1. User segment
		+ Functional Requirements and Major Elements
		+ Monitoring requirements
	2. 2 to item 4: For example: For a spacecraft, the following phase:
		+ Launch preparation
		+ Launch and Early Orbit Phase
		+ In Orbit Commissioning
		+ Nominal Operations
		+ Spacecraft Disposal

<<deleted and moved as item 4 into requirement B.2.1<4>a>>

Assessment of the performance

The MDD shall provide the

assessment against the current preliminary technical requirements specification requirements, and

identification of non-compliances, and their impact on the current preliminary technical requirements specification.

Identification of risk areas

The MDD shall provide the list of identified risk related to the concept, including as a minimum technology, contingencies handling, and programmatic aspects.

Conclusion

The MDD shall summarize the strengths and weaknesses of the concept.

* + 1. Special remarks

None.

1. (normative)
System concept report - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.3.3c.

* + 1. Purpose and objective

The system concept report describes the principal technical characteristics of alternative system concepts, relating to performance, architectures, driving technologies, interfaces, risk, their evaluation and classification, and later addresses the selected concept.

* 1. Expected response
		1. Scope and content

The system concept report shall be an instantiation of the trade-off report at system level in Phase 0 and Phase A of a project, conforming to ECSS-E-ST-10 Annex L.

1. The system concept report can be extended to Phase B where needed (e.g. late trade-offs).

This report shall address all technical (e.g. engineering disciplines), programmatic and related aspects relevant to the system.

Where relevant, specific e.g. discipline trade-off’s shall be performed, contributing to the system trade-off, each one being reported in a document conforming to ECSS-E-ST-10 Annex L.

* + 1. Special remarks

None.

1. (normative)
System engineering plan (SEP) - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirements 5.1a and 5.3.4a.

* + 1. Purpose and objective

The objective of the system engineering plan (SEP) is to define the approach, methods, procedures, resources and organization to co-ordinate and manage all technical activities necessary to specify, design, verify, operate and maintain a system or product in conformance with the customer’s requirements. In particular the SEP is established to fulfil the major technical project objectives, taking into account the defined project phases and milestones (as defined in ECSS-M-ST-10).

The SEP covers the full project lifecycle according to the scope of the business agreement. It is established for each item of the product tree (as defined in ECSS-M-ST-10).

It highlights the risks, the critical elements, the specified technologies, as well as potential commonalities, possibilities of reuse and standardization, and provides means for handling these issues.

The SEP is an element of the project management plan (as defined in ECSS-M-ST-10).

1. It is important to adapt the SEP content to the phase of the project, with more information on risk analysis and new technologies in early phases 0, A and B, and more information on verification and validation aspects in phases C, D.
	1. Expected response
		1. Scope and content

Introduction

The SEP shall contain a description of the purpose, objective, content and the reason prompting its preparation (e.g. programme or project reference and phase).

Applicable and reference documents

The SEP shall list the applicable and reference documents in support to the generation of the document.

The SEP shall include the references to the following applicable documents:

Business agreement

Project management plan, as defined in ECSS-M-ST-10 Annex A

Product assurance plan, as defined in ECSS-Q-ST-10 Annex A

Configuration management plan, as defined in ECSS-M-ST-40 Annex A

Production plan

Mission operations plan, as defined in ECSS-E-ST-70 Annex G

ILS plan.

Project overview

Project objectives and constraints

The SEP shall contain the following description of:

The project objective and the main elements that characterize the user’s need.

The objective of the system or product as established by the TS (as defined in the ECSS-E-ST-10-06 Annex A).

The main elements of the system architecture (i.e. first level elements of the architecture adopted for the system and identification of their reuse constraints).

The principal characteristics of the project lifecycle and the incremental development of the system (e.g. successive versions, progressive implementation of the functions of the system).

The main elements supporting the project lifecycle (e.g. ground support equipment, and facilities).

The organizational constraints impacting system engineering activities (e.g. the external and internal industrial organization (e.g. contractors, partners, suppliers, own company) constraints).

The list of the critical issues identified at the beginning of the project phase(s).

The list of national and international regulations.

The capacity for verification and validation of the product, taking into account the means available, e.g. for tests, analysis, or simulation.

Product evolution logic

The SEP shall detail the incremental development of the system:

progressive implementation of system functionalities,

identification of possible successive versions,

objectives and strategy for the implementation of the successive versions.

Project phase(s), reviews and planning

The SEP shall provide an implementation and schedule of the system engineering activities and identify for the considered phase(s), as a minimum:

the main project milestones driving the system engineering process,

the phase(s) of the project lifecycle and the main reviews in accordance to project management plan.

The SEP shall provide dates of milestones or the duration of phases and the critical path according to the project master schedule.

Procurement approach

The SEP shall describe the strategy for acquisition of the items of the system or products defined in the product tree (e.g. make or buy, product line, incremental development).

Initial critical issues

The SEP shall list the critical issues identified at the beginning of the project phase(s) covered in the SEP (e.g. any specific issues, problems, critical subjects, which require dedicated attention, investigation, action and planning).

System design approach

System engineering inputs

The SEP shall list the driving inputs for the system engineering activities described and defined by the:

business agreement,

outputs from previous phase(s) or expected under the heading of activities which are not controlled within the context of this SEP (e.g. data provided by the customer, data coming from other projects, upstream or predevelopment studies, product lines),

project management plan, product assurance plan, risk management plan, and configuration and documentation management plans.

The SEP shall list the external means and facilities (e.g. equipment, software, and premises) made available by the customer or by any other entity external to the supplier that is responsible of this SEP, and, for each identified mean or facility, identify the applicable interface requirements (e.g. interface control documentation) as well as the authority in charge of it.

The SEP shall list the internal means and facilities (e.g. equipment, software, and premises) made available by the organization in charge of the development of the system or product.

The SEP shall contain the Coordinate System Document (as defined in ECSS-E-ST-10-09 Annex A).

The SEP shall define the units system to be used in the project.

System engineering outputs

The SEP shall list the specified system engineering outputs as defined in ECSS-E-ST-10 clause 6 for the specific project phase(s) covered in the SEP.

1. An overview of document delivery is given in Annex A.

The SEP shall describe the following:

The strategy for the system engineering activities in line with the guidelines addressed by the management plan. In particular, identifying intermediate technical events for each phase in compliance with the master program schedule.

The system design activities, with their objectives and major outputs according to the phase.

The major engineering activities for each intermediate technical events, showing their mutual interactions and their relationships with the principal milestones (i.e. internal or contractual) of the project.

The model philosophy (as defined in ECSS-E-ST-10-02 clause 4.2.5) in terms of number and characterization of models, from system to the requested lower level, necessary to achieve a high confidence in the product verification.

The margin policy according to project phase, product category and maturity level.

The SEP shall also describe

the method(s) and process(es) considered for the engineering activities (e.g. concurrent engineering, value analysis, or iteration cycle),

the interrelation between the different engineering disciplines and other project activities (e.g. production, quality assurance, and operations and logistics),

the interaction with other actors (e.g. customer and suppliers),

the consistency and coherency of simultaneous activities (e.g. performed in parallel),

which and how, control activities are implemented,

Assessment of potential COTS usage

In the case of a system incremental evolution, the SEP shall describe the design strategy for the:

development of the initial release of the product,

development, the verification of subsequent releases and their deployment,

introduction of new technologies,

tools and methods used for analysis,

control of the evolutions for each release.

System engineering team responsibilities and organization

The SEP shall contain the following:

Definition of the entities participating in the system engineering activities and the corresponding functions according to the project management plan.

Identification of key engineering roles and responsibilities (e.g. system engineers, disciplines engineers, and technical managers).

Description of the co-operative work amongst the different teams participating in the system design.

System engineering coordination

The SEP shall describe the external and internal coordination in line with the project management plan.

Implementation and related plans

System engineering tasks description

<5.1.1> System engineering process description

The SEP shall describe the system engineering process tailored to the specifics of the considered project, and identify all the system engineering tasks to be implemented from the starting conditions (e.g. kick-off) to the closing event (e.g. review), their relationship, and their interfaces with other actors of the project, and identify and describe any existing iteration within the process.

For each task, the input information and their origin, the document(s) delivered (i.e. expected output) and their destination, the system engineering function(s) performed and the contribution of other actors shall be identified.

<5.1.2> Engineering disciplines integration

The SEP shall address the following activities that concern the different engineering disciplines, recalling the relevant applicable standards and ancillary dedicated plans that are considered integral part of this SEP.

The SEP shall define the process and control to be put in place to meet requirements for the thermal, structures, mechanisms, environmental control and life support, propulsion, pyrotechnics, mechanical parts, and materials functions and interfaces.

1. These requirements refer to Mechanical engineering as defined in ECSS-E-ST-3x series of standards.

The SEP shall define the process and control to be put in place to meet requirements for electrical and electronic engineering, covering all electrical and electronic aspects of the relevant space product, including functions such as power generation, storage, conversion and distribution, and optical, avionics and microwave domains, electromagnetic compatibility, and electrical interfaces.

1. These requirements refer to Electrical and electronic engineering as defined in ECSS-E-ST-20.

The SEP shall define process and control to be put in place to meet requirements for software engineering, covering, amongst others, flight and ground software, checkout software and simulation software.

1. These requirements refer to Software engineering as defined in ECSS-E-ST-40.

The SEP shall define process and control to be put in place to meet requirements for communication engineering, covering, amongst others, spacecraft-to-ground, spacecraft-to-spacecraft, ground-to-ground and on-board communications links.

* 1. 1 These requirements refer for Communications engineering as defined in ECSS-E-ST-50.
	2. 2 It includes aspects such link budgets, data management, RF, audio and video communications and protocols.

The SEP shall define process and control to be put in place to meet requirements for control engineering, covering, amongst others, AOCS, robotics, rendez-vous and docking.

The SEP shall define the process and control to be put in place to meet requirements specifying natural environment for all space regimes (e.g. debris regulations, or planetary contamination protection) and general models and rules for determining the local induced environment

1. These requirements refer to Space environment as defined in ECSS-E-ST-10-04.

The SEP shall define the process and control to be put in place to meet requirements for the approach, methods, procedures, organization and resources to be implemented to ensure proper technical interfaces between system engineering and production.

The SEP shall define the process and control to be put in place to meet requirements of operations of the space segment, covering, amongst others:

mission operation definition and preparation,

mission and trajectory analysis, and

operability analysis (e.g. autonomy, operational scenario, nominal and non-nominal modes, failure detection isolation and recovery).

1. These requirements refer to Operations engineering as defined in ECSS-E-ST-70.

The SEP shall define the process and control to be put in place to meet requirements for ground and in-orbit logistics and maintenance, addressing, amongst others, technical activities, related engineering standards, methods and analyses to be performed to ensure that the development of space systems (i.e. manned and unmanned) properly takes into account and integrates the supportability and support aspects for the whole life cycle.

The SEP shall define the process and control to be put in place to meet requirements for human activities and environments associated with space systems.

1. These requirements refer to Human factors engineering as defined in ECSS-E-ST-10-11.

The SEP shall define process and control to be put in place to meet requirements for implementation of design selections relating to humans for any item with associated human interface, including computer based system and equipment.

<5.1.3> Work package

The SEP shall define and describe the work package(s) for the relevant engineering tasks, which are maintained in the work breakdown structure.

Related plans

When the SEP includes sub-plans covering parts of system engineering activities, these sub-plans shall be annexed to the SEP.

The SEP shall identify the other plans relevant to system engineering function activity belonging to the following categories:

Programmatic plans

Verification plans

Engineering discipline plans

Operations plans

* 1. 1 Some of these plans can be integrated in the SEP in the early phases of a project.
	2. 2 Note to item 1: Examples of programmatic plans are: the SEP plans of sub-products constituting the system or product, Industrial procurement plan, risk management plan, off-the-shelf plan (see ECSS-Q-ST-20-10).
	3. 3 Notes to item 2:
		+ Examples of verification plans are: verification plan (VP), AIT plan, AIV plan and technology plan, system calibration plan, Security Aspects Verification Plan. Some of those DRDs are defined in this document, in ECSS-E-ST-10-02 or ECSS-E-ST-10-03.
		+ VP and AIT plans can be integral parts of the SEP, or rolled out separately (without overlap), or combined as the AIV Plan which can also be rolled out separately. However, the existence of the AIV Plan excludes independent VP and AIT plans.
	4. 4 Note to item 3: Examples of engineering discipline plans are: Fracture Control Plan (see ECSS-E-ST-32), Micro-gravity Control Plan, Electro-Magnetic Compatibility Plan (see ECSS-E-ST-20), Audible Noise Control Plan, Radio Frequency Plan, Alignment Requirements and Control Plan, System Performance Simulations Plan, Software Development Plan, Orbital Debris Mitigation Plan and Disposal Plan (as defined in ISO 24113:2011), Planetary protection Plan, Cleanliness and Contamination Control Plan.
	5. 5 Note to item 4: Examples of operation plans are: launch site operations and logistics plan, system commissioning and operation support plan.

The SEP shall describe the constraints and the interactions impacting the system engineering activities derived from the analysis of the plans identified as relevant in D.2.1<5.2>b.

System engineering methods, tools and models

The SEP shall list and briefly describe the methods, tools, and data models that the system engineering team uses in performing their tasks.

In relation to requirements traceability and demonstration of verification (compliance with requirements, VCD), the specific methods and tools shall be described (including interfaces to next lower level suppliers), and reuse of elements (e.g. COTS) identified.

Critical issues

The SEP shall describe any specific issues, problems requiring dedicated attention, investigations or actions during the current phase and identify risks, and risk mitigation measures.

System engineering for the following phase(s)

The SEP shall introduce the system engineering activities, to be conducted during subsequent phase(s) of the project, and as a minimum, list any identified critical issue and risk to be mitigated during the subsequent phase(s).

* + 1. Special remarks

None.

1. (normative)
Technology plan (TP) - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.6.7b.

* + 1. Purpose and objective

The objective of the technology plan (TP) is to define the approach, methods, procedures, resources and organization to evaluate the ability of a critical technology to meet the intended requirements. Also, the objective of this plan is to ensure effective preparation of the technologies necessary for a timely implementation of the system, in accordance to the requirements imposed by the specific characteristics of the relevant product.

It is established for each item of the function tree (as defined in ECSS-E-ST-10, Annex H), and highlights the technical requirements, and the critical technology of each item.

The TP is part of the system engineering plan (SEP) (as defined in ECSS-E-ST-10, Annex D).

* 1. Expected response
		1. Scope and content

Introduction

The TP shall contain a description of the purpose, objective, content and the reason prompting its preparation (e.g. programme or project reference and phase).

Applicable and reference documents

The TP shall list the applicable and reference documents in support to the generation of the document and include the reference to the following applicable documents:

SEP

Technology matrix (as defined in ECSS-E-ST-10, Annex F)

Function tree

Specification tree.

Project overview

The TP shall contain a summary of the main aspects of:

project objectives and constraints (i.e. section <3.1> of ECSS-E-ST-10, Annex D "SEP DRD");

product evolution logic (i.e. section <<3.2> of ECSS-E-ST-10, Annex D "SEP DRD");

project phase(s), reviews and planning (i.e. section <3.3> of ECSS-E-ST-10, Annex D "SEP DRD"),

Procurement approach (i.e. section <3.4> of ECSS-E-ST-10, Annex D "SEP DRD")

Tasks description

TP expected outputs

The TP expected output shall be an answer concerning the possibility for using the identified or needed technology to perform a function.

TP inputs

For each system function, the TP input shall be:

technical requirements,

the selected technology or technological element and its TRL,

the list of the identified project risks and critical aspects, and

the schedule for Engineering activities.

TP tasks

The TP shall establish and describe the necessary activities to complete the acquisition of each technology or technological element, including verification strategies and methods, and the link to product assurance aspects.

The TP shall define the model philosophy for each technology or technological element, based on an assessment on the maturity status and on the criticality of the technology with respect to functions' requirements.

The TP shall describe the technology development activities, their required or possible interrelations and timings, as necessary for the satisfactory acquisition of the technologies and procurement of the technological elements.

The TP shall identify technical milestones, showing their interactions and relationships with the SEP milestones.

Responsibilities and organization

The TP shall contain the following:

definition of the entities participating in the engineering activities and the corresponding functions according to the SEP;

identification of key engineering roles and responsibilities for each technology or technological element.

TP interfaces

The TP shall describe the external and internal interfaces in conformance to the SEP.

Technology issues

The TP shall describe, for any identified technology risk and related critical aspects for the project, the specific actions taken for risk mitigation based on identified technology readiness level (TRL).

The TP shall include the TRSL by using the template in Figure E-1, and listing:

the critical function, with reference to the Function tree,

the name of the technology or element(s) implementing such a function,

current declared and verified TRL, as defined in ECSS-E-AS-11,

reference to the TRA report confirming the declared TRL,

date of the report,

key points to support TRL declared in column [3],

forward plan for TRL evaluation, indicating the target TRL, the phase or date at which such target TRL is expected, and status of the planning to achieve the target TRL,

during phases A & B, indication whether or not the technology/element is a candidate for the CIL.

* 1. 1 The key point in column [6] are normally few lines summarizing the TRL assessment report referenced in column [4].
	2. 2 At the end of Phase B, the TRSL is introduced as part of the CIL.



: TRSL template

* + 1. Special remarks

The content of the TP may be merged with the content of the SEP.

The TP shall introduce the related activities, to be conducted during all phase(s) of the project.

1. (normative)
Technology matrix - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.6.7a.

* + 1. Purpose and objective

The technology matrix presents, for each technical requirement/function, the list of technologies or technological elements, which have the potential to meet this requirement. It summarizes candidate technologies per individual requirement.

The technology matrix is part of the Design Justification File (as defined in ECSS-E-ST-10, Annex K). It is the basic document for presenting all identified potential technologies for the product.

* 1. Expected response
		1. Scope and content

Introduction

The technology matrix shall contain a description of the purpose, objective, content and the reason prompting its preparation.

Applicable and reference documents

The technology matrix shall list the applicable and reference documents in support to the generation of the document and include the reference to the following applicable documents:

Specification tree

Preliminary technical requirements specifications

Function tree.

List of technical requirements/functions

The technology matrix shall list the system technical requirements/functions as defined in the functional architecture and its corresponding function tree, and their associated preliminary TS.

List of potential technologies for each technical requirement/function

The technology matrix shall list the system technical requirements/functions and for each, a potential technology or technological element.

1. Sources to identify potential technologies are technology watch, corporate technology plan, or research and development programme.

For each technology or technological element, the following information shall be listed:

index of technology readiness and maturity as defined in Table 4-2 of ECSS-E-AS-11;

proof of company's maturity concerning the knowledge and expertise of the technology, including a description of the necessary technology acquisition activities;

identification of potential risks, e.g. technology availability, programmatic and financial aspects.

Ranking of the potential technologies for each function

The technology matrix shall propose a ranking of the potential technology or technological element for each system requirement/ function.

Conclusion

The technology matrix shall provide, for each system requirement/function, the selected technology or technological element, a list of the identified project risks and critical aspects, and an identified back-up technological solution.

* + 1. Special remarks

None.

1. (normative)
Design definition file (DDF) - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirements 5.3.1c, 5.3.1f, 5.4.1.1b and 5.4.1.4a.

* + 1. Purpose and objective

The objective of the design definition file (DDF) is to establish the technical definition of a system or product that complies with its technical requirements specification (as defined in ECSS-E-ST-10-06 Annex A).

The design definition file is a basic structure referring to all information relative to the functional and physical architectures and characteristics of a system or product, necessary for its identification, manufacturing, utilization, support, configuration management and removal from service.

The DDF is a collection of all documentation that establishes the system or product characteristics such as lower level technical specifications, design and interface description, drawings, electrical schematics, specified constraints (e.g. on materials, manufacturing, processes, and logistic).

It details the as-designed configuration baseline (as defined in ECSS-M-ST-40) of the system or product and is built up and updated under the responsibility of the team in charge of system engineering. It is the technical baseline for the production, assembly, integration and test, operations and maintenance of the product.

The DDF, the technical requirements specification, and the Design Justification File (as defined in ECSS-E-ST-10 Annex K) are the basic documents used for product development. They are interrelated such as:

* the design (i.e. DDF) is the response to the requirements stated in the TS,
* the justification (i.e. DJF) demonstrates the conformance of the design (i.e. DDF) to the requirements stated in the TS.
1. The DDF is a logical file covering all TS disciplines required for the considered system. In general, the elements of the DDF are “rolled out” as separate documents.
	1. Expected response
		1. Scope and content

Introduction

The DDF shall contain a description of the purpose, objective and the reason prompting its preparation (e.g. programme or project reference and phase).

Applicable and reference documents

The DDF shall contain the list of applicable and reference documents, used in support to the generation of the document.

The DDF shall include the reference to the following applicable documents:

Business agreement

System engineering plan (as defined in ECSS-E-ST-10 Annex D)

Coordinate system document (as defined in ECSS-E-ST-10-09 Annex A)

Technical requirements specification (TS)

Product assurance plan

Configuration management plan (as defined in ECSS-M-ST-40)

Configuration status report (as defined in ECSS-M-ST-40).

The DDF shall refer to DDFs of next higher and lower level products.

Summary of the project and technical requirements

The DDF shall contain a brief description of the product and of the main technical requirements throughout its life cycle phases (e.g. launch, deployed, operations, end-of-life).

The DDF shall contain the description of the system or product design documentation, based on the product tree (as defined in ECSS-M-ST-10) and also include, or refer to, the specifications tree (as defined in ECSS-E-ST-10 Annex J).

The DDF of a system shall contain at least the technical requirements specifications of the elements in which the system is broken down

Functional description

Functional architecture

The DDF shall contain the description of the functional architecture of the system or product i.e. the arrangement of functions, their sub-functions and interfaces (internal and external), and the performance requirements to satisfy the requirements of the TS.

The DDF shall present the data and their flow interchanged between the different functions, the conditions for control, and the execution sequencing for the different operational modes and states.

1. The Functional Architecture is an output of the functional analysis process (as defined in ECSS-E-ST-10 clause 5.3.1a)

Function tree

The DDF shall contain or refer to the system or product function tree, the latter conforming to ECSS-E-ST-10 Annex H.

Description of functional chains

The DDF shall describe the functional chains that contribute to the realization of the functional requirements of the TS and their contributing functions, consider the different operational modes and states, and indicate the selected physical implementation for each of the functions.

Physical description

Physical architecture

The DDF shall contain the description of physical architecture of the system or product i.e. the arrangement of elements, their decomposition, interfaces (internal and external), and physical constraints, which form the basis of a system or product design to satisfy the functional architecture and the technical requirements.

1. The Physical Architecture is an output of the preliminary design definition activities (as defined in clause 5.3.1f).

Product tree

The DDF shall contain or refer to the product tree of the system or product, as defined in ECSS-M-ST-10 Annex B.

1. The Product Tree is a breakdown of the Physical Architecture.

Specification tree

The DDF shall contain or refer to the specification tree of the system or product, the latter conforming to Annex J.

Description of elements of the physical architecture

The DDF shall provide

the nomenclature of the system or product,

the overall system or product drawings,

for each element of the system, the description of the different constituents of the physical architecture,

the characteristics of the respective elements,

their configuration management identifier (e.g. hardware part number, software version number, drawings number, electrical schematics numbers).

The DDF shall reference any documentation containing detailed technical descriptions and associated matrices to ensure overall consistency and completeness.

Description of interfaces

The DDF shall describe the physical and functional characteristics of the internal and external interfaces of the system and refer to the relevant IRD and ICD, conforming to Annex A of ECSS-E-ST-10-24.

System technical budget, margins and deviations

The DDF shall present the budget allocation of the technical parameters of the system and provide the actual status of the system margins, and deviations.

The DDF shall contain or refer to the system or product technical budget, the latter conforming to Annex I.

System design constraints

Constraints for production

The DDF shall present the constraints induced by the system or product design definition on the production activities e.g. operational allowable envelopes, restrictions on assembling sequences, procedures and testing modes, exclusion zones, manufacturing environmental conditions, and conditions for procurement.

Constraints for operation

The DDF shall present the constraints induced by the system or product design definition on the implementation of the operations e.g. operational allowable envelopes, restrictions on operating modes, and exclusion zones.

Constraints for transportation and storage

The DDF shall present the constraints induced by the system or product design definition on the transportation activities and during the periods of storage of the product e.g. allowable envelopes, restrictions on transportation and storage, exclusion zones, packaging, shock levels, temperature environments, humidity, cleanliness, regulations, and dangerous materials.

Constraints for maintainability

The DDF shall present the constraints induced by the system or product design definition on the maintenance activities and procedures e.g. operational allowable envelopes, accessibility, tooling, support materials, parts availability, and deliveries.

Engineering data repository

The DDF shall contain the information on the system or product engineering data repository that contains the complete set of design parameters, or a reference to it.

1. Information about the set of design parameters is provided in ECSS-E-TM-10-10.

Conclusion

The DDF shall list and summarize all deviations of the design with respect to the technical specifications and constraints induced by the system or product design definition.

* + 1. Special remarks

None.

1. (normative)
Function tree - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.3.1b.

* + 1. Purpose and objective

The objective of the function tree document is to describe the hierarchical decomposition of a system or product capabilities into successive level of functions and sub-functions.

The function tree is part of the Design Definition File. It is the starting point for the establishment of the Product Tree (as defined in ECSS-M-ST-10) and is a basic structure to establish preliminary technical requirements specification(s) (as defined in ECSS-E-ST-10-06 Annex A).

* 1. Expected response
		1. Scope and content

Introduction

The function tree document shall contain a description of the purpose, objective and the reason prompting its preparation.

Applicable and reference documents

The function tree document shall contain the list of applicable and reference documents, used in support to the generation of the document.

Project summary and user’s need presentation

The function tree document shall contain a brief description of the project and of the key user’s needs.

Tree structure

The function tree document shall provide the complete list of functions that the system or product shall perform, and contain a graphical representation where the main specified function(s) (i.e. at the top level of the tree) is/are decomposed into lower level functions.

When recurrent products from previous space projects are used, the product’s functions shall be identified in the tree structure, and addition, every necessary function by the system or product that is not under the supplier’s responsibility identified in the tree structure.

* + 1. Special remarks

The function tree shall be coherent with other functional descriptions of the system or product (e.g. functional architecture, functional block diagram).

1. (normative)
Technical budget - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.4.1.2a.

* + 1. Purpose and objective

The technical budget defines for each key engineering parameter of a system or product, the nature of this parameter, its measure, specified value, metrics requirements and current actual or computed value and assessed value.

The technical budget is part of the Design Definition File (as defined in ECSS-E-ST-10 Annex G). It is the basic document for providing adequate control of the key engineering parameter properties to meet the system or product technical requirements.

* 1. Expected response
		1. Scope and content

Introduction

The technical budget shall contain a description of the purpose, objective, content and the reason prompting its preparation.

Applicable and reference documents

The technical budget shall list the applicable and reference documents in support to the generation of the document.

List of selected key engineering parameters

The technical budget shall:

list the selected key engineering parameters (those specified by the customer and those selected by the supplier),

present the reason for their selection,

identify for each key engineering parameters the stages of maturity of the design.

present the related margin policy for these parameters.

1. to item 1: Examples of key engineering parameters are mass, communication links, power, and on-board computer memory capacity.

Assessment of key engineering parameters

For each key engineering parameter, the technical budget shall:

provide the specified value of the parameter,

provide the supplier’s margin resulting of the allocation of the parameter to the lower level products,

provide the specified values with the reference to the relevant technical requirement of the lower level products,

propose a specific program to conform to the specified value in case of nonconformance,

contain a chart of parameter history that presents the evolution of the parameter’s value at the different design maturity steps for which the evaluation of the parameter is performed,

list the documentation sources (e.g. analysis report and verification report).

Conclusion

The technical budget shall contain a conclusion that identifies the key engineering parameters having a negative margin, and identify for each of those:

the impact on the technical requirements and the associated risk for the project, and

the specific program to conform to the specified value and for project risk mitigation.

* + 1. Special remarks

None.

1. (normative)
Specification tree - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.2.3.1c.

* + 1. Purpose and objective

The objective of the specification tree document is to define the hierarchical relationship of all technical requirements specifications for the different elements of a system or product.

The specification tree is part of the Design Definition File (as defined in ECSS-E-ST-10 Annex G). It is the basic structure to perform the system or product requirements traceability and to manage their internal interfaces.

* 1. Expected response
		1. Scope and content

Introduction

The specification tree document shall contain a description of the purpose, objective and the reason prompting its preparation.

Applicable and reference documents

The specification tree document shall contain the list of applicable and reference documents, used in support to the generation of the document.

Project summary and user’s need presentation

The specification tree document shall contain a brief description of the project and the key user’s needs.

Tree structure

The specification tree document shall provide the complete list of specifications defining the system or product, and contain a graphical representation where the system or product specification (i.e. at the top level of the tree) is decomposed into lower level product specifications.

When recurrent products from previous space projects are used, their specification shall be identified in the tree structure, and in addition, for every necessary product that is not under the supplier’s responsibility, their specification shall be identified in the tree structure.

* + 1. Special remarks

The specification tree shall be coherent with the product tree (see ECSS-M-ST-10) and the business agreement structure (see ECSS-M-ST-60).

1. (normative)
Design justification file (DJF) - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirements 5.3.1d, 5.3.1g, 5.3.1h and 5.4.1.4b.

* + 1. Purpose and objective

The objective of the design justification file (DJF) is to present the rationale for the selection of the design solution, and to demonstrate that the design meets the baseline requirements.

The DJF is progressively prepared during the detailed design process and according to the system engineering plan (SEP) (as defined in ECSS-E-ST-10 Annex D), and serves the following purposes:

* it provides access to the necessary justification information,
* it presents a review of all acquired justifications,
* it constitutes a basic element for decision taking concerning the product definition qualification.

The DJF together with the Design Definition File (DDF) (as defined in Annex G) and the technical requirements specification (TS) (as defined in ECSS-E-ST-10-06 Annex A) are the basic documents used for the development of the product. These documents are used to monitor the evolution of the design.

The DJF is a collection of all documentation that traces the evolution of the design during the development and maintenance of the product. The DJF is updated according to the evolution of the DDF, in accordance with the above-mentioned objectives.

The DJF provides also access to coherent and substantiated information which can be used to support decision-making in the analysis of change requests for the management of non conformances.

The DJF contains results obtained during the evolution of the design as a consequence of the activities performed along the design process:

* Analysis and trade-off reports concerning the evaluation of alternative design solutions and the justification of the choice.
* All results obtained during the verification of the design as a consequence of the activities performed along the verification process.
* Test Reports on engineering model, structural and thermal model and qualification model (e.g. Protoflight Models).
1. The DJF is a logical file covering all technical disciplines required for the considered system. In general, the elements of the DJF are “rolled out” as separate documents.
	1. Expected response
		1. Scope and content

Introduction

The DJF shall contain a description of the purpose, objective, content and the reason prompting its preparation.

Applicable and reference documents

The DJF shall list the applicable and reference documents in support to its generation.

The applicable document list shall contain the reference to the relevant product specifications, and the relevant DDF and system engineering plan.

The reference document list shall contain the reference to:

Trade-Off-Reports, as defined Annex L.

Analysis Reports (e.g. requirements allocation analysis, functional analysis).

Requirements Traceability Matrix, as defined in Annex N (with link to analysis).

Verification Control Document

All verification documentation, such as:

Analysis Reports (e.g. reports w.r.t. qualification aspects)

Test Reports

ROD Reports

Inspection Reports

Verification Reports

Design description

The DJF shall contain a description of the expected product, its intended mission, architecture and design, and the functioning principles on which it is based.

The DJF shall define the requirement criteria levels for qualification and acceptance verification of the product.

Design Justification File Synthesis

The DJF shall present status of the design justification in response to requirements, with emphasis on the driving requirements that have a big impact on the system design, production and maintainability (see also K.2.1<8.2.4>a.)

The DJF shall present an overall system qualification status synthesis, including:

the list of requirements which have not been met (e.g. nonconformances), including proposed actions,

the list of all critical points, and how criticalities have been or are intended to be resolved,

the identification of requirements which have not been justified yet, and associated risks analysis, with emphasis on those that can have an impact at system level.

Justification of the Functional Architecture

The DJF shall contain the demonstration that all requirements of the preliminary technical requirements specification are allocated to functional blocks of the system functional architecture.

Where requirements assigned to functional blocks do not have their origin within any of the customer preliminary technical specifications, these requirements shall be justified.

Justification of the Physical Architecture

The DJF shall contain the demonstration that the system design conforms to the requirements of the technical specification, and identify products which are reused (e.g. COTS).

The DJF shall also provide the justification for the choice of architectural elements at the next lower level, or lower levels in case of system critical elements.

Where requirements do not have their origin within any of the upper level technical specifications, these shall be justified.

Development activities and synthesis of development results

The DJF shall present the development activities (e.g. assessments, analyses, tests, and trade-offs) and the design drivers, which lead to and justify the design as defined in the DDF, in line with the development approach identified in the SEP.

The justification shall concern all the engineering disciplines contributing to design and development of the product (including its operational modes and scenarios).

The DJF shall include the status of DJF of lower level products.

1. Activities related to verification are dealt with in section K.2.1<8>.

For the system and each discipline, following information shall be produced:

Activity inputs, such as requirements, operational modes, assumptions, analysis cases, boundary conditions, model descriptions and limitations.

Activity results, such as

raw results,

evaluation of results,

evaluation of margins with respect to the technical requirements contained in the TS,

identification of any marginal areas.

Activity synthesis, such as

evidence of compliance to the technical requirements contained in the TS,

list of technical requirements which have not been met, including proposed actions,

list of all critical points, and how criticalities have been or are intended to be resolved,

identification of aspects of the design, which are not yet justified, and assessment of inherent risks.

The DJF shall reference the requirements traceability matrix, e.g. w.r.t. building up the justification of a considered system top level requirements in terms of the various elements contributing to it, including where relevant contribution from other disciplines (e.g. pointing as a function of thermal, structures, and AOCS).

Verification activities and synthesis of results

 Verification plan

The DJF shall integrate or refer to the document that conforms to the verification plan DRD defined in ECSS-E-ST-10-02 Annex A.

1. The verification activities are detailed in the Verification Plan (VP), which also contains the justification of the verification strategy (as defined in ECSS-E-ST-10-02).

Qualification verification and synthesis of results

<8.2.1> Qualification evidence

The DJF shall present the evidence of the qualification of the design in conformance to the applicable technical requirements and proper qualification margins.

1. This is done in line with the qualification approach identified in the VP.

The DJF shall cover the system and all disciplines relevant to the product in all its operational modes and scenarios, addressing all applicable technical requirements and proper qualification margins.

* 1. 1 This is done in line with the system verification matrix.
	2. 2 The formal compliance with the qualification requirements is recorded in the VCD, together with references to the close-out documents.

<8.2.2> Implementation of the qualification plan

The DJF shall present the implementation of the qualification plan and the status thereof, addressing the detailed definition of qualification activities (e.g. analysis, test, ROD, and inspection), including the detailed definition of the tests, the prediction of expected test results, test success criteria, test specifications, and model validations.

1. Details on test specifications are provided in ECSS-E-ST-10-03 Annex B.

<8.2.3> Validation of models

The DJF shall contain all evidence (e.g. analyses, test results, and model descriptions and correlations) regarding the suitability and validation of all models used for the analysis of the system.

<8.2.4> Requirements status log

The DJF shall include a requirement status log addressing each requirement in turn, and including the

reference to relevant elements of the verification plan,

synthesis of the justifications acquired, calling up references to the supporting activities and evidence (e.g. Technical Notes listed in section K.2.1<4>),

list of justifications to be acquired and related activities,

conclusion / action flag.

<8.2.5> Manufacturing process status log

The DJF shall include a requirement status log, addressing design relevant aspects of manufacturing processes, and recording their characteristics in regard to qualification.

Acceptance verification

The DJF shall present the implementation of the acceptance verification and the status thereof, addressing the detailed definition of acceptance activities (e.g. inspection, test, analysis), including the detailed definition of the tests, the prediction of expected test results, test success criteria, and test specifications.

1. Details on test specifications are provided in ECSS-E-ST-10-03 Annex B.

The DJF shall cover the system and all disciplines relevant to the product, addressing all acceptance verification activities in line with the system verification Plan (VP).

Justification of System Technical Budgets and Margins

The DJF shall present a synthesis of all technical budgets and margins for specific parameters according to the functional and physical architectures.

1. For technical budgets and margins, see ECSS-E-ST-10 Annex I.

Justification of Constraints imposed by the System Design

Design constraints on the production

The DJF shall present the justification of constraints induced by the system or product design definition on the production activities e.g. operational allowable envelopes, restrictions on assembling sequences, procedures and testing modes, exclusion zones, manufacturing environmental conditions, and conditions for procurement.

System design constraints for operation

The DJF shall present the justification of constraints induced by the system or product design definition on the implementation of the operations e.g. operational allowable envelopes, restrictions on operating modes, and exclusion zones.

System design constraints for transportation and storage

The DJF shall present the justification of constraints induced by the system or product design definition on the transportation activities and during the periods of storage of the product e.g. allowable envelopes, restrictions on transportation and storage, exclusion zones, packaging, shock levels, temperature environments, humidity, cleanliness, regulations, and dangerous materials.

System design constraints for maintainability

The DJF shall present the justification of constraints induced by the system or product design definition on the maintenance activities and procedures e.g. operational allowable envelopes, accessibility, tooling, support materials, parts availability, and deliveries.

Constituent documents

The DJF shall integrate or refer to the documents that conform to the:

ECSS-E-ST-10 Annex L, Trade-Off-Report - DRD

ECSS-E-ST-10 Annex Q, Analysis Report - DRD

ECSS-E-ST-10 Annex O, Requirement Justification File - DRD

ECSS-E-ST-10 Annex N, Requirements Traceability Matrix - DRD

ECSS-E-ST-10-02 Annex B, Verification Control Document - DRD

ECSS-E-ST-10-02 Annex C, Test Report - DRD

ECSS-E-ST-10-02 Annex D, Review Of Design Report - DRD

ECSS-E-ST-10-02 Annex E, Inspection Report - DRD

ECSS-E-ST-10-02 Annex F, Verification Report - DRD

The DJF shall include or refer to the DJF of lower level elements of the product.

* + 1. Special remarks

None.

1. (normative)
Trade-off report - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.3.3b.

* + 1. Purpose and objective

The Trade-off report provides the system-engineering point of view on alternative design solutions, an evaluation and a classification of the alternative design solutions, and the justification of their ranking.

* 1. Expected response
		1. Scope and content

Introduction

The trade-off report shall contain a description of the purpose, objective, content and the reason prompting its preparation.

Applicable and reference documents

The trade-off report shall list the applicable and reference documents in support to the generation of the document and include the reference to the following applicable documents:

Mission description document, if relevant

Technical requirements specification

System engineering plan

Project phasing and planning requirement document.

Objective and context of the trade-off study

The trade-off report shall contain a brief description of the purpose of the trade-off study and its context (e.g. logic, organization, process or procedure).

Key technical requirements

The trade-off report shall list the key technical requirements from the TS (as defined in ECSS-E-ST-10-06) to be satisfied by the possible alternative design solutions to conform to the needs or requirements of the user.

The research of possible alternative design solutions should not preclude the identification of design solutions which are not currently mature enough, but which can be potential design solution for future similar applications.

1. A possible design solution is a technical answer that has the capability to meet a set of technical requirements.

The system trade-off report shall identify and present the sources of information used to identify the possible design solution, e.g. R&D results, lessons learned, or similar applications.

Evaluation criteria

The trade-off report shall list the selected evaluation criteria and precise the justification for selecting those criteria, and provide the weighting of criteria and their justifications.

1. The criteria are selected theme by theme from the Technical Specification (as defined in ECSS-E-ST-10-06 Annex A), the programmatic aspects (including e.g. budget, schedule, etc… for development, manufacturing, as well as target cost for operations and recurrent items), and the technical risks.

The trade-off report shall identify the entity responsible for the evaluation of the design solutions for any criteria, as well as the source and agreement regarding weighting factors (e.g. with management).

Presentation of the alternative design solutions

The trade-off report shall present every different alternative design solutions proposed by the organization in charge of the development of the system or product, the proposals from the customer and supplier if any, and emphasize the technical description that is correlated to the criteria of evaluation.

The trade-off report shall characterize each alternative design solution in terms of technology status or maturity, performances capability, and risks.

Evaluation of the alternative design solutions

The system trade-off report shall present the result of the evaluation of every identified alternative design solution with regard to the key technical requirements.

For each alternative design solution the following shall be performed:

assessment of all the key technical requirements / evaluation criteria,

presentation of the pros and cons of the design solution, and

identification of the technical and programmatic risks.

The trade-off report shall present, in a table, the result of the evaluation per criteria.

Classification of the alternative design solutions

Based on the proposed scheme for weighting the evaluation criteria, the trade-off report shall provide a classification of the different alternative design solutions.

Analysis of the robustness of the classification

The trade-off report shall provide the result of a sensitivity analysis of the criteria that provide advantage to the solution ranked first, e.g. when changing the weighting of the evaluation criteria.

Conclusion

The trade-off report shall recommend one solution and explain the reason for this choice (e.g. evaluation criteria where the selected solution take advantage), and precise the condition for the application of the recommended solution.

The trade-off report shall present the identified technical and programmatic risks induced by the choice of the recommended solution, and any additional activity necessary to be performed for risk mitigation.

* + 1. Special remarks

None.

1. (normative)
<<deleted>>
2. (normative)
Requirements traceability matrix (RTM) - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.2.2b.

* + 1. Purpose and objective

The requirement traceability matrix (RTM) defines the relationships between the requirements of a deliverable product defined by a technical requirements specification and the apportioned requirements of the product's lower level elements.

The purpose of the RTM is to help verify that all stated and derived requirements are allocated to system components and other deliverables (forward trace).

The matrix is also used to determine the source of requirements (backward trace). Requirements traceability includes tracing any information that satisfy the requirements such as capabilities, design elements, and tests.

The RTM is also used to ensure that all requirements are met and to locate affected system components when there is a requirements change. The ability to locate affected components allows the impact of requirements changes on the system to be determined, facilitating cost, benefit, and schedule determinations.

* 1. Expected response
		1. Scope and content

Introduction

The RTM shall contain a description of the purpose, objective, content and the reason prompting its preparation.

Applicable and reference documents

The RTM shall list the applicable and reference documents in support to the generation of the document.

The RTM shall include the following:

Technical requirements specification (as defined in ECSS-E-ST-10-06 Annex A) of the product and its lower level elements

Product tree (as defined in ECSS-M-ST-10 Annex B)

Specification tree (as defined in ECSS-E-ST-10 Annex J).

Requirement traceability

The RTM shall list all the technical requirement of the product TS.

The RTM shall list all the lower level elements constituting the product and their technical requirements (contained in the lower-level element TS).

The requirement identification shall be identical in the RTM and the different TS.

Each technical requirement of the product shall be linked to at least one requirement of a lower level element.

1. The required visibility of the traceability down the elements of the product tree is depending on the criticality of some lower level elements w.r.t. the product requirements.

Each technical requirement of a lower level element should be linked to a technical requirement of the product.

When a technical requirement of a lower level element is not linked to a technical requirement of the product, this requirement shall be justified and an evaluation of its existence or removal on the product shall be agreed between the customer and the supplier.

* + 1. Special remarks

None.

1. (normative)
Requirements justification file (RJF) - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10, requirement 5.2.1e.

* + 1. Purpose and objective

The requirement justification file (RJF) is a generic title referring to all documentation which:

* Records and describes the needs and the associated constrains resulting from the different trade-offs.
* Demonstrates how the requirements of the technical requirements specification (TS) (as defined in ECSS-E-ST-10-06 Annex A) at each level can satisfy the needs and the constraints of the TS of the level above.
1. A top level RJF document is established at the upper level of the project structure that is, according to ECSS-M-ST-10, the first-level customer situated at level 0 of the customer supplier network. For other levels, the RJF is part of the design justification file (DJF) (as defined in, Annex K).
	1. Expected response
		1. Scope and content

Introduction

The RJF shall contain a description of the purpose, objective, content and the reason prompting its preparation.

Applicable and reference documents

The RJF shall list the applicable and reference documents in support to the generation of the document.

The RJF shall include the reference to the technical requirements specification.

Selected concept/solution justification

The RJF shall present the rationale for the selection of a concept for the technical requirements specification.

1. For justification, reference can be made to the system concept report of the considered project.

Life profile justification for the selected concept/solution

The RJF shall present and justify the life profile situations for the concept presented in the technical requirements specification.

1. For justification, reference can be made to the system concept report of the considered project where relevant.

Environments and constraints justification

The RJF shall present and justify the different environments and constraints for each life profile situations for the concept presented in the technical requirements specification.

1. For justification, reference can be made to the system concept report of the considered project where relevant.

Technical requirements justification

The RJF shall list all the technical requirements, and their identifier, expressed by the corresponding TS as they are organized in these documents.

For each technical requirement the following information shall be provided:

the justification of the requirement (i.e. justified source),

the Entity or owner responsible for the requirement,

if one technical requirement is induced by several sources, the reason of the specified performance,

the justification of the quantified performance (such as the range, the approach used to determine the level, e.g. measure, estimation),

the justification of the selected verification method.

Requirement traceability

The RJF shall present the requirement traceability between the technical requirements of the TS, and their justified source.

Compliance matrix for COTS

For COTS, the RJF shall contain a compliance matrix between the technical specification/characteristics of the COTS and the technical requirement expressed by the TS.

* + 1. Special remarks

The RJF may be part of the design justification file (DJF) (as defined in ECSS-E-ST-10 Annex K).

1. (normative)
Product user manual (PUM or UM) - DRD
	1. DRD identification
		1. Requirement identification and source document

This DRD is called from ECSS-E-ST-10 requirement 5.4.1.4c.

* + 1. Purpose and objective

The objective of the product user manual (PUM) is to provide information on design, operations and data of the product that is required by the user to handle, install, operate, maintain and dispose the product during its life time.

* 1. Expected response
		1. Scope and content

Introduction

The introduction shall describe the purpose and objective of the PUM.

Applicable and reference documents

The PUM shall list the applicable and reference documents in support of the generation of the document.

Product function definition

Product expected functions

The PUM shall provide a general description of the expected functions of the product during its lifetime in expected operational context and environment.

Product functional constraints

The PUM shall describe all product functional constraints.

Life time phases and purposes

The PUM shall address the whole product life cycle and all its modes:

Handling

Storage

Installation

Operations (nominal and contingency)

Maintenance

Disposal.

The PUM shall consider potential consequences of the environment on those sequences (e.g. sensor blinding, eclipses);

Product description

Design summary

The PUM shall include the following:

summary of the product design, showing the definition of the product, its constituents, the distribution of functions and the major interfaces;

block diagram of the product;

top-level description of the product software architecture;

description of nominal product operations scenarios and constraints e.g. mutually exclusive modes of operation, power or resource sharing.

Product level autonomy

The PUM shall include the following:

description of product-level autonomy provisions in the areas of fault management (FDIR);

definition, for each autonomous function, of the logic or rules used and of its internal (product constituents) and external interfaces.

Product configurations

The PUM shall include the following:

drawings of the overall product configuration in all product modes;

definition of the product reference axes system(s);

drawings of the product layouts.

Product budgets

The PUM shall provide the distribution (or allocation) of the following budgets, per product constituent, or per operating mode, as appropriate:

mass properties;

alignment;

power consumption for all operational modes;

thermal budget and constraints and predictions;

Description of interfaces and related budgets. (e.g. RF links);

telemetry and telecommand date rates;

memory;

timing.

Interface specifications

The PUM shall provide a cross-reference to the applicable version of the ICD.

Handling

The PUM shall describe the conditions and procedures for the handling of the product, be it integrated or stand-alone.

The PUM shall describe the specific design features, transport and environmental conditions, required GSE, and limitations for the handling of the product.

Storage

The PUM shall describe the conditions and procedures for the storage of the product, be it integrated or stand-alone.

The PUM shall describe the specific design features, environmental conditions, required GSE, monitoring requirements, life-limited items, health maintenance procedures (activation, monitoring) and limitations for the storage of the product.

Installation

The PUM shall describe the conditions and procedures for the installation of the product, be it integrated or stand-alone.

The PUM shall describe the specific design features, required GSE, modes, environmental conditions, and limitations for the installation of the product.

Product operations

<4.9.1> General

The PUM shall include timelines, modes and procedures, constraints to operate the product during its life cycle in nominal and contingency conditions, and highlight critical operations.

* 1. 1 When the product is a space segment, the product operations aspects are included in a specific part of the UM called Flight Operations Manual (FOM).
	2. 2 The implementation of the FOM by the ground segment responsible organisation is contained in the Mission Operations Plan (MOP, as defined in ECSS-E-ST-70 Annex G).

<4.9.2> Timelines

The PUM shall include:

Baseline event timelines for all nominal and contingency modes and phases.

Related constraints.

Each timeline shall contain a detailed description (i.e. down to the level of each single operational action) of the complete sequence of operations to be carried out, including a description of the rationale behind the chosen sequence of events, a definition of any constraints (e.g. absolute timing, relative timing) and the interrelationships between operations in the sequence.

<4.9.3> Product modes

The PUM shall describe all nominal and contingency modes, including:

their purpose (i.e. circumstances under which they are used),

the related procedures,

operational constraints,

resource utilization,

the definition of the associated modes, and

monitoring requirements.

The PUM shall describe the allowable mode transitions and the operations procedure corresponding to each such transition.

Appropriate cross-reference shall be made to product constituent modes and procedures.

<4.9.4> Product failure analysis

The PUM shall provide the results of the product failure modes, effects and criticality analysis (FMECA) and the resulting list of single point failures.

Potential product failures shall be identified by means of a fault-tree analysis (FTA).

Maintenance

The PUM shall describe the conditions, procedures and logistics for the maintenance of the product, be it integrated or stand-alone.

1. The description can refer to the document that conforms to the Integrated Logistic Support Plan in conformance with ECSS-M-ST-70.

Disposal

The PUM shall describe the conditions and procedures for the disposal of the product, be it integrated or stand-alone.

The procedures shall include passivation, as relevant.

The PUM shall identify the risks during and after disposal.

Products constituents description

General

The information specified in P.2.1<5.2> to P.2.1<5.9> shall be provided for each product constituent.

Product constituent design summary

The PUM shall describe the product constituent including:

the overall functions of the product constituent and the definition of its operational modes during the different mission phases;

description of any product constituent management functions, fault management concept and redundancy provisions;

a summary description of the component units/equipment and software including the functions which each supports;

product constituent functional block diagrams and a diagram showing the source of telemetry outputs and the sink of telecommand inputs;

interfaces;

budgets.

Product constituent design definition

The following shall be provided for each product constituent:

a detailed design description, including block diagrams, functional diagrams, logic and circuit diagrams;

physical characteristics including location and connections to the support structure, axes definition and alignment where relevant, dimensions and mass properties;

principle of operation and operational constraints of the product constituent;

lower level of breakdown for products composed of many complex elements.

Software

The PUM shall include:

description of software design,

product constituent software,

application process service software, and

memory map.

The PUM shall describe the organization of the software and its physical mapping onto hardware.

The PUM shall describe the details of each software component i.e. scheduler, interrupt handler, I/O system, telecommand packet handling system, telemetry packet handling system, including for each component its functions, component routines, input/output interfaces, timing and performance characteristics, flowcharts and details of any operational constraints.

For the application process service software, the PUM shall:

describe the services implemented making cross-reference to ECSS-E-ST-70-41 “Telemetry and telecommand packet utilization”, as tailored for the mission;

summarize all telemetry and telecommand structures (e.g. packets) including the conditions under which they are generated, the generation frequency, content and interpretation.

For each memory block, a map shall be provided showing RAM and ROM address areas, areas allocated for program code, buffer space and working parameters (e.g. content of protected memory).

Product component performance

The PUM shall describe all relevant product constituent performance characteristics, define the expected performance degradation as a function of time during the mission, and identify the resulting impact in terms of modifications to operational requirements or constraints.

Product component telemetry and telecommand lists

For each product constituent, the following lists shall be provided:

a list of the housekeeping telemetry parameters;

a list of the telecommands.

Each housekeeping telemetry shall have a functional description with validity conditions, telecommand relationship, and all technical information necessary for using it.

Each telecommand shall have a functional description with utilization conditions (e.g. pre-transmission validity, criticality level), command parameters (syntax and semantics) and execution verification in telemetry.

Product component failure analysis

The PUM shall describe:

Identification of potential product constituent failures by means of a systematic failure analysis (including a subsystem FMECA and FTA).

Identification of the methods by which the higher levels can identify a failure condition from analysis of the telemetry data and isolate the source of the failure.

Product components operations

The PUM shall describe:

product constituent modes;

nominal operational procedures;

contingency procedures.

product constituent modes shall be defined for all distinct nominal and back-up modes of the subsystem including:

purpose (i.e. conditions under which each is used);

operational constraints;

resource utilization;

the definition of the associated modes for each product constituent and its software functions;

higher level monitoring requirements;

identification of the allowable mode transitions and any product constituent operational constraints.

Nominal operational procedures shall be defined for each nominal mode transition identified under P.2.1<5.8>b.6.

For each procedure described in P.2.1<5.8>c., the following shall be provided:

an introduction describing the purpose of the procedure and the phase(s) or conditions when applicable;

the body of the procedure, structured according to operational steps, including:

pre-conditions for the start of the step defining, where applicable:

* product or product constituent level pre-requisites (e.g. configuration and resource requirements, such as power, fuel);
* external interfacing products pre-requisites.

telecommands to be sent;

telemetry data to be monitored to verify correct execution of the step;

interrelationships between steps (e.g. conditional branching within the procedure, timing requirements or constraints, hold and check points);

conditions for completion of the step.

Contingency procedures shall be defined for each failure case identified in the product constituent failure analysis (FMECA/FTA).

1. This can utilize a nominal operational procedure already identified in P.2.1<5.8>c. above.

For contingency procedures, the same details shall be provided as for nominal operational procedures in P.2.1<5.8>d. above.

Where the recovery method for a failure or group of failures is mode, mission, or phase dependent, separate procedures shall be described for each mode/mission phase.

Product component data definition

For each operational mode of the product constituent, sensor output data, conditions under which they are generated, their contents, and data rate shall be described.

Required on-board processing performed on sensor data and algorithms used for this shall be described.

* + 1. Special remarks

Where the objective is to allow for the accommodation of equipment designed a posteriori w.r.t an existing platform or vehicle, the following documents shall be part of the UM:

The accommodation handbook describing the location, mounting, all interfaces and clearances of equipment in a platform or vehicle.

The installation plan describing the approach, methods, procedures, resources and organization to install, commission, and check the operation of the equipment in its fixed operational environment.

1. <<deleted and replaced by informative Annex S>>
2. (informative)
Mapping of typical DDP to ECSS documents

|  |  |
| --- | --- |
| **Design Development Plan (DDP) content** | **ECSS coverage** |
| **Introduction*** General summary of the scope, objective and constraints
* Definition of responsibilities and pre-requisites
 | ECSS-M-ST-10-PMP <3>ECSS-E-ST-10-SEP <3.1>ECSS-M-ST-10-PMP <4> |
| **System definition including high level product tree*** Identification of customer furnished products
* Availability of and need to reuse existing products
* Specification tree
 | ECSS-M-ST-10-PTECSS-M-ST-60-9.6.2 req. ECSS-E-ST-10-SEP <4.2>.6 and <5.2.13>ECSS-M-ST-10-PT <3>.eECSS-E-ST-10-Annex J |
| **Technology assessment**Availability of and need to develop new technologies | ECSS-E-ST-10-SEP <5.2.5> ECSS-E-ST-10-TP <4.3> |
| **System design flow and philosophy of models*** Model philosophy
* Design margin philosophy for budgets
	+ Margin philosophy for requirements as flown down from system to subsystem- assembly – and equipment level
	+ Management of system resource allocation over the entire project phases and resource reporting to the next higher level
	+ Rationale
 | ECSS-E-ST-10-SEP <4.2>.4ECSS-E-ST-10-SEP <4.2>.5 |
| **System control and verification*** Qualification and acceptance philosophy
* Budget allocation philosophy
* Compliance to requirements demonstration philosophy
* High-level Assembly, Integration & Verification Plan, incl.:
	+ end to end test
	+ mission simulation and Dress Rehearsals
 | ECSS-E-ST-10-SEP <5.2.2> -> ECSS-E-ST-10-02-VP-> ECSS-E-ST-10-02-VCD (inc. VM) |
| **Planning and definition of milestones and reviews** including the analysis of the critical path(s)* definition and scope of reviews in terms of
	+ baselining of requirements and requirements control
	+ design releases and control of released design including external and internal interfaces
 | ECSS-M-ST-10-PMP <7> -> ECSS-M-ST-60-SECSS-M-ST-10-01 ECSS-E-ST-10-SEP <3.3> |
| **Definition of required Ground Support Equipment** and schedule of development and delivery |  |
| **Risk assessment** linked to development choices | ECSS-E-ST-10-SEP <5.4> <3.5>ECSS-M-ST-80-RAR |
| ECSS-M-ST-10-PMP | = ECSS-M-ST-10, Project management plan DRD-Annex A |
| ECSS-M-ST-10-PT | = ECSS-M-ST-10, Product tree DRD-Annex B |
| ECSS-M-ST-60-S | = ECSS-M-ST-60, Schedule DRD-Annex B |
| ECSS-M-ST-80-RAR | = ECSS-M-ST-80, Risk assessment report DRD-Annex C |
| ECSS-E-ST-10-SEP | = ECSS-E-ST-10, System engineering plan DRD-Annex D |
| ECSS-E-ST-10-TP | = ECSS-E-ST-10, Technology plan DRD-Annex E |
| ECSS-E-ST-10-02-VP | = ECSS-E-ST-10-02, Verification plan DRD-Annex A |
| ECSS-E-ST-10-02-VCD | = ECSS-E-ST-10-02, Verification control document DRD-Annex B (Note: Verification matrix = 1st issue of VCD) |

1. (informative)
Guideline content of Analysis Report
	1. DRD identification
		1. Requirement identification and source document

This report structure is called from the Note of ECSS-E-ST-10, requirement 5.3.1j and is provided as a guideline.

* + 1. Purpose and objective

The analysis report describes, for each analysis, the relevant assumptions, utilized methods, techniques and results.

* 1. Expected response
		1. Scope and content

Introduction

1. The analysis report contains a description of the purpose, objective, content and the reason prompting its preparation.
2. Any open issue, assumption and constraint relevant to this document are stated and described.

Applicable and reference documents

1. The analysis report lists the applicable and reference documents in support to the generation of the document, and make a clear reference to the configuration baseline of the product considered for the analysis.

Definitions and abbreviations

1. The analysis report lists the applicable dictionary or glossary and the meaning of specific terms or abbreviations utilized in the document with the relevant meaning.

Analysis approach

1. The analysis report summarizes the analysis content and the method utilized.

Assumptions and limitations

1. The analysis report describes the basic assumptions, the boundary conditions, validity of the analysis, life profile aspects, and all other related limitations.

Analysis description

1. The analysis report describes and justify the analysis methods used including software, tools and associated models.

Analysis results

1. The analysis report presents the main calculations, associated results, accuracies, sensitivities, margins where relevant.

Conclusions

1. The analysis report:
	1. summarizes the analysis results,
	2. summarizes the conditions of validity of this analysis,
	3. clearly states and describes any open issue.
2. Where the analysis report is used for the verification of requirements it lists the requirements to be verified (in correlation with the VCD), summarizes the analysis results, presents comparison with the requirements, and indicates the verification closeout judgements (e.g. requirement met / not met).
	* 1. Special remarks

None.

Bibliography

|  |  |
| --- | --- |
| ECSS-S-ST-00 | ECSS system – Description, implementation and general requirements |
| ECSS-E-ST-10-03 | Space engineering – Testing |
| ECSS-E-ST-10-04 | Space engineering – Space environment |
| ECSS-E-ST-10-11 | Space engineering – Human factors engineering |
| ECSS-E-ST-20 | Space engineering – Electrical and electronic |
| ECSS-E-ST-3x series | Space engineering – Materials series |
| ECSS-E-ST-40 | Space engineering – Software general requirements |
| ECSS-E-ST-50 | Space engineering – Communications |
| ECSS-E-ST-6x series | Space engineering – Control engineering series |
| ECSS-E-ST-70 | Space engineering – Ground systems and operations |
| ECSS-E-ST-70-41 | Space engineering – Telemetry and telecommand packet utilization |
|  |  |
| ECSS-E-TM-10-10 | Space engineering – Logistic engineering |
| ECSS-E-TM-10-20 | Space engineering – Product data exchange |
| ECSS-E-TM-10-21 | Space engineering – System modelling and simulation |
| ECSS-M-ST-60 | Space project management – Cost and schedule management |
| ECSS-M-ST-70 | Space project management – Integrated logistic support  |
| ECSS-M-ST-80 | Space project management – Risk management |
| ECSS-Q-ST-10 | Space product assurance – Product assurance management |
| IEEE P1220 | Standard for application and management of the systems engineering process |
| ISO 24113:2011  | Space systems – Space debris mitigation |