- (normative)
Assembly, integration and test plan (AITP) - DRD

  - DRD identification

    - Requirement identification and source document

This DRD is called from ECSS-E-ST-10-03, requirement 4.3.3.2a.

    - Purpose and objective

The assembly integration and test plan is the master plan for the product AIT process. It describes the complete AIT process and demonstrates together with the verification plan how the requirements are verified by inspection and test.

It contains the overall AIT activities and the related verification tools (GSE and facilities), the involved documentation, the AIT management and organization. It also contains the AIT schedule.

It is one of the major inputs to the project schedule and is used to provide the customer a basis for review and evaluation of the effectiveness of the AIT programme and its proposed elements.

An AITP is prepared for the different verification levels covering in detail the AIT activities at that level and outlining the necessary lower level aspects.

The AITP is complementary to the verification plan. It takes into account the test standards defined in the Customer requirements.

The availability of the verification plan is a prerequisite to the preparation of the AITP.

  - Expected response

    - Scope and content

          - Introduction

          - The AITP shall contain a description of the purpose, objective, content and the reason prompting its preparation.

          - Any open issue, assumption and constraint relevant to this document shall be stated and described.

          - Applicable and reference documents

          - The AITP shall list the applicable and reference documents in support to the generation of the document.

          - Definitions and abbreviations

          - The AITP shall list the applicable dictionary or glossary and the meaning of specific terms or abbreviations utilized in the document.

          - Product presentation

          - The AITP shall briefly describe the selected models and their built status with reference to the verification plan (see ECSS-E-ST-10-02).

          - Assembly, integration and test programme

          - The AITP shall document the AIT activities and associated planning.

          - The AITP shall include test matrix(ces) that link the various tests with the test specifications, test procedures, test blocks and hardware model.

          - Assembly, integration and test programmes including inspections, should be detailed through dedicated activity sheets.

          - Activity sheets shall include descriptions of the activity including the tools and GSE to be used, the expected duration of the activity, and the relevant safety or operational constraints.

          - The sequencing of activities should be presented as flow charts.

          - GSE and AIT facilities

          - The AITP shall list and describe the GSE, test software and AIT facilities to be used.

          - The AITP shall describe the logistics and list the major transportations.

          - AIT documentation

          - The AITP shall describe the AIT documents to be produced and their content.

          - Organization and management

          - The AITP shall describe the responsibility and management tools applicable to the described AIT process with reference to ECSS-E-ST-10-02.

          - The AITP shall describe the responsibilities within the project team, the relation to product assurance, quality control and configuration control (tasks with respect to AIT) as well as the responsibility sharing with external partners.

- Tasks with respect to AIT include for example, anomaly handling, change control, safety, and cleanliness.

          - The planned reviews and the identified responsibilities shall be stated.

          - AIT schedule

          - The AITP shall provide the AIT schedule as reference.

    - Special remarks

None.