## Sheet1
AIL
INDIVIDUAL STATUS
| Action # | MoM ref | Action | Actionee | Due date | Status | FT | VV | Close-out | Comment
| 1 | 2 | • Ch.5, normative documentation: add ECSS-E-ST-20, ECSS-E-ST-50-14 | FT | 2023-11-08 | C | C |  |  | ECSS-E-ST-10-24C-Rev.1-DRAFT0 (6February2023)WORKING COPY version 7Nov23
| 2 | 2 | • Ch.7, terms definitions and abbreviated terms: add EICD, MICD, TICD after checking if these acronyms are better introduced in the ECSS-S-ST-00-01 with the ECSS secretariat consider that MICD already appears in ECSS-E-ST-10-09 | FT | 2023-11-08 | C | C |  | Closed with respect to draft ECSS 9Nov23 | ECSS secretariat notified
| 3 | 2 | • Ch.7, terms definitions and abbreviated terms: add GERD after checking if this acronym is better introduced in the ECSS-E-ST-33-11 (where GDIR is already present) with the ECSS secretariat | FT | 2023-11-08 | C | C |  | Closed with respect to draft ECSS 9Nov23 | ECSS secretariat notified
| 4 | 2 | • Ch.7, terms definitions and abbreviated terms: identify that the following acronyms are already available in other ECSS: - DRD (ECSS-E-ST-10 and many others) - GDIR (ECSS-E-ST-33-11) - EQM (ECSS-E-ST-10-03, ECSS-Q-ST-70-60) check with ECSS secretariat if another column should be added in paragraph 3.3 of the draft ECSS-E-ST-10-24C to identify in which other ECSS standards applicable acronyms are | FT | 2023-11-08 | C | C |  | Closed with respect to draft ECSS 9Nov23 | ECSS secretariat notified
| 5 | 2 | • Ch. 8 space segment equipment remove all text in parentheses “(…)”from requirements and substitute it with notes | FT | 2023-11-08 | C | C |  |  | ECSS-E-ST-10-24C-Rev.1-DRAFT0 (6February2023)WORKING COPY version 7Nov23
| 6 | 2 | Req."The equipment EICD shall address any mating/de-mating connector constraint, if any." To be checked with other colleagues if this requirement is relevant to EICD or not (especially at equipment level). | ALL | 2023-11-08 | C | C | C | No such requirement in EICD agreed 23Nov23 | Email sent to EEWC and other colleagues 7Nov23 by FT.
| 7 | 2 | Check if other requirements can be formulated for equipment level EICD. | ALL | 2023-11-08 | C | C | C |  | Email sent to EEWC and other colleagues 7Nov23 by FT. Replies received by J. Aroca and A. Fernandez were discussed on the meeting of 23Nov23.
| 8 | 3 | Power interface, to make a difference between actual versus specified performances: it can be a recommendation (use “should”) and explain in a note the relevance of this point for recurrent products | FT | 2023-12-07 | C | C |  | ECSS-E-ST-10-24C-Rev.1-DRAFT0 (6February2023) WC 23Nov23 | See req. 5.8.1h.
| 9 | 3 | Frequency plan requirement: should it go to the EMCCP or in the EICD? Discuss it with the EMC experts (AI ALL). The best option is to introduce it into the EMCCP DRD in annex to the ECSS-E-ST-20C. | ALL | 2023-11-23 | C | C | C |  | CR to ECSS-E-ST-20C sent to require frequency plan in the EMCCP DRD in annex to the standard.
| 10 | 3 | Chapter 5.7 has been dedicated to requirements that apparently are not specific to EICD but seems applicable also to MICD and TICD. To be discussed with mechanical and thermal colleagues. | ALL | 2023-12-07 | C | C | C |  | FT discussed it with B. Laine (Mechanical LE in ESA). For outcome see MoM of meeting 4.
| 11 | 3 | Logical “Timing” needs of EICD (MICD, TICD) will be provided by VV in relevant requirements. They might be added to chapter 5.7 of the standard. | VV | 2023-12-07 | C |  | C | Mom #5 | It is decided not to provide specific inputs at the moment, the timing issue will be passed as an input to the EDS SAVOIR WG - see relevant AI.
| 12 | 3 | For uniformity, use “equipment” and not “unit” in all introduced requirements. | FT | 2023-12-07 | C | C |  | ECSS-E-ST-10-24C-Rev.1-DRAFT0 (6February2023) WC 23Nov23
| 13 | 3 | It seems that there is the need of some additional requirement in relation to which information is expected in the link/pin allocation table. For example unicity of signals at equipment level (for example the signal identifiers shall be uniquely named across equipment, s/s and system view). See 5.8.2j and 5.8.3j of the draft ECSS. | VV | 2023-12-07 | O |  | O |  | Unicity of naming was added as requirement (para 5.7 req. e.). Details on the template for the link/pin allocation table and relevant exchange of data to be addressed within EDS SAVOIR WG.
| 14 | 4 | We will indicate that the overall grounding diagram shall provided in the EICD or a reference shall be made in the EICD to the dedicated document which contains it. | FT | 2023-12-07 | C | C |  | Working Copy 4 Dec2023
| 15 | 4 | To check the presence of TMTC ICD in the existing ECSS requirements, or to provide a chapter covering that in the present standard. | ALL | 2023-12-07 | C | C | C | MoM #5 | 04Dec23: I am checking with SW experts.
| 16 | 4 | With reference to the comment on a provision of an interface template for supporting the harness design (electrical interconnections with other equipment) at a higher level, check with the originator of the comment if he referred only to the pin to pin table or if the request is more general. | FT | 2023-12-07 | C | C |  | Email FT to J. Aroca 04Dec23 16:58
| 17 | 4 | With reference to the requirement: “The equipment EICD shall refer to equipment module EICD of the modules used within the equipment” add a note explaining that we are speaking of modules under a different responsibility than the one of the overall equipment containing them. | FT | 2023-12-07 | C | C |  | Working Copy 4 Dec2023
| 18 | 4 | The following additional requirement and note is added to the standard to cover the issue of fault emission and fault tolerance (and similar requirements are added for space segment subsystem – 5.8.2d - and space segment element – 5.8.3d -). 5.8.1d Fault emission and fault tolerance requirements shall be specified, and then verified, for all equipment external electrical interfaces. NOTE Fault emission and fault tolerance requirements are expressed in terms of voltage and current. | FT | 2023-12-07 | C | C |  | ECSS-E-ST-10-24C-Rev.1-DRAFT0 (6February2023) WC 23Nov23
| 19 | 4 | Reference to (current, voltage) fault emission and fault tolerance definitions made in the ECSS-E-ST-20-20 will be added to the ECSS-E-ST-10-24 standard. | FT | 2023-12-07 | C | C |  | ECSS-E-ST-10-24C-Rev.1-DRAFT0 (6February2023) WC 23Nov23
| 20 | 4 | As for action 10 is concerned, the TCS ICD (TICD in our standard definition) is already requested in a DRD to ECSS-E-ST-31C. In our standard, we shall identify that specific TICD requirements are thereby provided. | FT | 2023-12-07 | C | C |  | Working Copy 4 Dec2023 | The recommendation of the present WG to the ECSS TA is to include all specific ICD (for TICD, MICD, TM/TC ICD) requirements and DRDs in the ECSS-E-ST-10-24 and remove them to other standards through CRs.
| 21 | 4 | Apparently, there is no formal set of requirements relevant to the Mechanical ICD in the ECSS set. A relevant CR will be raised to the ECSS-E-ST-32C “Structural general requirements” to either add a relevant DRD dedicated to the MICD there (like the TICD DRD present in the ECSS-E-ST-31C) or to update the ECSS-E-ST-10-24C to add a relevant set of requirements as done for the EICD part. | FT | 2023-12-07 | C | C |  |  | The recommendation of the present WG to the ECSS TA is to include all specific ICD (for TICD, MICD, TM/TC ICD) requirements and DRDs in the ECSS-E-ST-10-24 and remove them to other standards through CRs.
| 22 | 5 | WRT action 20 - To ask TA if it is better to import the DRD in this standard or refer to it. | FT | 2024-01-11 | C | C |  | MoM #5 | The recommendation of the present WG to the ECSS TA is to include all specific ICD (for TICD, MICD, TM/TC ICD) requirements and DRDs in the ECSS-E-ST-10-24 and remove them to other standards through CRs.
| 23 | 5 | WRT action 21 - To ask TA if it is better to import the DRD in this standard or refer to it. | FT | 2024-01-11 | C | C |  | MoM #5 | The recommendation of the present WG to the ECSS TA is to include all specific ICD (for TICD, MICD, TM/TC ICD) requirements and DRDs in the ECSS-E-ST-10-24 and remove them to other standards through CRs.
| 24 | 5 | From WG perspective, the best option for the moment is to reference in the present standard ECSS-E-ST-10-24 the existing information, DRD, requirements available for the TICD and TMTC ICDs, and to ask a change request for the missing mechanical ICD requirements (to be put either in the ECSS-E-ST-10-24 or as a normative DRD in the ECSS‐E‐ST‐32C “Structural general requirements”). | FT | 2024-01-11 | C | C |  | MoM #5 | The recommendation of the present WG to the ECSS TA is to include all specific ICD (for TICD, MICD, TM/TC ICD) requirements and DRDs in the ECSS-E-ST-10-24 and remove them to other standards through CRs.
| 25 | 5 | It is not possible to work out more elaborated solutions at the moment because of the limited WG composition (which included only electrical experts). The point will be communicated to the ECSS TA at the next report. | FT | 2024-01-31 | O | O
| 26 | 5 | For next meeting the full draft document ECSS-E-ST-10-24 shall be read by the WG members to identify any other possible improvements. | ALL | 2024-01-11 | C | C | C | MoM #5